## SOP-Job Description Mapping
SOP Number | SOP Title | Primary Role | Supporting Roles | Job Description Ref
9.2.005 | Review Contract for High-Risk Clauses | Project Manager | Contract Manager; Branch Manager | 7.3.1; 7.5
9.2.010 | Team Selection | Project Manager | General Superintendent; Branch Manager | 7.3.1; 7.2.5
9.2.015 | Project Turnover Meeting | Project Manager | Field Supervisor; Estimator | 7.3.1; 7.2.4; 7.3.3
9.2.040 | PM Reviews Plans Specs and Schedule | Project Manager | Estimator | 7.3.1; 7.3.3
9.2.050 | FS Reviews Plans Specs and Schedule | Field Supervisor (Foreman) | Project Manager | 7.2.4; 7.2.5
9.2.055 | Compare Est vs Planned | Project Manager | Field Supervisor; Estimator | 7.3.1; 7.2.4; 7.3.3
9.2.057 | Identify VE and Prefabrication Opportunities | Project Manager | Estimator; Pre-Fab Manager | 7.3.1; 7.3.3; 7.3.7
9.2.060 | Create Issue List and Begin RFI Process | Project Manager | Field Supervisor | 7.3.1; 7.2.4
9.2.070 | Conduct Site Visit | Project Manager | Field Supervisor; Safety Coordinator | 7.3.1; 7.2.4; 7.2.6
9.2.080 | Prepare Material Handling Plan | Project Manager | Field Supervisor; Purchasing | 7.3.1; 7.2.4; 7.4.4
9.2.090 | Develop Labor Budget | Project Manager | General Superintendent; Estimator | 7.3.1; 7.2.5; 7.3.3
9.2.100 | Prepare Layout and Sequencing Plan | Project Manager | Field Supervisor | 7.3.1; 7.2.4; 7.2.5
9.2.110 | Develop Project Schedule | Project Manager | Field Supervisor | 7.3.1; 7.2.4; 7.2.5
9.2.120 | Establish Tracking and Control Systems | Project Manager | Admin Support | 7.3.1; 7.4.5
9.2.130 | Construction Execution Kickoff Meeting | Project Manager | Field Supervisor; All Team | 7.3.1; 7.2.4; 7.2.5
9.2.140 | Develop Project Budget | Project Manager | Estimator; Branch Manager | 7.3.1; 7.3.3
9.2.160 | Develop Procurement Plan | Project Manager | Purchasing Manager | 7.3.1; 7.4.4
9.3.010-120 | Site Setup SOPs (Office, Storage, Power, etc.) | Foreman | Project Superintendent; Project Manager | 7.2.4; 7.2.5; 7.3.1
9.3.470 | Develop Site-Specific Safety Plan | Safety Coordinator | Project Manager; Foreman | 7.2.6; 7.4.6; 7.2.4
9.41.470-510 | Safety Management SOPs | Safety Coordinator | Foreman; All Field | 7.2.6; 7.4.6; 7.2.4
9.41.515-555 | Quality Management SOPs | Foreman | Project Superintendent; Project Manager | 7.2.4; 7.2.5; 7.3.1
9.41.560-595 | Resource Management SOPs | Project Manager | General Superintendent; Foreman | 7.3.1; 7.2.5; 7.2.4
9.41.600-670 | Procurement SOPs | Project Manager | Purchasing Manager; Foreman | 7.3.1; 7.4.4; 7.2.4
9.41.675-725 | Field Operations SOPs | Foreman | Project Superintendent; Project Manager | 7.2.4; 7.2.5; 7.3.1
9.6.005-085 | Project Closeout SOPs | Project Manager | Foreman; Admin Support | 7.3.1; 7.2.4; 7.4.5