## SOP-MD Mapping
SOP Number | SOP Title | Management Directive | MD Section | Alignment Notes
9.2.005 | Review Contract for High-Risk Clauses | MD 9.5; MD 9.7 | Contract Review - Scope (9.5); Post-Contract Award (9.7) | Aligns with PM contract review requirements and Estimating scope verification
9.2.010 | Team Selection | MD 9.4; MD 9.5 | Work Force Development (9.4); Field Leadership & Manpower (9.5) | Aligns with Gen Supt workforce development and PM staffing responsibilities
9.2.015 | Project Turnover Meeting | MD 9.5; MD 9.7 | Project Pre-Planning (9.5); Project Turnover Meeting (9.7) | Required by both PM and Estimating directives for project handoff
9.2.040-055 | Plans/Specs Review SOPs | MD 9.3; MD 9.5 | Pre-Planning (9.3); Job Plans (9.5) | Aligns with Field Leadership pre-planning and PM job monitoring
9.2.057 | Identify VE and Prefabrication | MD 9.5; MD 9.7 | Prefabrication (9.5); Value Engineering Alternates (9.7) | Aligns with PM prefab requirements and Estimating VE directives
9.2.060 | Create Issue List/RFI Process | MD 9.5; MD 9.7 | Document Control (9.5); RFI Process (9.7) | Aligns with PM document control and Estimating RFI requirements
9.2.070 | Conduct Site Visit | MD 9.5 | Job Site Visits (9.5) | Aligns with PM job site visit requirements (minimum twice per month)
9.2.080 | Material Handling Plan | MD 9.5 | Submittals & Purchasing (9.5) | Aligns with PM coordination with Purchasing Department
9.2.090 | Develop Labor Budget | MD 9.4; MD 9.5 | Manpower Projections (9.4); Job Plans (9.5) | Aligns with Gen Supt workforce planning and PM labor tracking
9.2.100-110 | Layout/Sequencing/Schedule SOPs | MD 9.5 | Scheduling (9.5) | Aligns with PM scheduling directives including pull planning
9.2.120 | Establish Tracking Systems | MD 9.5 | Job Plans; Document Control (9.5) | Aligns with PM tracking and job plan requirements
9.2.130 | Construction Kickoff Meeting | MD 9.5; MD 9.7 | Project Pre-Planning (9.5); Project Turnover Meeting (9.7) | Transition point from planning to execution per PM and Estimating directives
9.3.xxx | Site Setup SOPs | MD 9.3 | Execution of the Plan (9.3) | Aligns with Field Leadership plan execution requirements
9.41.470-510 | Safety SOPs | MD 9.2; MD 9.3; MD 9.4 | Safety Requirements (9.2); Safety Management (9.3); Safety Enforcement (9.4) | Aligns with all safety requirements across field employee, leadership, and superintendent directives
9.41.675 | Daily Huddles | MD 9.3 | Execution of the Plan (9.3) | Aligns with Field Leadership daily work layout requirements
9.41.680 | Weekly Foreman Meetings | MD 9.4 | Work Force Development Coordination (9.4) | Aligns with Gen Supt weekly PM meeting attendance requirement
9.41.690-700 | Tracking SOPs | MD 9.3; MD 9.5 | Reporting (9.3); Job Plans (9.5) | Aligns with Field Leadership reporting and PM job plan tracking
9.41.215 | Daily Reports | MD 9.3; MD 9.5 | Daily Reports (9.3); Weekly Project Status Reports (9.5) | Aligns with Field Leadership daily reporting and PM weekly status requirements
9.41.360 | Change Orders | MD 9.3; MD 9.5 | Changed Work (9.3); Change Order Requests (9.5) | Aligns with Field Leadership change authorization and PM change order management
9.6.xxx | Closeout SOPs | MD 9.5 | Project Closeout - Required Documents (9.5) | Aligns with PM closeout requirements (interviews, O&M, warranty, billing, evaluations, surveys)