# Policy Manual 9.5

## Management Directives for Project Management

## CROSS-REFERENCE SUMMARY

| Target Audience | Project Managers, Contract Managers, Business Managers |
| --- | --- |
| Related Job Descriptions | Policy 7.3.1 (Operations Management / Project Manager) |
| Implementing SOPs | 9.2.xxx Pre-Construction SOPs; 9.41.xxx Execution SOPs; 9.6.xxx Closeout SOPs |
| Required Training | Project Planning; Scheduling; ProCore; ViewPoint; Values-Driven Leadership; Productivity Analysis |

## PURPOSE

To establish expectations and requirements for GSL Project Management regarding contract administration, pre-planning, execution monitoring, cost control, and project closeout.

## SCOPE

Applies to all Project Managers, Contract Managers, and Business Managers responsible for GSL project delivery.

## KEY DIRECTIVES

### Contract Review

Scope of Work shall include work set forth in GSL's bid

Scope must be consistent with Prime Agreement

Review with Estimating to ensure clarifications identified in contract

### Schedule Analysis

Perform schedule analysis prior to establishing bid price

Request detailed copy of schedule if not included

Determine cost impacts of aggressive or elongated schedules

### Pre-Planning

Conduct Project Turnover Meetings with Estimating

Review bid documents and pre-construction checklist

Prepare Project Organization Chart

Prepare man-loaded schedule and Schedule of Values

### Prefabrication

Review each project for prefabrication opportunities

Coordinate with GSL's prefabrication team

Utilize BIM Modeling for raceway systems layout

### Scheduling

Take initiative on project scheduling

Work with Field Leadership on look ahead schedules

Utilize Pull Planning by milestone

Identify beginning dates and normal durations

### Job Monitoring

Focus on executing the plan with sufficient job site time

Minimum twice per month job site visits (every week if possible)

Review daily reports and prepare Weekly Project Status Reports

Communicate delays, disruptions, scope changes to Contract Managers

### Job Plans

Track labor productivity by comparing budgeted to actual hours

Determine positive/negative labor hour variances

Update at least monthly for change orders and adjustments

Share Job Costs/Estimates Report with Field Leadership weekly

### Change Orders

Submit timely, accurate change order requests

Follow-up on pending change orders

Always request time extensions when necessary

### Project Closeout

Complete Field Leadership Interviews

Operations and Maintenance Manuals

Letter of Warranty

Final Progress and Retention Billing

Employee Evaluations

General Contractor or Owner Survey

## IMPLEMENTING STANDARD OPERATING PROCEDURES

The following SOPs implement the requirements of this Management Directive:

SOP 9.2.005 - Review Contract for High-Risk Clauses

SOP 9.2.010 - Team Selection

SOP 9.2.015 - Project Turnover Meeting

SOP 9.2.040 - PM Reviews Plans, Specifications & Schedule

SOP 9.2.110-130 - Schedule and Kickoff SOPs

SOP 9.2.140 - Develop Project Budget

SOP 9.41.315-350 - Scheduling SOPs

SOP 9.41.355-390 - Change Order SOPs

SOP 9.41.395-465 - Cost Control SOPs

SOP 9.6.010-085 - Closeout SOPs

## TRAINING REQUIREMENTS

Personnel subject to this directive must complete:

Project Planning and Execution (Tab 2) - Upon promotion

ProCore Fundamentals (Tab 57) - First 90 days

ViewPoint Change Orders (Tab 8) - First 90 days

Scheduling Techniques (Tab 6) - First 6 months

Job Plan Management (Tab 7) - First 6 months

Values-Driven Leadership (Tab 51) - Ongoing

Productivity Analysis (Tab 56) - First year

## JOB DESCRIPTION ALIGNMENT

This directive applies to Project Manager positions defined in Policy Manual 7.3.1. The Project Manager job description includes compliance with MD 9.5 as a primary responsibility.

## COMPLIANCE AND ENFORCEMENT

Compliance is mandatory. Weekly Project Status Reports must be submitted. Progress billings and job plan updates must be completed monthly by required dates. Under billings must be avoided.

## ACKNOWLEDGEMENT

Project Managers must acknowledge understanding of these directives upon assignment to project management role.