GSL ELECTRIC
Standard Operating Procedure (SOP)

Title: SOP 9.2.010/9.2.015: Team Selection and Estimator Turnover
Department: Operations / Purchasing
Effective Date: [Insert Date]
Approved By: [Insert Approving Authority]
Reviewed By: [Insert Reviewer Name]
Version: 1.0

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials:

- Tab 3: Kickoff/Project Turnover Meeting (Estimating-Kickoff Meeting.docx, Modified Kickoff Meeting Form.docx)

- Tab 51: Job Structure & Org Chart (Job Structure and Organizational Chart.pptx)

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.5 Project Superintendent

- 7.3.1 Operations Management

- 7.3.3 Estimating

Management Directives (Policy Manual Section 9):

- 9.4 Management Directives for General Superintendents

- 9.5 Management Directives for Project Management

- 9.7 Management Directives for Estimating

Key Requirements:

- Per MD 9.5: 'GSL's Contract Manager, Branch Manager, Project Manager and Project Field Leadership shall meet with GSL's estimators to review the bid documents and contract documents'

- Per MD 9.7: 'The estimating department shall participate in the Project Turn-Over Meeting with the Operations Project Management team following the Turn-Over Meeting Agenda'

- Per MD 9.7: 'All value engineering options shall be reviewed. All major vendors and subcontractors shall be discussed'

================================================================================

Pre-Construction Planning Activities

## SOP 9.2.010/9.2.015: Team Selection and Estimator Turnover

### 1. Purpose

To establish a structured process for selecting the project management and field leadership teams and to ensure effective knowledge transfer from the estimating phase to project execution.

### 2. Scope

This procedure applies to all projects transitioning from the estimating phase to execution, ensuring that the appropriate personnel are selected and adequately briefed for successful project delivery.

### 3. Procedure

#### Activity 1: Finalize Selection of Project Team

- 1.1 The Branch Manager selects the Project Manager, considering factors such as current workload, expertise, and project requirements.

- 1.2 The Branch Manager and General Superintendent jointly decide on the Field Supervisor, evaluating their experience, availability, and suitability for the project. If necessary, collaborate with the Project Manager.

Responsible Parties: Branch Manager (Project Manager selection); Branch Manager & General Superintendent (Field Leadership selection)

#### Activity 2: Conduct Estimator Turnover Meeting

- 2.1 Schedule a formal Estimator Turnover Meeting to transition all relevant information from the Estimator to the Project Manager and Field Leadership. Conduct the meeting in-office to avoid distractions and allow for comprehensive planning.

- 2.2 Invite key team members including the Branch Manager/VP of Operations, General Superintendent, Pre-Fab Superintendent, Field Leadership, Safety, depending on project size and complexity.

- 2.3 Use a standardized checklist to cover:

  - Contractual scope, exclusions, and assumptions

  - Budget details and material procurement strategies

  - Key milestones, manpower, and pre-fab opportunities

  - Job plan expectations and reporting structure

  - Safety, document control, and change order processes

Responsible Parties: Estimator (facilitator), Project Manager, Branch Manager/VP of Operations, Field Supervisor, General Superintendent, Pre-Fab Superintendent

### 4. Documentation and Tools

- Team Selection Checklist

- Estimator Turnover Meeting Agenda

- Responsibility Matrix

- Job Plan Forms

- Document Control Logs

### 5. Compliance

Adherence to this SOP is mandatory. Any deviations must be approved by GSL’s Branch Management.

| SOP | Project Manager | Project Foreman | Business Manager | Contract Manager | Branch Manager | Estimator | General Superintendent | Pre-Fab Superintendent | Purchasing | Safety |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Activity 1: Finalize Selection of Project Team |  |  |  |  | x |  | x |  |  |  |
| #### Activity 2: Conduct Estimator Turnover Meeting | x | x |  |  |  | x | x | x |  |  |