SOP 9.055.190 – Procurement of Large Feeder Wire

Department: Project Management / Purchasing
Created by: Tom Ewing
Effective Date: [Insert Date] Version: 1.0
Related SOPs: SOP 9.056.190 – Release of Large Feeder Wire; SOP 9.057.190 – Feeder Wire Procurement & Release Log; GSL Wire Release Conditions

1. Overview

This SOP defines the process for procuring and releasing large feeder wire to ensure timely pricing lock, submittal preparation, coordination with vendors, and Just-In-Time (JIT) delivery. It also outlines GSL’s release conditions to minimize waste, ensure usable spool lengths, and align procurement with project schedules.

2.

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.4.4 Purchasing Manager

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Scope

This procedure applies to all projects requiring feeder wire (typically #1 AWG and larger), both for temporary and permanent installations. It is intended for Project Managers (PMs), Assistant Project Managers (APMs), Project Coordinators (PCs), Purchasing staff, and Field Leadership.

3. Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager (PM) | Confirms feeder quantities and schedule with the PE/APM or Project Coordinator. Approves final procurement decisions. |
| Assistant Project Manager (APM) / Project Coordinator | Verifies feeder sizes and lengths from drawings, validates quantities, and prepares submittals. |
| Purchasing / Buyer | Issues RFQs, compares vendor quotes, reviews vendor history, confirms terms, and places purchase orders. |
| Field Leadership | Confirms spool sizes and provides delivery timing preferences. |

4. Requirements

- Cable sizes, types, and footage are required at the estimating stage.

- Preplanning takeoff lengths with BIM modeling (if available) may be used later to verify conduit paths, but are not required for procurement.

- Required documents and tools include:

  - Large Wire / Cable BOM Form

  - Approved submittals (verify wire sizes against approved gear)

  - Feeder schedule or riser diagram

  - Project schedule

  - RFQ template and vendor contact list

  - Delivery tracking spreadsheet

5. Process

Step 1 – Feeder Procurement & Release Log populated

Upon Notice of Award or Letter of Intent, the PM exports feeder information from the Accubid file and loads it into the Feeder Wire Procurement & Release Log (see SOP 9.057.190).

- PM, APM/PC, and Foreman confirm:

  - Submittal requirements

  - Feeder size, quantity, and length

  - Conductor Material (CU, AL)

  - Color coding, labeling, and insulation type (if applicable)

Step 2 – 2+ vendor quotes documented and archived

Purchasing issues RFQs including details such as wire type/size, quantity, delivery terms, reel specifications, freight, taxes, and reel return policy.

- RFQ response time: 2–3 business days

- Vendors must acknowledge and agree to GSL Wire Release Conditions.

Step 3 – PO with pricing lock and lead times

PM reviews quotes and selects vendors based on best value.  Including: price per foot, availability, lead time, spool sizes, approved manufacturers, and vendor performance.

- PM signs off on selected quote; Purchasing issues purchase order.

- Billed upon release, not procurement

Step 4 – Submittal Preparation

- PM/APM/PC assembles the submittal package per project specifications.

- No wire releases may occur until submittals are approved.

Step 5 – Pre-Planning with Field Supervision

- PM collaborates with Field Supervision to define site logistics, routing, material handling, and installation timelines.

- BOM and Conduit/Wire Pull Schedule are prepared using scaled drawings.

Step 6 – Storage and Release Conditions

- Vendors must store all procured wire at their warehouse until GSL issues a release notice.

- Submittal approval before release: mandatory

- Upon release, vendors cut and bundle feeders onto single spools (or coils for short runs), including:

  - Colored phase and neutral conductors

  - Ground conductor (spooled separately if size differs)

- Vendors should use standard inventory stock when possible to minimize waste and ensure usable lengths.

- Vendors are expected to manage spool usage responsibly, ensuring practical lengths are available for releases.

- Wire and cable are billed to GSL upon release, not upon initial procurement.

Appendix:

- Feeder Wire Procurement & Release Log1.xlsx