SOP 9.2.030 – Review Contract for Unfavorable or High-Risk Clauses

Department: Project Management / Pre-Construction
Created by: Schachinger Solutions GmbH
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule
Reference: GSL Pre-Construction Planning – Contract Review

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To ensure all project contracts are reviewed systematically for unfavorable or high-risk clauses that could affect project execution, budget, or liability, and to define mitigation measures prior to mobilization.

Scope

This SOP applies to all Project Managers during the pre-construction phase of awarded projects. It covers all contract types including general conditions, subcontract agreements, and owner-issued contracts.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Leads contract review, completes checklist, and escalates risks. |
| Estimator | Provides bid assumptions and clarifications for comparison. |
| Field Supervisor | Identifies field-related risks tied to contractual obligations. |
| Branch Manager | Approves mitigation strategy for high-risk clauses. |

Required Documents and Tools

- Contract Review Checklist (Table 4.6)

- Executed contract documents (general conditions, terms, scope)

- Bid submission and clarification letters

- Insurance and bonding requirements

Procedure

Step 1: Collect Documents

- Gather executed contracts, specifications, drawings, and bid clarifications.

Step 2: Review Key Clauses

- Complete Contract Review Checklist with focus on:

  - Indemnification and liability allocation

  - Delay clauses and liquidated damages

  - Dispute resolution (ADR, arbitration, mediation)

  - Change order notification procedures

  - Insurance, bonding, and permit requirements

Step 3: Identify Risks

- Flag unfavorable terms and propose mitigation strategies.

- Review risks with Branch Manager for approval.

Step 4: Recordkeeping

- Save completed checklist and notes in the project folder.

- Incorporate findings into turnover meeting agenda (SOP 9.41.010).

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Completed Contract Review Checklist | Project Manager | Project Folder |
| Risk Notes & Mitigation Plan | PM | Pre-Construction Binder |
| Updated Agenda Notes | PM | Smartsheet Turnover Agenda |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of contracts reviewed before turnover | 100% |
| All risks documented in Contract Review Checklist | 100% |
| High-risk clauses escalated to Branch Manager | 100% |

References

- GSL Pre-Construction Planning – Section 4.3 Scope and Contract Review

- Contract Review Checklist (Table 4.6)

Appendix

- Contract Review Checklist (sample)

- Insurance & Bonding Matrix

- Dispute Resolution Clause Examples