GSL ELECTRIC
Standard Operating Procedure (SOP)

Title: SOP 9.2.030-070: Scope and Contract Review
Department: Operations / Project Management / Field Leadership
Effective Date: [Insert Date]
Approved By: [Insert Approving Authority]
Reviewed By: [Insert Reviewer Name]
Document Owner: [Insert Name]
Next Review Date: [Insert Review Cycle]
Version: 1.0

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials:

- Tab 2: Preplanning & Staging (Pre-Planning Foreman.docx)

- Tab 4: Staging & Job Familiarization (JOB FAMILIARIZATION, STAGING II.ppt)

- Tab 6: Scheduling (2-C.c.4 Scheduling Foreman.docx)

- Tab 7: Job Plans (New Job Plan Procedures subfolder)

- Tab 11: Estimating Take-off Procedures

- Tab 29: Evaluating the Job Plan (JOB PLAN SUMMARY.pptx)

- Tab 30: Jobsite Efficiency

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.5 Project Superintendent

- 7.3.1 Operations Management

- 7.3.3 Estimating

- 7.3.7 Pre-Fabrication

Management Directives (Policy Manual Section 9):

- 9.5 Management Directives for Project Management

- 9.7 Management Directives for Estimating

Key Requirements:

- Per MD 9.5: 'GSL's scope of work must also be consistent with the Prime Agreement between the General Contractor and the Owner'

- Per MD 9.5: 'Branch Management and Project Management shall review with Estimating to ensure that all clarifications and exclusions in GSL's Bid Proposal are specifically identified'

- Per MD 9.5/9.7: 'It is imperative that a schedule analysis be performed prior to establishing the bid price'

- Per MD 9.5: 'Project Management shall review each of their projects and proactively determine the scope of work that can effectively be prefabricated'

================================================================================

Pre-Construction Planning Activities

SOP 9.2.030-070: Scope and Contract Review (over $2M) Training Materials and Smartsheets

1. Purpose

To ensure comprehensive understanding of project requirements and contract obligations by thoroughly reviewing the scope, specifications, plans, and contract documents prior to execution.

2. Scope

This procedure applies to Project Managers, Field Supervisors, and other relevant staff responsible for interpreting project deliverables, identifying risk clauses, assessing scheduling constraints, planning field execution, and ensuring contract compliance before commencing physical work.

3. Procedure

The Scope and Contract Review process encompasses eight core activities, each supported by specific checklists and collaborative reviews among office and field leadership.

Activity 1: Contract Risk and Requirements Review

- Complete the Contract Review Checklist (Table 4.6).

- Identify all required bonds, permits, and insurance certificates.

- Review billing timelines and invoicing requirements.

- Understand and document the formal Change Order procedures.

- Identify any Alternative Dispute Resolution (ADR) requirements (e.g., mediation or arbitration), noting whether they are binding or non-binding.

Responsible Parties: Business Manager, Project Manager, Contract Manager, Branch Manager

Activity 2: Project Manager’s Scope and Schedule Review

- Order and distribute sufficient sets of plans and specifications.

- Complete the Scope and Schedule Review Checklist (Table 4.7).

- Reconcile contract scope with bid scope to identify discrepancies.

- Review discrepancies between drawings and specifications.

- Assess schedule feasibility and determine if acceleration measures are necessary.

Responsible Parties: Project Manager, Estimator

Activity 3: Field Supervisor’s Execution Planning

- Complete the Scope and Schedule Review Checklist.

- Review company best practices and lessons learned.

- Identify Value Engineering (VE) and prefabrication opportunities.

- Estimate manpower requirements and initiate foreman selection.

- Identify specialty tools required for efficient execution.

Responsible Parties: Field Supervisor, General Superintendent, Pre-Fab Superintendent

Activity 4: RFI Process Setup

- Compile questions arising from the review of drawings and specifications.

- Assign RFI numbers and submit them to the General Contractor/Owner following established protocols.

Responsible Parties: Project Manager, Field Supervisor

Activity 5: Site Visit (Recommended)

- Complete the Site Visit Checklist (Table 4.8).

- Evaluate site logistics, including laydown space and access points.

- Identify available lifts, cranes, and utility connections.

- Plan for the setup of temporary power systems.

- Verify actual site conditions against design assumptions.

Responsible Parties: Field Supervisor, Project Manager

Activity 6: Bid vs. Execution Strategy Comparison

- Compare the estimator’s assumptions with the planned field execution strategy.

- Clarify any discrepancies directly with the estimator.

- Document potential cost savings or overruns.

Responsible Parties: Project Manager, Field Supervisor, Estimator

Activity 7: Value Engineering and Simplification

- Reassess VE and prefabrication opportunities identified during turnover.

- Identify new methods to simplify work processes (e.g., bulk wire ordering, labeling systems).

- Calculate potential savings or additional costs associated with implementation.

Responsible Parties: Project Manager, Field Supervisor

Activity 8: Construction Takeoff

- Perform a detailed takeoff based on the planned installation sequence.

- Include waste factors and specify purchasing units.

- Compare the construction takeoff with the bid takeoff to identify significant discrepancies.

Responsible Parties: Project Manager, Purchasing, Estimator

4. Documentation and Tools

- Contract Review Checklist (Table 4.6)

- Scope and Schedule Review Checklist (Table 4.7)

- Site Visit Checklist (Table 4.8)

- RFI Log and Tracker

- Construction Takeoff Sheets and Color Codes

- Cost Control Report

5. Compliance

All identified discrepancies, risks, or scheduling concerns must be communicated to Branch and Executive Management. Adherence to this SOP is mandatory to mitigate project risks and ensure successful delivery.

| SOP | Project Manager | Project Foreman | Business Manager | Contract Manager | Branch Manager | Estimator | General Superintendent | Pre-Fab Superintendent | Purchasing |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity 1: Contract Risk and Requirements Review | x | x | x | x | x |  |  |  |  |  |
| Activity 2: Project Manager’s Scope and Schedule Review | x |  |  |  |  | x |  |  |  |  |
| Activity 3: Field Supervisor’s Execution Planning |  | x |  |  |  |  | x | x |  |  |
| Activity 4: RFI Process Setup | x | x |  |  |  |  |  |  |  |  |
| Activity 5: Site Visit (Recommended) | x | x |  |  |  |  |  |  |  |  |
| Activity 6: Bid vs. Execution Strategy Comparison | x | x |  |  |  | x |  |  |  |  |
| Activity 7: Value Engineering and Simplification | x | x |  |  |  |  |  |  |  |  |
| Activity 8: Construction Takeoff | x |  |  |  |  | x |  |  | x |  |