SOP 9.2.040 – Project Manager Reviews Plans, Specifications & Schedule

Department: Project Management
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.015 – Review Contract for Unfavorable or High-Risk Clauses; 9.41.025 – Field Supervisor Reviews Plans, Specifications & Schedule
Reference: GSL Pre-Construction Planning – Scope & Schedule Review

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To ensure that the Project Manager conducts a detailed review of project drawings, specifications, and schedules to confirm alignment with contract requirements and identify risks before mobilization.

Scope

This SOP applies to all Project Managers for awarded projects during the pre-construction planning phase.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Performs review of drawings, specifications, and schedules; documents findings and updates the Project Execution Plan (PEP). |
| General Superintendent | Validates manpower feasibility and resource planning. |
| Estimator | Provides bid documentation and assumptions for comparison. |
| Branch Manager | Confirms alignment with branch capacity and execution strategy. |

Required Documents and Tools

- Latest project drawings and specifications

- Contract documents and milestone schedules

- Bid package and clarification letters

- Scope & Schedule Review Checklist (Table 4.7)

- Project Execution Plan (PEP) template

Procedure

Step 1: Gather Documents

- Collect all drawings, specifications, and contractual schedules.

- Obtain bid submission documents for baseline comparison.

Step 2: Review Drawings and Specifications

- Verify scope completeness and identify omissions, conflicts, or design gaps.

- Compare against contract inclusions/exclusions.

Step 3: Review Schedule

- Validate milestone dates, phasing, and dependencies.

- Identify long-lead items or sequencing conflicts.

Step 4: Document Findings

- Complete the Scope & Schedule Review Checklist.

- Record risks and clarifications in the PEP.

Step 5: Communicate Results

- Share findings with Superintendent, Estimator, and Branch Manager.

- Update turnover materials as required.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Scope & Schedule Review Checklist | Project Manager | Project Folder |
| Updated PEP | PM | Project Folder |
| Review Notes | PM | Pre-Construction Binder |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of drawings and specs reviewed before mobilization | 100% |
| Milestones validated against schedule | 100% |
| Discrepancies documented in review checklist | 100% |

References

- GSL Pre-Construction Planning – Section 4.3 Scope & Contract Review

- Scope & Schedule Review Checklist (Table 4.7)

Appendix

- Scope & Schedule Review Checklist (sample)

- Project Execution Plan (PEP) template

- Example Bid Clarification Letter