SOP: 9.2.050 - Field Supervisor Reviews Plans, Specifications & Schedule

Department: Field Operations

Related SOPs:

- 9.2.040 - PM Reviews Plans, Specifications & Schedule

- 9.2.060 - Create List of Issues & Begin RFI Process

- 9.2.070 - Conduct Site Visit

- 9.2.100 - Prepare Layout & Sequencing Plan

============================================================

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.5 Project Superintendent

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

PURPOSE

============================================================

To ensure field leadership conducts a thorough review of project plans, specifications, and schedule from a constructability perspective, identifying potential issues before field mobilization.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Project has been awarded and team assigned

- Field leadership has been selected

- Pre-construction planning phase is underway

- Constructability input is needed

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Field Supervisor (R) | Conducts detailed constructability review; Documents issues and concerns; Provides installation sequence input |

| General Superintendent (A) | Validates field concerns; Approves constructability assessment; Coordinates multi-project lessons learned |

| Project Manager (C) | Provides contract context; Coordinates with design team; Incorporates field input into planning |

| Safety Coordinator (C) | Reviews safety-related constructability concerns |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Current set of drawings (all disciplines)

- Project specifications

- Project schedule

- Site logistics plan (if available)

- Previous similar project lessons learned

- Constructability review checklist

============================================================

PROCEDURE

============================================================

STEP 1 - Obtain Current Documents

--------------------------------------

Field Supervisor obtains from PM:

- Latest drawing set (electrical and other trades)

- Relevant specification sections

- Preliminary project schedule

- Site photos or as-built information

- Contract special conditions affecting field work

STEP 2 - Review Electrical Drawings

--------------------------------------

Conduct detailed review focusing on:

- Panel locations and accessibility

- Conduit routing and coordination

- Equipment placement and clearances

- Prefab opportunities

- Installation sequence constraints

- Code compliance concerns

STEP 3 - Review Other Trade Drawings

--------------------------------------

Coordinate review with other disciplines:

- Mechanical conflicts (routing, equipment)

- Structural impacts (penetrations, supports)

- Architectural finishes (ceiling heights, access)

- Fire protection coordination

- Plumbing conflicts

STEP 4 - Assess Schedule Feasibility

--------------------------------------

Review schedule from field perspective:

- Work sequence logic

- Crew loading requirements

- Material delivery timing

- Area access and availability

- Weather considerations

- Other trade dependencies

STEP 5 - Document Issues and Concerns

--------------------------------------

Create issue list including:

- Constructability concerns

- Coordination conflicts

- Missing or unclear information

- Scope gaps or assumptions

- Prefab recommendations

- Schedule concerns

STEP 6 - Participate in Planning Meetings

--------------------------------------

Share findings with project team:

- Present issues at turnover/planning meetings

- Support RFI development (SOP 9.2.060)

- Contribute to layout & sequencing plan (SOP 9.2.100)

- Validate labor budget assumptions (SOP 9.2.090)

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| FS review completed before kickoff meeting | 100% |

| Constructability issues documented | 100% |

| Input provided to layout & sequencing plan | 100% |

| Coordination conflicts identified early | 100% |

============================================================

APPENDIX

============================================================

- Constructability Review Checklist

- Common Coordination Issues Reference

- Lessons Learned Database Access

- Issue Documentation Form

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.025 â€“ FS Reviews Plans, Specs & Schedule

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Field Operations | Approver: Executive Committee