SOP 9.2.060 – Create List of Issues & Begin RFI Process

Department: Project Management / Pre-Construction
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.025 – Field Supervisor Reviews Plans, Specifications & Schedule; 9.41.035 – Conduct Site Visit
Reference: GSL Pre-Construction Planning – RFI Process

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To provide a standardized process for documenting project issues and resolving them through the Request for Information (RFI) process before construction begins.

Scope

This SOP applies to Project Managers, Field Supervisors, and Estimators for all awarded projects during the pre-construction phase.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Creates and manages the RFI Log, drafts RFIs, and ensures timely submission and tracking. |
| Field Supervisor | Identifies constructability issues during field reviews and submits them for RFI consideration. |
| Estimator | Provides input on bid assumptions related to identified issues. |
| General Superintendent | Reviews RFI outcomes for manpower and sequencing impacts. |
| Branch Manager | Monitors the status and timeliness of RFI resolutions. |

Required Documents and Tools

- RFI Log Template

- Standard RFI Form (Figure 4.4)

- Project drawings and specifications

- Bid clarifications and assumptions

Procedure

Step 1: Identify Issues

- Document all conflicts, discrepancies, omissions, or unclear items found during plan/spec/contract reviews or site visits.

Step 2: Create Issue List

- Maintain a running list of issues in the RFI Log.

- Prioritize issues that could affect safety, scope, budget, or schedule.

Step 3: Draft RFI

- Complete an RFI Form with a clear question, reference drawing/spec, and proposed solution (if applicable).

Step 4: Submit RFI

- Submit RFI to GC/Owner per contract requirements.

- Assign tracking numbers for each submission.

Step 5: Track Responses

- Update the RFI Log with submission date, response due date, and final resolution.

- Distribute responses to project stakeholders.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| RFI Log | Project Manager | Project Folder / RFI Subfolder |
| RFI Forms | PM | Shared Folder / Submitted to GC |
| Issue List | PM / FS | Pre-Construction Binder |

Compliance & Review

| KPI | Target |
| --- | --- |
| All issues documented before mobilization | 100% |
| RFI responses received before affected work starts | ≥95% |
| RFI Log updated within 24 hours of activity | 100% |

References

- GSL Pre-Construction Planning – Section 4.3 Scope and Contract Review

- Figure 4.4 – Standard RFI Form

Appendix

- RFI Log Template

- Example Completed RFI

- Open Issue Tracking Sheet