SOP 9.2.070 – Conduct Site Visit

Department: Field Operations / Project Management
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.040 – Compare Estimated vs. Planned Performance
Reference: GSL Pre-Construction Planning – Site Visit Checklist

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.5 Project Superintendent

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To confirm that site conditions align with project documents and to identify potential risks or discrepancies that may affect construction execution.

Scope

This SOP applies to Field Supervisors, Project Managers, and Safety Coordinators. A pre-mobilization site visit must be performed for all awarded projects.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Field Supervisor | Conducts site visit, completes checklist, and documents findings. |
| Project Manager | Integrates site visit findings into the Project Execution Plan (PEP). |
| Safety Coordinator | Identifies site-specific hazards and updates the Safety Plan. |
| General Superintendent | Reviews site visit outcomes for manpower, logistics, and sequencing implications. |

Required Documents and Tools

- Site Visit Checklist (Table 4.8)

- Current project drawings and specifications

- Camera or mobile device for documentation

- PPE (Personal Protective Equipment)

Procedure

Step 1: Schedule Site Visit

- PM and Field Supervisor coordinate with Owner/GC for site access.

Step 2: Perform Site Walk

- Review site access, laydown areas, parking, and staging space.

- Verify availability of utilities (power, water, etc.).

- Assess storage, handling, and safety/security conditions.

Step 3: Document Findings

- Complete Site Visit Checklist with observations and supporting photos.

- Highlight discrepancies from drawings/specifications.

Step 4: Report Outcomes

- Submit completed checklist to PM.

- Incorporate findings into turnover discussion and PEP.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Completed Site Visit Checklist | Field Supervisor | Project Folder |
| Site Photos | Field Supervisor | Project Folder / Shared Drive |
| Updated PEP Notes | Project Manager | PEP File |

Compliance & Review

| KPI | Target |
| --- | --- |
| Site visit completed before mobilization | 100% |
| Checklist completed and filed | 100% |
| Discrepancies documented in RFI log (if applicable) | 100% |

References

- GSL Pre-Construction Planning – Section 4.3 Site Visit

- Site Visit Checklist (Table 4.8)

Appendix

- Sample Site Visit Checklist

- Example Site Logistics Plan

- Photo Documentation Guidelines