SOP 9.2.080 – Prepare Material Handling Plan

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.065 – Develop Labor Budget
Reference: GSL Pre-Construction Planning – Material Handling Plan

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.5 Project Superintendent

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To prepare a material handling plan that ensures safe, efficient, and cost-effective delivery, movement, and storage of project materials on site.

Scope

This SOP applies to Project Managers and Field Supervisors during pre-construction planning.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Ensures material handling plan aligns with procurement schedule and project milestones. |
| Field Supervisor | Develops logistics details for delivery, staging, and installation of materials. |
| Safety Coordinator | Reviews plan for safety compliance and hazard prevention. |
| General Superintendent | Validates manpower and equipment needs. |

Required Documents and Tools

- Site Visit Checklist (SOP 9.41.035)

- Project logistics/site layout plan

- Equipment and delivery schedules

- Safety guidelines and handling standards

Procedure

Step 1: Review Site Conditions

- Use site visit results to evaluate laydown areas, access points, and storage options.

Step 2: Define Material Flow

- Map delivery routes, unloading areas, staging zones, and installation paths.

Step 3: Coordinate with Procurement

- Align handling requirements with delivery schedules (long-lead and critical items).

Step 4: Develop Plan

- Complete Material Handling Plan form with:

  - Delivery schedules

  - Staging areas

  - Equipment needs (lifts, hoists, cranes)

  - Storage methods and constraints

Step 5: Safety Review

- Validate plan against OSHA and GSL safety requirements.

- Incorporate site-specific hazard controls.

Step 6: Communicate & File

- Share plan with project team and subcontractors.

- Save approved plan to project folder.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Material Handling Plan | Field Supervisor | Project Folder |
| Updated Logistics Notes | Project Manager | PEP File |

Compliance & Review

| KPI | Target |
| --- | --- |
| Plan completed before mobilization | 100% |
| Plan reviewed and approved by Safety Coordinator | 100% |
| Plan distributed to project stakeholders | 100% |

References

- GSL Pre-Construction Planning – Section 4.5 Material Handling Plan

Appendix

- Material Handling Plan Template

- Example Site Logistics Diagram

- Equipment Requirements Checklist