SOP 9.2.090 – Develop Labor Budget

Department: Project Management / Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.060 – Prepare Material Handling Plan; 9.41.070 – Prepare Layout & Sequencing Plan
Reference: GSL Pre-Construction Planning – Budget Preparation

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.5 Project Superintendent

- 7.3.1 Operations Management

- 7.3.3 Estimating

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To establish a labor budget based on estimated quantities, productivity rates, and planned sequencing to provide accurate benchmarks for tracking and project control.

Scope

This SOP applies to Project Managers and General Superintendents during pre-construction planning for all awarded projects.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Develops detailed labor budget and integrates into the Project Execution Plan (PEP). |
| General Superintendent | Reviews and validates manpower projections. |
| Estimator | Provides labor assumptions from bid documents. |
| Branch Manager | Reviews and approves the final labor budget. |

Required Documents and Tools

- Final Construction Takeoff (SOP 9.41.050)

- Bid labor assumptions and productivity data

- Labor budget template

- PEP (Project Execution Plan)

Procedure

Step 1: Gather Inputs

- Collect bid labor assumptions, productivity rates, and construction takeoff data.

Step 2: Develop Labor Forecast

- Allocate labor hours by task, trade, and project phase.

- Identify peak manpower requirements.

Step 3: Validate Forecast

- Review with General Superintendent for feasibility.

- Adjust based on workforce capacity and sequencing.

Step 4: Document Budget

- Complete the Labor Budget Worksheet.

- Integrate labor budget into the PEP.

Step 5: Approvals

- Submit labor budget to Branch Manager for review and sign-off.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Labor Budget Worksheet | Project Manager | Project Folder |
| Updated PEP | PM | Project Folder |
| Branch Approval Record | Branch Manager | Branch Records |

Compliance & Review

| KPI | Target |
| --- | --- |
| Labor budget completed before mobilization | 100% |
| Reviewed by General Superintendent | 100% |
| Approved by Branch Manager | 100% |

References

- GSL Pre-Construction Planning – Section 4.6 Budget Preparation

Appendix

- Labor Budget Worksheet Template

- Productivity Rate Reference Sheet

- Example PEP Labor Section