SOP 9.080.41 – Establish Tracking & Control Systems

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs:

- 9.075.41 – Develop Project Schedule

- 9.085.41 – Construction Execution Kickoff Meeting

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

- 7.4.4 Purchasing Manager

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To define the process for implementing project tracking and control systems that monitor labor, material, productivity, costs, and schedule performance during project execution.

Scope

Applies to all projects and must be initiated before field mobilization. Used by the PM, PE, GS, Foreman, and support staff throughout the job lifecycle.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Establishes systems, oversees updates, and uses data for decision-making. |
| Project Engineer | Maintains logs, trackers, and reports. |
| General Superintendent | Confirms field tracking is accurate and useful. |
| Foreman / Field Lead | Inputs daily information and participates in reviews. |
| Branch Admin / Support | Supports data entry and system consistency. |

Required Documents and Tools

- Labor tracking sheet or app

- Procurement log

- Submittal log

- Project schedule (baseline and updated)

- RFI and change order tracker

- GSL Daily Log / Progress Report templates

- Budget tracking worksheet

Procedure

Step 1: Set Up Job Cost and Labor Tracking

- PM and PE configure:

  - Job cost codes

  - Labor budgets by phase/system

  - Daily labor report template (crew count, hours, tasks)

- Assign responsibility for daily input (typically Foreman or PE)

Step 2: Configure Procurement and Submittal Tracking

- Update vendor log with:

  - Submittal due and returned dates

  - PO issue dates and delivery windows

- Assign Purchasing or PE to update weekly

Step 3: Establish Communication and Reporting Rhythm

- Set cadence for:

  - Daily logs from the field

  - Weekly labor reports

  - Procurement/submittal review meetings

  - Monthly project review (PM and Branch Manager)

Step 4: Implement Schedule Monitoring

- PM/PE track:

  - Task progress vs. baseline

  - Missed milestones or float use

  - Submittals and material delays impacting work

- Update schedule bi-weekly or monthly depending on duration

Step 5: Use Data for Course Correction

- Review labor efficiency weekly with Foreman and GS

- Flag systems or crews falling behind budget

- Escalate long-lead or delivery issues to Branch Leadership

- Document issues in project risk log

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Labor Tracking Sheet | Foreman / PE | Job Cost Folder |
| Procurement and Submittal Logs | PE / Buyer | Procurement Folder |
| Weekly Progress Report | PM / PE | GC / Internal Share Folder |
| Updated Project Schedule | Project Manager | Project Planning Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| All tracking systems in place before first field install | 100% |
| Daily logs and weekly updates submitted on time | 100% |
| Monthly reviews completed with leadership | 100% |

References

- Labor Budget (SOP 9.065.41)

- Procurement and Submittal Logs

- Project Schedule (SOP 9.075.41)

- GSL Project Review Framework

Appendix

- Tracking Sheet Templates

- Weekly Progress Report Sample

- Procurement Risk Summary