SOP 9.085.41 – Construction Execution Kickoff Meeting

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs:

- 9.080.41 – Establish Tracking & Control Systems

- 9.090.41 – Setup Office Trailer

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.5 Project Superintendent

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

- 7.4.4 Purchasing Manager

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To formally launch field construction by aligning the project team, reviewing key work plans, confirming roles, and addressing critical first-week activities before installation begins.

Scope

Applies to all projects immediately prior to the start of construction. Participants include PM, PE, GS, Foreman, Safety, Prefab, and Procurement representatives.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Schedules and leads the kickoff meeting, prepares materials, and assigns action items. |
| General Superintendent | Presents field execution strategy and sequencing. |
| Foreman / Field Lead | Reviews manpower, install areas, and early work packages. |
| Safety Coordinator | Reviews job-specific safety plan and onboarding process. |
| Prefab Lead | Confirms prefab install readiness and delivery coordination. |
| Project Engineer | Prepares support documents and logs follow-up items. |

Required Documents and Tools

- Final labor budget and schedule

- Layout & sequencing plan

- Safety plan and job hazard analysis (JHA)

- Prefab plan and first delivery dates

- First-week work package

- Construction Execution Kickoff Agenda Template

Procedure

Step 1: Schedule the Meeting

- PM schedules the Construction Execution Kickoff to occur:

  - Before field mobilization

  - After all plans, logistics, and safety reviews are complete

- Required attendees notified at least 3 business days in advance

Step 2: Prepare Kickoff Materials

- PM and PE prepare:

  - Job schedule with labor curves

  - Project drawings and site maps

  - Material delivery schedule

  - Safety orientation packet

  - Prefab tracking and BOM review

Step 3: Conduct the Kickoff Meeting

Meeting topics include:

- Project scope and critical dates

- Initial work areas and field layout

- Daily reporting and communication protocol

- Prefab deliveries and install strategy

- Safety orientation and expectations

- Material handling and first-week manpower plan

- Open issues and escalation protocol

Step 4: Assign and Log Action Items

- PE documents all discussion items and action points

- Assign each action with a due date and responsible owner

- Upload notes to project folder and email summary to team

Step 5: Monitor Execution of Plan

- GS and PM follow up on first-week tasks

- Confirm:

  - Crew onboarding

  - Site setup

  - Material arrival

  - Work installed per layout plan

- Escalate any execution risks immediately

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Kickoff Agenda and Meeting Notes | PM / PE | Project Folder / Coordination |
| First Week Execution Checklist | Foreman / GS | Field Documentation Folder |
| Action Log and Status Tracker | Project Engineer | Project Control Tools Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Kickoff held prior to first day of installation | 100% |
| All required stakeholders present or represented | 100% |
| First-week tasks tracked and completed on schedule | 100% |

References

- Layout & Sequencing Plan (SOP 9.070.41)

- Safety Program and JHA Template

- Prefab Plan (SOP 9.090.41)

- Project Schedule

Appendix

- Kickoff Agenda Template

- First Week Manpower & Task Tracker

- Prefab Delivery Map Example