SOP 9.2.130 – Construction Execution Kickoff Meeting

Department: Project Management / Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.080 – Establish Tracking & Control Systems; 9.42.005 – Oversee Field Safety Planning with Safety Coordinator
Reference: GSL Pre-Construction Planning – Construction Execution Kickoff

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.5 Project Superintendent

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

- 7.4.4 Purchasing Manager

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To conduct a structured kickoff meeting at the start of field mobilization, ensuring the project team is aligned on scope, schedule, safety, manpower, procurement, and client expectations.

Scope

This SOP applies to all awarded projects and must be completed before construction activities commence.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Organizes and leads the meeting; prepares agenda and distributes supporting documents. |
| General Superintendent | Confirms manpower assignments and validates sequencing strategy. |
| Field Supervisor | Reviews site logistics and constructability with the team. |
| Purchasing | Provides procurement and delivery updates. |
| Safety Coordinator | Presents site-specific safety plan and hazard analysis. |
| Branch Manager | Confirms kickoff aligns with branch goals and provides oversight. |

Required Documents and Tools

- Kickoff Meeting Agenda template

- Project Execution Plan (PEP)

- Baseline Project Schedule (SOP 9.41.075)

- Procurement Log (SOP 9.41.055)

- Site-Specific Safety Plan (SSSP)

- Project Responsibility Matrix

Procedure

Step 1: Schedule Meeting

- PM schedules meeting within 5 business days of mobilization.

- Invite all required participants (see Roles & Responsibilities).

Step 2: Prepare Agenda

- Draft agenda including: scope, schedule, budget, manpower, procurement, safety, logistics, and reporting protocols.

- Distribute agenda at least 48 hours before meeting.

Step 3: Conduct Meeting

- Cover:

  - Contractual scope and milestones

  - PEP highlights

  - Safety plan and hazard controls

  - Procurement status and delivery schedule

  - Manpower assignments and sequencing

  - Communication and reporting protocols

Step 4: Document Outcomes

- Record attendance, minutes, and action items.

- Upload agenda and minutes to project folder within 48 hours.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Kickoff Agenda & Minutes | Project Manager | Project Folder |
| Attendance Sheet | PM / Admin | Project Folder |
| Updated PEP Notes | PM | Project Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Kickoff completed before field mobilization | 100% |
| Minutes and action items distributed within 48 hrs | ≥95% |
| Attendance by all required roles | 100% |

References

- GSL Pre-Construction Planning – Section 4.10 Construction Execution Kickoff

- Project Execution Plan (PEP) Template

- Site-Specific Safety Plan

Appendix

- Kickoff Agenda Template

- Attendance Sheet Template

- Communication Matrix