SOP 9.41.600 – Develop Procurement Plan

Department: Project Management / Procurement
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.005 – Team Selection; 9.41.395 – Develop Project Budget; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Procurement

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.3.3 Estimating

- 7.4.4 Purchasing Manager

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To prepare a procurement plan that identifies all major materials, equipment, and subcontracted services required for the project, including lead times and responsibilities.

Scope

This SOP applies to Project Managers, Estimators, and Purchasing.
All procurement plan documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Develops procurement plan with input from Estimator and Field. |
| Estimator | Provides historical pricing and bid scope references. |
| Purchasing | Confirms vendor capabilities and lead times. |
| Branch Manager | Approves final procurement plan. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Project estimate and budget

- Procurement plan template

Procedure

- Review contract, estimate, and schedule.

- Identify long-lead items and critical subcontract scopes.

- Assign procurement responsibilities (PM, Purchasing, Field).

- Establish lead times and required delivery dates.

- File approved plan per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Procurement Plan | Project Manager | Per SOP 190A |
| Lead Time Schedule | Purchasing | Per SOP 190A |
| Approval Record | Branch Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Procurement plan developed within 30 days of turnover | 100% |
| 100% of long-lead items identified | 100% |
| Plan reviewed monthly | 100% |

References

- GSL Project Manager Procedures – Procurement

- SOP 9.41.190A – Document Filing Standards

Appendix

- Procurement Plan Template

- Lead Time Schedule Example