SOP 9.3.010 – Setup Office Trailer

Department: Project Management / Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.095 – Setup Storage Trailer; 9.41.100 – Setup Site Fencing and Access Control
Reference: GSL Project Manager Procedures – Mobilization (formerly EPMP Implementation Manual)

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 4: Staging & Job Familiarization

- Tab 22: Document Management

Job Descriptions (Policy Manual Section 7):

- 7.2.5 Project Superintendent

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

Purpose

To establish a standardized process for setting up the office trailer to ensure project management and administrative staff have a functional workspace with necessary utilities, communication systems, and safety features.

Scope

This SOP applies to Project Managers and Site Administrators responsible for site mobilization on all projects requiring an office trailer.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Secures trailer, ensures utilities and internet setup, coordinates placement on site. |
| Site Administrator | Sets up furniture, equipment, and documentation systems. |
| General Superintendent | Confirms trailer location supports site logistics and safety. |
| IT/Communications | Ensures phone, internet, and networking are operational. |

Required Documents and Tools

- Site logistics plan

- Trailer setup checklist

- Utility service agreements (electric, water, sewer)

- Communications plan

Procedure

Step 1: Confirm Location

- Review site logistics plan and determine trailer placement.

- Ensure access for staff and deliveries, with safe separation from construction zones.

Step 2: Secure Utilities

- Arrange power, water, and sewer connections.

- Install HVAC as needed for climate control.

Step 3: Install Communications

- Set up internet, phones, and networking.

- Verify functionality before staff occupancy.

Step 4: Equip Trailer

- Provide desks, chairs, filing cabinets, printers, copiers, and whiteboards.

- Stock office supplies (paper, pens, binders, etc.).

Step 5: Safety Setup

- Install fire extinguishers, first aid kits, and emergency exit signage.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Trailer Setup Checklist | Project Manager | Project Folder |
| Utility Connection Records | PM | Project Folder |
| IT Setup Log | IT/Communications | Project Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Trailer fully operational prior to mobilization | 100% |
| Utilities and communications tested before occupancy | 100% |
| Safety equipment installed and documented | 100% |

References

- GSL Project Manager Procedures – Mobilization

Appendix

- Office Trailer Setup Checklist

- Site Logistics Plan Example