SOP 9.3.040 – Setup Temporary Power

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.090 – Setup Office Trailer; 9.41.095 – Setup Storage Trailer; 9.41.100 – Setup Site Fencing and Access Control
Reference: GSL Project Manager Procedures – Mobilization

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 4: Staging & Job Familiarization

- Tab 22: Document Management

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

Purpose

To establish reliable temporary power for construction activities, ensuring safe, code-compliant distribution throughout the jobsite.

Scope

This SOP applies to Project Managers, Field Supervisors, and subcontractors involved in temporary power installation and inspection.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Coordinates power requirements with owner/utility and ensures budget coverage. |
| Field Supervisor | Oversees installation, verifies distribution points, and inspects for safety. |
| Electrical Subcontractor | Installs temporary panels, wiring, and grounding per code. |
| Safety Coordinator | Verifies OSHA and NEC compliance. |

Required Documents and Tools

- Site logistics plan

- Temporary power drawings/layout

- Utility service agreements

- Safety inspection forms

Procedure

Step 1: Assess Requirements

- Review project scope and determine temporary power needs.

- Identify required voltage, amperage, and distribution points.

Step 2: Coordinate with Utility

- Submit applications for temporary service.

- Confirm installation timeline with owner/utility provider.

Step 3: Install Distribution System

- Install panels, feeders, and distribution boxes per plan.

- Ground all systems and provide GFCI protection.

Step 4: Safety Review

- Inspect for trip hazards, exposed conductors, and improper grounding.

- Correct deficiencies before use.

Step 5: Document and File

- Record inspection results and utility confirmations.

- Maintain log of temporary power usage and inspections.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Temporary Power Setup Checklist | Field Supervisor | Project Folder |
| Utility Service Records | PM | Project Folder |
| Safety Inspection Log | Safety Coordinator | Safety Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Temporary power installed prior to mobilization | 100% |
| NEC and OSHA compliance verified | 100% |
| Inspection log updated weekly | 100% |

References

- GSL Project Manager Procedures – Mobilization

- NEC / OSHA Standards

Appendix

- Temporary Power Setup Checklist

- Site Power Layout Example