SOP 9.4.010 – Conduct Coordination Meetings

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.160 – Conduct Owner/GC Coordination Meetings; 9.41.170 – Conduct Progress Meetings; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Coordination

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To establish a standard process for conducting project coordination meetings to ensure alignment between all project stakeholders, resolve issues, and review progress.

Scope

This SOP applies to Project Managers, Field Supervisors, Subcontractors, and Design Team representatives.
All coordination meeting documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Schedules and chairs coordination meetings, sets agenda. |
| Field Supervisor | Provides field updates and identifies coordination issues. |
| Subcontractors | Share progress updates and upcoming needs. |
| Design Team / Consultants | Provide design clarifications as required. |
| Site Administrator | Records minutes, action items, and files records. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Coordination meeting agenda template

- Action item log

Procedure

- Schedule coordination meetings weekly (or as required by project).

- Prepare and distribute meeting agenda at least 24 hours in advance.

- Conduct meeting covering:

  - Safety

  - Progress updates

  - Upcoming activities

  - Coordination issues (site access, deliveries, manpower, conflicts)

  - Action items

- Record attendance and meeting minutes.

- Distribute minutes within 48 hours.

- File minutes and action item log per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Meeting Agenda | Project Manager | Per SOP 190A |
| Meeting Minutes | Site Administrator | Per SOP 190A |
| Action Item Log | Project Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Agendas issued 24 hrs before meetings | 100% |
| Minutes distributed within 48 hrs | 100% |
| Action items closed by due dates | ≥95% |

References

- GSL Project Manager Procedures – Coordination

- SOP 9.41.190A – Document Filing Standards

Appendix

- Coordination Meeting Agenda Template

- Action Item Log Example