SOP 9.4.040 – Compare Estimated vs. Planned Performance

Department: Project Management / Estimating
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.045 – Identify Value Engineering & Prefabrication Opportunities
Reference: GSL Pre-Construction Planning – Bid vs. Execution Review

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To confirm that bid assumptions for labor, materials, and productivity align with the planned project execution strategy, ensuring accurate budgets and realistic performance goals.

Scope

This SOP applies to Project Managers and Estimators during the pre-construction planning phase of all awarded projects.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Compares estimated assumptions with planned execution; documents adjustments. |
| Estimator | Provides bid documentation, scope notes, and clarifications. |
| General Superintendent | Reviews manpower and sequencing implications of variances. |
| Branch Manager | Validates budget alignment with operational strategy. |

Required Documents and Tools

- Estimator’s bid package and clarifications

- Final Construction Takeoff (SOP 9.41.050)

- Labor productivity data

- Budget tracking tools

- Project Execution Plan (PEP)

Procedure

Step 1: Collect Documents

- Obtain bid package, assumptions, and estimator clarifications.

Step 2: Compare Labor & Materials

- Review bid productivity rates versus manpower plan.

- Confirm material quantities align with construction takeoff.

Step 3: Identify Variances

- Document discrepancies that may affect budget, schedule, or scope.

Step 4: Adjust Plan

- Incorporate adjustments into the PEP and labor budget.

- Escalate significant deviations to Branch Manager for resolution.

Step 5: Record & File

- Save comparison notes and updated budget files to project folder.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Bid vs. Execution Comparison Notes | Project Manager | Project Folder |
| Updated PEP | PM | Project Folder |
| Variance Report | PM / Estimator | Branch Manager |

Compliance & Review

| KPI | Target |
| --- | --- |
| Comparison completed before mobilization | 100% |
| Variances documented and resolved pre-construction | 100% |
| Adjustments incorporated into PEP | 100% |

References

- GSL Pre-Construction Planning – Section 4.3 Bid vs. Execution Review

Appendix

- Sample Comparison Worksheet

- Variance Tracking Template