SOP 9.4.050 – Conduct Prefabrication Coordination Meetings

Department: Project Management / Prefabrication
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.045 – Identify Value Engineering & Prefabrication Opportunities; 9.41.050 – Prepare Construction Takeoff; 9.41.065 – Develop Labor Budget
Reference: GSL Project Manager Procedures – Coordination

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.5 Project Superintendent

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To coordinate with the prefabrication team to align prefab deliverables with the construction schedule, manpower plan, and site logistics.

Scope

This SOP applies to Project Managers, Prefab Leads, and Field Supervisors during pre-construction and throughout project execution.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Schedules and facilitates prefab meetings; tracks action items. |
| Prefabrication Lead | Identifies prefab opportunities, provides shop schedules, and confirms delivery dates. |
| Field Supervisor | Validates prefab strategies for constructability and installation feasibility. |
| General Superintendent | Confirms manpower availability and sequencing for prefab installations. |

Required Documents and Tools

- Prefabrication proposal log

- Prefab shop schedule

- Project schedule (SOP 9.41.075)

- PEP (Project Execution Plan)

Procedure

- Schedule Meetings – Coordinate bi-weekly or as needed based on prefab scope.

- Prepare Agenda – Cover prefab deliverables, delivery schedules, manpower, and logistics.

- Conduct Meeting – Review prefab shop status and field readiness.

- Resolve Issues – Address design conflicts, delivery risks, or manpower constraints.

- Record & Distribute Outcomes – Save minutes and update prefab coordination log.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Prefab Meeting Agenda | Project Manager | Project Folder |
| Meeting Minutes | PM | Project Folder |
| Prefab Coordination Log | Prefab Lead | Shared Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Prefab meetings conducted bi-weekly | 100% |
| Delivery schedules aligned with project milestones | 100% |
| Issues resolved within 1 week | ≥90% |

References

- GSL Project Manager Procedures – Coordination

Appendix

- Prefab Coordination Log Template

- Sample Meeting Agenda