SOP 9.4.200 – Manage Submittals

Department: Project Management / Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.1
Related SOPs: 9.41.050 – Prepare Construction Takeoff; 9.41.055 – Procurement of Large Feeder Wire; 9.41.075 – Develop Project Schedule; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Documentation Management

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.4.4 Purchasing Manager

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To establish a standard process for preparing, submitting, tracking, and closing out all project submittals to ensure compliance with specifications and schedule.

Scope

This SOP applies to Project Managers, Purchasing, and Subcontractors.
All submittal documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Prepares submittal log, ensures timely submissions. |
| Purchasing | Coordinates vendor submittals. |
| Subcontractors | Provide required shop drawings and product data. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Project specifications

- Submittal log

Procedure

- Identify required submittals from project specs.

- Enter submittals into project log.

- Submit for review and approval.

- Track responses and distribute approved versions.

- File per SOP 190A requirements.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Submittal Log | Project Manager | Per SOP 190A |
| Approved Submittals | PM | Per SOP 190A |
| Distribution Records | PM | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Submittal log created within 5 days of turnover | 100% |
| Submittals submitted before work begins | ≥95% |
| Approved submittals distributed within 24 hrs | 100% |

References

- GSL Project Manager Procedures – Documentation Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- Submittal Log Template

- Sample Submittal Form