SOP 9.4.220 – Manage Drawing Logs (Procore)

Department: Project Management / Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.205 – Manage RFIs (Requests for Information)
Reference: GSL Project Manager Procedures – Documentation Management; Procore Drawings Module

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To maintain an accurate and up-to-date drawing log using Procore’s Drawings tool, ensuring the field team always has access to the latest drawings and revisions.

Scope

This SOP applies to Project Managers, Site Administrators, and Field Supervisors.
All drawings, revisions, and markups will be filed and maintained in Procore as the system of record.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Reviews and publishes drawings in Procore. |
| Site Administrator | Uploads drawings, manages revisions, and maintains metadata. |
| Field Supervisor | Ensures crews access latest drawings in Procore. |

Required Documents and Tools

- Procore Drawings tool

- Current contract drawings and revisions

- Linked RFIs/Submittals in Procore

Procedure

- Upload New Drawings – SA uploads into Procore Drawings tool.

- Review & Publish – PM reviews and publishes for field access.

- Markup & Link – Add notes, link RFIs/Submittals in Procore.

- Field Access – Supervisors confirm field crews use Procore mobile app.

- Audit – PM audits Procore drawing log monthly.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Current Drawing Log | Procore System | Procore |
| Revision History | Site Administrator | Procore |
| Linked RFIs/Submittals | PM / SA | Procore |

Compliance & Review

| KPI | Target |
| --- | --- |
| New drawings uploaded within 24 hrs of receipt | 100% |
| Superseded drawings marked and archived | 100% |
| Monthly Procore audit completed by PM | 100% |

References

- GSL Project Manager Procedures – Documentation Management

- Procore Drawings Tool Guide