SOP 9.4.330 – Develop Schedule Recovery Plans

Department: Project Management / Scheduling
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.325 – Monitor Schedule Performance; 9.41.040 – Compare Estimated vs. Planned Performance; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Scheduling

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To create corrective action plans when project schedules deviate from baseline or milestones are at risk.

Scope

This SOP applies to Project Managers, Superintendents, and Branch Managers.
All recovery schedules and supporting documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Develops recovery plan with input from field. |
| Superintendent | Identifies labor/equipment adjustments needed. |
| Branch Manager | Reviews and approves recovery strategies. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Updated project schedule

- Resource allocation logs

Procedure

- Identify slippage or critical path delays.

- Assess root causes and impacted milestones.

- Propose recovery strategies (overtime, resequencing, added crews).

- Review strategies with project team and Branch Manager.

- Update recovery schedule and file per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Recovery Schedule | Project Manager | Per SOP 190A |
| Corrective Action Plan | PM | Per SOP 190A |
| Approval Notes | Branch Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Recovery plans developed within 5 days of variance detection | 100% |
| Approved recovery strategies implemented | ≥95% |
| Filed and logged per SOP 190A | 100% |

References

- GSL Project Manager Procedures – Scheduling

- SOP 9.41.190A – Document Filing Standards

Appendix

- Recovery Plan Template

- Corrective Action Example