SOP 9.4.335 – Prepare Lookahead Schedules

Department: Project Management / Scheduling
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.320 – Update Project Schedule; 9.41.330 – Develop Schedule Recovery Plans; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Scheduling

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To prepare short-term lookahead schedules that detail upcoming work and resource requirements to guide daily and weekly field activities.

Scope

This SOP applies to Project Managers, Superintendents, and Field Foremen.
All lookahead schedules must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Prepares weekly/monthly lookahead schedules. |
| Superintendent | Verifies field requirements and sequencing. |
| Field Foreman | Uses lookahead schedule to assign crews. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Updated project schedule

- Manpower and material logs

Procedure

- Extract near-term activities from master schedule.

- Break down into weekly/daily tasks.

- Align tasks with manpower and material availability.

- Review with Superintendent and Foreman.

- File lookahead schedules per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Weekly Lookahead Schedule | Project Manager | Per SOP 190A |
| Daily Activity Breakdown | Field Foreman | Per SOP 190A |
| Review Notes | Superintendent | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Lookahead schedules issued weekly | 100% |
| Activities aligned with available resources | ≥95% |
| Records filed and archived | 100% |

References

- GSL Project Manager Procedures – Scheduling

- SOP 9.41.190A – Document Filing Standards

Appendix

- Weekly Lookahead Template

- Daily Task List Example