SOP 9.4.390 – Manage Claims

Department: Project Management / Contract Administration / Legal
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.360 – Manage Change Orders; 9.41.370 – Manage Owner Directives; 9.41.385 – Manage Force Account Work; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Scope & Change Control

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.3.3 Estimating

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To document, prepare, and submit claims for additional time, cost, or damages arising from circumstances outside GSL’s control.

Scope

This SOP applies to Project Managers, Branch Managers, Estimators, and Legal Counsel.
All claim documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Identifies and documents potential claims, prepares claim package. |
| Estimator | Provides cost analysis and backup. |
| Branch Manager | Reviews and approves claims before submission. |
| Legal Counsel | Assists with preparation and negotiation of disputes. |
| Site Administrator | Maintains claim log and files records. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Claim log template

- Contract provisions regarding claims

Procedure

- Identify potential claim circumstances (delays, owner changes, differing site conditions).

- Document details (dates, impacts, supporting evidence).

- Prepare claim package including cost/time analysis.

- Submit claim to Branch Manager for review and approval.

- Submit to owner/GC as required by contract.

- File claim and responses per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Claim Log | Site Administrator | Per SOP 190A |
| Claim Package | Project Manager | Per SOP 190A |
| Approval/Response Records | Branch Manager / PM | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Potential claims documented within 5 days of event | 100% |
| Claim packages prepared per contract deadlines | 100% |
| Owner/GC responses logged and filed | 100% |

References

- GSL Project Manager Procedures – Scope & Change Control

- SOP 9.41.190A – Document Filing Standards

Appendix

- Claim Log Template

- Claim Package Checklist