SOP 9.4.430 – Manage Profit Projections

Department: Project Management / Accounting / Branch Management
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.405 – Manage Cost Forecasts; 9.41.425 – Manage Job Cost Reports; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Cost Management

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.5 Accounting

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To project project-level and portfolio-level profitability by comparing revenue, costs, and forecasts.

Scope

This SOP applies to Project Managers, Accounting, and Branch Managers.
All profit projection documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Prepares project-level profit projection. |
| Accounting | Provides financial data for analysis. |
| Branch Manager | Reviews projections and approves adjustments. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Budget and forecast data

- Profit projection template

Procedure

- Collect updated revenue and cost data.

- Project final profit based on forecasts.

- Compare to baseline profit margin.

- Document reasons for variances.

- File projection reports per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Profit Projection Report | Project Manager | Per SOP 190A |
| Variance Analysis | PM / Accounting | Per SOP 190A |
| Review Notes | Branch Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Projections updated monthly | 100% |
| Variances documented | 100% |
| Reviewed and approved by Branch Manager | 100% |

References

- GSL Project Manager Procedures – Cost Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- Profit Projection Template

- Example Variance Report