SOP 9.4.575 – Manage Subcontractor Resources

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.155 – Conduct Subcontractor Coordination Meetings; 9.41.415 – Manage Committed Costs; 9.41.560 – Manage Manpower Allocation; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Resource Management

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To manage subcontractor manpower, equipment, and material resources to ensure their availability aligns with project requirements and schedules.

Scope

This SOP applies to Project Managers, Field Supervisors, and Subcontractors.
All subcontractor resource documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Coordinates subcontractor resources with schedule. |
| Field Supervisor | Verifies subcontractor manpower and equipment on-site. |
| Subcontractors | Provide accurate forecasts and updates of resource needs. |
| Site Administrator | Logs subcontractor resource updates. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Subcontractor manpower/equipment logs

- Lookahead schedules

Procedure

- Collect subcontractor resource forecasts weekly.

- Compare resources to project manpower and equipment plans.

- Resolve conflicts or shortfalls with subcontractors.

- Track actual subcontractor resources on-site.

- File subcontractor resource documentation per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Subcontractor Resource Log | Site Administrator | Per SOP 190A |
| Weekly Updates | Subcontractors | Per SOP 190A |
| Review Notes | Project Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of subcontractors provide weekly updates | 100% |
| Variances identified and resolved within 2 days | ≥95% |
| Records filed and archived | 100% |

References

- GSL Project Manager Procedures – Resource Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- Subcontractor Resource Log Template

- Weekly Update Form