SOP 9.4.690 – Track Manpower Utilization

Department: Field Operations / Project Management / Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.560 – Manage Manpower Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Field Execution

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To track manpower utilization daily to ensure labor is allocated effectively and productivity targets are met.

Scope

This SOP applies to Project Managers, Field Supervisors, and Site Administrators.
All manpower utilization records must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Field Supervisor | Tracks actual manpower on-site. |
| Project Manager | Reviews utilization vs. plan. |
| Site Administrator | Logs manpower data into project system. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Manpower tracking log

- Daily reports

Procedure

- Record actual manpower by trade and crew daily.

- Compare against manpower allocation plan.

- Identify variances and corrective actions.

- Summarize weekly for PM review.

- File utilization records per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Manpower Tracking Log | Site Administrator | Per SOP 190A |
| Weekly Utilization Summary | Project Manager | Per SOP 190A |
| Variance Reports | Field Supervisor | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of manpower logged daily | 100% |
| Weekly utilization summaries issued | 100% |
| Variances resolved within 3 days | ≥95% |

References

- GSL Project Manager Procedures – Field Execution

- SOP 9.41.190A – Document Filing Standards

Appendix

- Manpower Tracking Log Template

- Weekly Summary Example