SOP 9.4.695 – Track Production Quantities

Department: Field Operations / Project Management
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.400 – Monitor Project Costs; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Field Execution

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To track production quantities of installed work daily to measure productivity and progress against plan.

Scope

This SOP applies to Field Supervisors, Foremen, and Project Managers.
All production tracking records must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Field Supervisor | Records daily quantities of installed work. |
| Foremen | Provide input on production achieved. |
| Project Manager | Compares actual production to plan. |
| Site Administrator | Logs production data in system. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Production tracking log

- Daily reports

Procedure

- Collect daily production quantities from Foremen.

- Record installed work by trade and activity.

- Compare production to schedule and budgeted rates.

- Summarize weekly for PM review.

- File production records per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Production Tracking Log | Field Supervisor | Per SOP 190A |
| Weekly Production Summary | Project Manager | Per SOP 190A |
| Variance Reports | PM / Supervisor | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of production logged daily | 100% |
| Weekly summaries reviewed by PM | 100% |
| Variances documented and acted upon | ≥95% |

References

- GSL Project Manager Procedures – Field Execution

- SOP 9.41.190A – Document Filing Standards

Appendix

- Production Tracking Log Template

- Weekly Summary Example