SOP 9.4.720 – Conduct Productivity Analysis

Department: Project Management / Field Operations / Accounting
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.690 – Track Manpower Utilization; 9.41.695 – Track Production Quantities; 9.41.400 – Monitor Project Costs; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Field Execution

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

- 7.5 Accounting

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To analyze field productivity by comparing actual labor hours and production against planned values, enabling corrective action.

Scope

This SOP applies to Project Managers, Field Supervisors, and Accounting.
All productivity analysis records must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Reviews productivity metrics and initiates corrective action. |
| Field Supervisor | Provides daily production and labor input. |
| Accounting | Supplies actual labor cost data. |
| Site Administrator | Maintains productivity logs. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Productivity analysis log

- Cost and labor reports

Procedure

- Collect daily labor and production data.

- Compare against budgeted hours and planned production.

- Identify variances and root causes.

- Recommend corrective actions to improve performance.

- File analysis results per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Productivity Analysis Log | Site Administrator | Per SOP 190A |
| Weekly Variance Report | Project Manager | Per SOP 190A |
| Corrective Action Notes | PM / Supervisor | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of variances analyzed weekly | 100% |
| Corrective actions implemented within 5 days | ≥95% |
| Reports filed and reviewed monthly | 100% |

References

- GSL Project Manager Procedures – Field Execution

- SOP 9.41.190A – Document Filing Standards

Appendix

- Productivity Analysis Template

- Variance Report Example