SOP: 9.5.550 - Manage Commissioning Activities

Department: Project Management / Quality

Related SOPs:

- 9.5.010 - Conduct Commissioning Meetings

- 9.4.240 - Manage Inspections

- 9.6.020 - Manage Punch Lists

============================================================

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 38: Testing

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.4 Business Administration

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

PURPOSE

============================================================

To establish a standardized process for managing all commissioning activities, ensuring systematic testing, verification, and documentation of electrical systems prior to owner turnover.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Electrical systems require commissioning

- Functional testing is contractually required

- Owner acceptance testing is needed

- Third-party commissioning is specified

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Overall commissioning management; Schedule coordination |

| Field Supervisor (R) | Supports testing; Ensures systems ready; Coordinates corrections |

| Commissioning Agent (R) | Executes testing protocols; Documents results |

| Quality/QA-QC (R) | Verifies compliance; Reviews documentation |

| Subcontractors (R) | Support testing of their systems; Make corrections |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Commissioning plan

- System-specific test protocols

- Pre-functional checklists

- Test equipment (calibrated)

- Manufacturer startup procedures

- Training documentation

============================================================

PROCEDURE

============================================================

STEP 1 - Develop Commissioning Plan

--------------------------------------

PM develops comprehensive plan:

- Identify all systems requiring commissioning

- Establish testing sequence

- Define acceptance criteria

- Schedule testing phases

- Assign responsibilities

- Coordinate with commissioning agent

STEP 2 - Complete Pre-Functional Checklists

--------------------------------------

Before testing begins:

- Verify installation complete

- Check all connections and terminations

- Confirm power available

- Review manufacturer requirements

- Complete pre-functional checklists

- Document any outstanding items

STEP 3 - Conduct Functional Testing

--------------------------------------

Execute testing protocols:

- Follow approved test procedures

- Document all test results

- Identify any deficiencies

- Photograph issues found

- Notify responsible parties

- Track corrections needed

STEP 4 - Manage Deficiencies

--------------------------------------

Handle issues discovered:

- Log in deficiency tracking system

- Assign to responsible party

- Set completion deadlines

- Verify corrections made

- Re-test as required

- Document resolution

STEP 5 - Coordinate Owner Training

--------------------------------------

Arrange system training:

- Schedule training sessions

- Coordinate with equipment vendors

- Prepare training materials

- Document attendance

- Obtain owner sign-off

STEP 6 - Complete Commissioning Documentation

--------------------------------------

Finalize all documentation:

- Compile test reports

- Complete commissioning certificates

- Obtain required signatures

- Submit O&M manuals

- Archive in project files

- Transition to closeout

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| Pre-functional checklists complete | 100% |

| All systems tested per protocol | 100% |

| Deficiencies resolved before turnover | 100% |

| Owner training completed | 100% |

============================================================

APPENDIX

============================================================

- Commissioning Plan Template

- Pre-Functional Checklist

- Test Report Template

- Deficiency Log Template

- Training Sign-off Sheet

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.550 - Manage Commissioning Activities

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee