SOP: 9.6.005 - Prepare for Turnover (Field Perspective)

Department: Field Operations

Related SOPs:

- 9.6.010 - Conduct Closeout Meetings

- 9.6.020 - Manage Punch Lists

- 9.6.030 - Manage As-Built Drawings

============================================================

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 18: Job Close Out

- Tab 22: Document Management

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

- 7.4 Business Administration

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

PURPOSE

============================================================

To establish a standardized process for field personnel to prepare electrical systems and work areas for project turnover, ensuring all field responsibilities are complete before closeout.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Project is approaching substantial completion

- Field demobilization is being planned

- Systems are being prepared for owner acceptance

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Field Supervisor (A) | Leads field turnover preparation; Coordinates with PM |

| Foreman (R) | Executes punch list work; Prepares work areas |

| General Superintendent (C) | Reviews field readiness; Coordinates demobilization |

| Project Manager (C) | Coordinates overall turnover schedule |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Punch list status

- As-built drawing markups

- Equipment/system status

- Cleaning requirements

- Demobilization plan

- Turnover checklist

============================================================

PROCEDURE

============================================================

STEP 1 - Review Outstanding Work

--------------------------------------

FS reviews remaining items:

- Current punch list status

- Incomplete installations

- Outstanding testing/inspections

- Required corrections

- Schedule for completion

STEP 2 - Complete All Installations

--------------------------------------

Ensure all work complete:

- Verify all devices installed

- Check all covers and plates

- Confirm labeling complete

- Verify fire stopping

- Complete any missed items

STEP 3 - Finalize As-Built Markups

--------------------------------------

Complete drawing updates:

- Mark all field changes

- Note routing variations

- Document concealed conditions

- Verify accuracy of markups

- Submit to PM for processing

STEP 4 - Prepare Work Areas

--------------------------------------

Ready areas for turnover:

- Remove all construction debris

- Clean electrical rooms

- Organize panels and equipment

- Remove temporary items

- Touch up finishes as needed

STEP 5 - Support Final Inspections

--------------------------------------

Prepare for final walkthroughs:

- Ensure access to all areas

- Have documentation ready

- Assign escort for inspections

- Address findings immediately

- Document any exceptions

STEP 6 - Coordinate Demobilization

--------------------------------------

Plan field demobilization:

- Identify tools to return

- Plan trailer removal

- Coordinate material returns

- Schedule crew release

- Document lessons learned

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| All punch items addressed | 100% |

| As-built markups submitted | 100% |

| Work areas clean and ready | 100% |

| Demobilization plan complete | 100% |

============================================================

APPENDIX

============================================================

- Field Turnover Checklist

- As-Built Markup Guidelines

- Demobilization Checklist

- Cleaning Standards

============================================================

REVISION HISTORY

============================================================

Formerly: New SOP

Revision: 1.0 | Effective Date: 2025-10-10

Owner: Field Operations | Approver: Executive Committee