SOP: 9.6.010 - Conduct Closeout Meetings

Department: Project Management

Related SOPs:

- 9.6.005 - Prepare for Turnover (Field Perspective)

- 9.6.020 - Manage Punch Lists

- 9.6.060 - Manage Closeout Documentation

============================================================

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 18: Job Close Out

- Tab 22: Document Management

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

PURPOSE

============================================================

To establish a standardized process for conducting project closeout meetings, ensuring proper coordination of all closeout activities and successful project completion.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Project is approaching substantial completion

- Closeout coordination is required

- Final turnover to owner is planned

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Leads closeout meetings; Tracks closeout progress |

| Field Supervisor (R) | Reports field status; Coordinates punch completion |

| Subcontractors (R) | Participate; Complete their closeout requirements |

| Client/Owner (I) | Participates in final acceptance; Approves turnover |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Closeout checklist

- Punch list status

- Submittal/documentation status

- Warranty information

- Training schedule

- Final billing status

============================================================

PROCEDURE

============================================================

STEP 1 - Schedule Closeout Meetings

--------------------------------------

PM schedules meetings:

- Initial closeout planning meeting (30 days before)

- Regular progress meetings

- Final turnover meeting

- Invite all required parties

- Distribute agenda in advance

STEP 2 - Conduct Initial Closeout Meeting

--------------------------------------

Review all closeout requirements:

- Outstanding punch items

- Remaining documentation

- Warranty requirements

- Training needs

- Final inspections

- Billing/retention status

STEP 3 - Track Progress in Regular Meetings

--------------------------------------

Monitor closeout progress:

- Review punch list completion

- Track documentation submittals

- Confirm inspection schedules

- Address any issues

- Update closeout schedule

- Assign action items

STEP 4 - Prepare for Final Turnover

--------------------------------------

Finalize all items:

- Confirm all punch complete

- Verify documentation submitted

- Schedule owner training

- Prepare turnover package

- Resolve any open issues

STEP 5 - Conduct Final Turnover Meeting

--------------------------------------

Complete project turnover:

- Present completed punch list

- Review all documentation

- Obtain owner acceptance

- Transfer warranties

- Discuss warranty service

- Document any exceptions

STEP 6 - Document and Archive

--------------------------------------

Complete meeting documentation:

- Distribute final minutes

- Archive meeting records

- Document lessons learned

- Close out project files

- Transition to warranty phase

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| Closeout meetings held per schedule | 100% |

| All action items tracked | 100% |

| Owner acceptance obtained | 100% |

| Documentation complete | 100% |

============================================================

APPENDIX

============================================================

- Closeout Meeting Agenda Template

- Closeout Checklist

- Final Turnover Package Contents

- Acceptance Sign-off Form

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.555 - Conduct Closeout Meetings

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee