SOP: 9.6.040 - Manage O&M Manuals

Department: Project Management

Related SOPs:

- 9.4.200 - Manage Submittals

- 9.6.050 - Manage Warranties

- 9.6.060 - Manage Closeout Documentation

============================================================

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 18: Job Close Out

- Tab 22: Document Management

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.4.5 Administrative Support

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

PURPOSE

============================================================

To establish a standardized process for compiling and submitting Operation and Maintenance (O&M) manuals, ensuring owners receive complete documentation for facility maintenance.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- O&M manuals are contractually required

- Equipment/system documentation must be provided

- Owner needs maintenance information

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Manages O&M compilation; Submits final manuals |

| Site Administrator (R) | Compiles documentation; Organizes manuals |

| Purchasing (C) | Coordinates vendor documentation |

| Subcontractors (R) | Provide O&M materials for their equipment |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Contract O&M requirements

- Equipment manufacturer data

- Maintenance schedules

- Parts lists

- Warranty information

- Training documentation

============================================================

PROCEDURE

============================================================

STEP 1 - Review O&M Requirements

--------------------------------------

At project start, identify:

- Contract specification requirements

- Number of copies required

- Format requirements (paper/electronic)

- Content requirements by section

- Submission deadlines

- Approval process

STEP 2 - Track Required Documentation

--------------------------------------

Create tracking system:

- List all equipment requiring O&M data

- Identify vendors/manufacturers

- Set collection deadlines

- Track receipt of materials

- Follow up on missing items

STEP 3 - Collect Vendor Documentation

--------------------------------------

Gather O&M materials:

- Request from manufacturers

- Include with submittal requirements

- Collect from subcontractors

- Obtain installation instructions

- Include maintenance schedules

STEP 4 - Compile O&M Manuals

--------------------------------------

Organize documentation:

- Follow specification format

- Organize by division/section

- Include table of contents

- Add project-specific information

- Include as-built conditions

STEP 5 - Submit for Review

--------------------------------------

Submit draft manuals:

- Submit required copies

- Address review comments

- Make corrections/additions

- Resubmit as needed

- Track approval status

STEP 6 - Finalize and Deliver

--------------------------------------

Complete O&M submission:

- Prepare final copies

- Bind per requirements

- Deliver to owner

- Obtain receipt

- Archive copy in project files

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| All vendor documentation collected | 100% |

| O&M format meets specification | 100% |

| Submitted before substantial completion | 100% |

| Owner acceptance obtained | 100% |

============================================================

APPENDIX

============================================================

- O&M Tracking Log Template

- Standard O&M Format Outline

- Vendor Documentation Request Letter

- Submittal Checklist

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.570 - Manage O&M Manuals

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee