SOP 9.6.060 – Manage Closeout Documentation

Department: Project Management / Closeout
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.1
Related SOPs: 9.41.185 – Conduct Closeout Meetings; 9.41.250 – Manage As-Built Drawings; 9.41.255 – Manage O&M Manuals; 9.41.260 – Manage Warranties; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Documentation Management

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 18: Job Close Out

- Tab 22: Document Management

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

Purpose

To compile, review, and submit all required closeout documentation to the client as a condition of final turnover.

Scope

This SOP applies to Project Managers, Field Supervisors, Subcontractors, and Site Administrators.
All closeout documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Oversees closeout documentation process. |
| Site Administrator | Compiles documents per SOP 190A. |
| Subcontractors | Provide required deliverables. |
| Owner/Client | Reviews and accepts final package. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Closeout checklist

Procedure

- Create closeout checklist per contract.

- Collect deliverables from subcontractors/vendors.

- Upload and log documents.

- Verify completeness with PM.

- Transmit final package to owner.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Closeout Checklist | Project Manager | Per SOP 190A |
| Final Documentation Package | PM | Per SOP 190A |
| Owner Acceptance | PM | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Closeout checklist established within 30 days of substantial completion | 100% |
| 100% of required docs uploaded prior to turnover | 100% |
| Owner acceptance documented | 100% |

References

- GSL Project Manager Procedures – Documentation Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- Closeout Checklist Template

- Owner Transmittal Example