SOP: 9.6.070 - Conduct Post-Project Review

Department: Project Management

Related SOPs:

- 9.6.060 - Manage Closeout Documentation

- 9.6.080 - Capture Client Feedback

- 9.6.085 - Document Lessons Learned

============================================================

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 18: Job Close Out

- Tab 22: Document Management

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

PURPOSE

============================================================

To establish a standardized process for conducting post-project reviews, evaluating project performance, and identifying successes and areas for improvement.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Project has reached substantial completion

- Formal project review is warranted

- Performance evaluation is required

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Branch Manager (A) | Oversees review process; Approves action items |

| Project Manager (R) | Leads review meeting; Compiles findings |

| Field Supervisor (R) | Provides field perspective; Shares observations |

| Operations Manager (C) | Reviews operational impacts; Provides input |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Project financial data

- Schedule performance data

- Safety records

- Quality documentation

- Client feedback

- Team availability for meeting

============================================================

PROCEDURE

============================================================

STEP 1 - Schedule Review Meeting

--------------------------------------

Plan post-project review:

- Schedule within 30 days of completion

- Invite all key project participants

- Allow 2-4 hours for comprehensive review

- Select neutral meeting location

- Distribute agenda in advance

STEP 2 - Gather Project Data

--------------------------------------

Compile performance metrics:

- Final budget vs. actual costs

- Schedule performance (planned vs. actual)

- Change order summary

- Safety incident records

- Quality inspection results

- Client feedback received

STEP 3 - Conduct Review Meeting

--------------------------------------

Facilitate structured review:

- Review original project objectives

- Analyze financial performance

- Discuss schedule adherence

- Evaluate safety performance

- Assess quality outcomes

- Review client satisfaction

STEP 4 - Identify Successes

--------------------------------------

Document what went well:

- Effective processes/methods

- Team performance highlights

- Successful problem resolution

- Innovation/improvements made

- Client relationship management

- Cost savings achieved

STEP 5 - Identify Areas for Improvement

--------------------------------------

Discuss challenges openly:

- Budget overruns and causes

- Schedule delays and reasons

- Quality issues encountered

- Communication breakdowns

- Resource constraints

- Process inefficiencies

STEP 6 - Develop Action Items

--------------------------------------

Create improvement plan:

- Assign specific action items

- Designate responsible parties

- Set completion deadlines

- Identify training needs

- Update procedures as needed

- Communicate findings company-wide

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| Post-project review conducted | 100% of projects >$100K |

| Review within 30 days of completion | 100% |

| Action items assigned and tracked | 100% |

| Findings documented and shared | 100% |

============================================================

APPENDIX

============================================================

- Post-Project Review Agenda Template

- Performance Metrics Summary Form

- Action Item Tracking Template

- Review Meeting Minutes Template

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.585 - Conduct Post-Project Review

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee