# SOP: 9.2.010 – Team Selection

Department: Project Management / Operations

## CROSS-REFERENCE SUMMARY

| Related Job Descriptions | Policy 7.3.1 (Project Manager); Policy 7.2.4 (Foreman); Policy 7.2.5 (Project Superintendent); Policy 7.2.6 (Safety Coordinator) |
| --- | --- |
| Management Directives | MD 9.4 (Work Force Development - General Superintendents); MD 9.5 (Field Leadership & Manpower - Project Management) |
| Related Training Modules | Project Structure, Delegation, and Team Development; Chapter 4 Building an Effective Team; Introduction to Field Leadership Section 1 |
| Related SOPs | 9.2.015 - Project Turnover Meeting; 9.2.040 - PM Reviews Plans, Specs & Schedule; 9.2.130 - Construction Execution Kickoff Meeting |

## PURPOSE

To establish a standardized process for selecting and assembling the project team immediately after project award, ensuring the right mix of skills, experience, and availability to meet project requirements.

## SCOPE

Applies to all projects / situations where:

Project has been awarded

Project team needs to be assembled

Resource planning and assignment is required before kickoff

## ROLES & RESPONSIBILITIES

Branch Manager (A)

Selects Project Manager and assigns or approves final team assignments

Allocates resources across projects

Resolves resource conflicts

Project Manager (R)

Identifies required roles and skill sets

Recommends team members

Coordinates with Branch Manager on availability

General Superintendent (C)

Validates field leadership assignments

Confirms crew availability and capability

Safety Coordinator (C)

Ensures safety-qualified personnel are assigned

Reviews site-specific safety requirements

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

## REQUIREMENTS

Award package and project scope

Project schedule and duration

Resource availability matrix

Skills/certification requirements

Project complexity assessment

Historical performance data (similar projects)

## PROCEDURE

### Step 1 – Assess Project Requirements

PM reviews award package and project scope to identify:

Required roles (PM, APM, Foreman, Field Supervisor, Safety, etc.)

Skill requirements (certifications, experience level)

Duration and timing of resource needs

Special requirements (BIM, prefab, commissioning)

### Step 2 – Review Resource Availability

PM coordinates with Branch Manager and GS to:

Review current project commitments

Identify available personnel

Consider geographical and logistical factors

Assess workload balance across projects

### Step 3 – Select Team Members

Based on requirements and availability:

Match skills to project needs

Consider team chemistry and past performance

Ensure appropriate supervision ratios

Address any certification gaps

### Step 4 – Obtain Approval

Branch Manager reviews and approves:

Final team roster

Resource allocation timing

Any cross-project resource sharing

Budget implications of team selection

### Step 5 – Communicate Assignments

PM communicates assignments to:

Selected team members

Supporting departments (Safety, Purchasing, Prefab)

Project Coordinator for administrative setup

Schedule turnover meeting (SOP 9.2.015)

## COMPLIANCE & REVIEW

KPIs:

Team selection complete within 3 days of award - 100%

All required roles identified and filled - 100%

Branch Manager approval obtained - 100%

Team members notified before turnover meeting - 100%

## TRAINING REQUIREMENTS

Personnel performing this SOP must complete the following training:

Project Manager: Project Structure, Delegation, and Team Development (Tab 51)

Project Manager: Chapter 4 Building an Effective Team (Tab 51)

General Superintendent: Introduction to Field Leadership Section 1 (Tab 51)

All: Team Management training per Target Skill Rules

## MANAGEMENT DIRECTIVE ALIGNMENT

This SOP implements the requirements of MD 9.4 (Work Force Development Coordination) which directs General Superintendents to coordinate with Project Management and Field Leadership to assign desired field leadership and employees to projects. It also aligns with MD 9.5 (Field Leadership & Manpower) which requires Project Managers to coordinate with Branch Manager, Branch General Superintendent, and Branch Safety Superintendent to ensure best available field leadership and labor are assigned.

## APPENDIX

Team Selection Checklist

Resource Availability Matrix Template

Skills/Certification Requirements by Role

Project Complexity Assessment Form