# SOP: 9.2.015 – Project Turnover Meeting

Department: Project Management / Estimating / Operations

## CROSS-REFERENCE SUMMARY

| Related Job Descriptions | Policy 7.3.1 (Project Manager); Policy 7.3.3 (Estimator); Policy 7.2.4 (Foreman); Policy 7.2.5 (Project Superintendent) |
| --- | --- |
| Management Directives | MD 9.5 (Project Pre-Planning & Construction Plan Development); MD 9.7 (Project Turnover Meeting) |
| Related Training Modules | Introduction to Field Leadership Section 1; Chapter 0 Introduction to Critical Leadership Training; Introduction to Project Planning and Execution |
| Related SOPs | 9.2.010 - Team Selection; 9.2.040 - PM Reviews Plans, Specs & Schedule; 9.2.050 - FS Reviews Plans, Specs & Schedule; 9.2.130 - Construction Execution Kickoff Meeting |

## PURPOSE

To establish a standardized process for conducting the project turnover meeting between Estimating and Project Management/Field Leadership, ensuring complete transfer of project knowledge, means and methods, and bid assumptions.

## SCOPE

Applies to all projects / situations where:

Project has been awarded and team selected

Turnover from Estimating to Operations is required

Project planning phase is beginning

## ROLES & RESPONSIBILITIES

Project Manager (R)

Schedules and facilitates turnover meeting

Documents turnover items and action items

Ensures all questions are addressed

Estimator/Lead Estimator (R)

Presents bid scope, means and methods

Reviews all exclusions and clarifications

Explains prefabrication assumptions

Discusses major vendors and subcontractors

Field Supervisor (C)

Reviews field installation approach

Identifies potential field issues

Confirms understanding of scope

Branch Manager (A)

Ensures turnover meeting occurs

Resolves any scope or resource issues

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

## REQUIREMENTS

Award package and contract documents

Complete bid documents in estimating folder

Bid proposal with exclusions and clarifications

Project Turnover Meeting Agenda

Project Turnover Checklist

Contract Summary

## PROCEDURE

### Step 1 – Schedule Meeting

PM schedules turnover meeting within 5 days of team selection:

Invite PM, Estimator, Field Supervisor, Branch Manager

Reserve adequate time (typically 2-4 hours)

Prepare meeting agenda

### Step 2 – Review Bid Documents

Estimator presents comprehensive review:

All bid documents identified and numbered

Scope of work and contract documents

All exclusions and clarifications in bid

RFIs submitted and responses received

### Step 3 – Review Means and Methods

Estimator explains installation approach:

Means and methods utilized in take-off

Prefabrication incorporated

Value engineering options

Labor units and assumptions

### Step 4 – Review Major Contracts

Discuss vendors and subcontractors:

Major vendor commitments

Subcontractor scopes

Pricing commitments and expirations

Material lead times

### Step 5 – Review Schedule and Resources

Confirm schedule and manpower:

Construction schedule and interim milestones

GSL field leadership and manpower requirements

Resource loading assumptions

Critical path items

### Step 6 – Document and Distribute

PM documents all turnover items:

Complete Project Turnover Checklist

Document action items with owners

Distribute Contract Summary

Move bid documents to job folder and Plan Grid

## COMPLIANCE & REVIEW

KPIs:

Turnover meeting held within 5 days of team selection - 100%

Project Turnover Checklist completed - 100%

All exclusions/clarifications documented - 100%

Bid documents transferred to Plan Grid - 100%

## TRAINING REQUIREMENTS

Personnel performing this SOP must complete the following training:

Project Manager: Introduction to Project Planning and Execution (Tab 2)

Estimator: MD 9.7 Estimating Directives training

Field Supervisor: Introduction to Field Leadership Section 1 (Tab 51)

All: Chapter 0 Introduction to Critical Leadership Training

## MANAGEMENT DIRECTIVE ALIGNMENT

This SOP implements MD 9.5 (Project Pre-Planning) which requires Project Turnover Meetings where Contract Manager, Branch Manager, Project Manager, and Field Leadership meet with Estimators. It also implements MD 9.7 (Project Turnover Meeting) which requires Estimating Department participation following the Turn-Over Meeting Agenda, including thorough review of means and methods, exclusions, prefabrication, value engineering, vendors, subcontractors, schedule, and Contract Summary.

## APPENDIX

Project Turnover Meeting Agenda

Project Turnover Checklist

Contract Summary Template

Bid Document Log Template