# SOP: 9.41.675 – Conduct Daily Huddles

Department: Field Operations

## CROSS-REFERENCE SUMMARY

| Related Job Descriptions | Policy 7.2.4 (Foreman); Policy 7.2.3 (Lead Journeyman); Policy 7.2.5 (Project Superintendent) |
| --- | --- |
| Management Directives | MD 9.3 (Execution of the Plan - Field Leadership) |
| Related Training Modules | Techniques for Better Communication and Feedback; Chapter 8 Introduction to Effective Communication; Leadership Essentials; Building and Maintaining Team Morale |
| Related SOPs | 9.41.680 - Conduct Weekly Foreman Meetings; 9.41.215 - Manage Daily Reports; 9.41.485 - Conduct Safety Meetings |

## PURPOSE

To establish a standardized process for conducting daily crew huddles to communicate work assignments, safety reminders, coordinate activities, and ensure all crew members understand daily objectives.

## SCOPE

Applies to all projects / situations where:

Start of each work shift

After lunch breaks as needed

When work conditions or plans change significantly

## ROLES & RESPONSIBILITIES

Foreman (R)

Conducts daily huddle

Communicates work assignments

Reviews safety topics

Addresses crew questions

Lead Journeyman (C)

Assists with huddle coordination

Provides input on crew assignments

Supports Foreman communication

Project Superintendent (A)

Ensures huddles occur

Provides project-level updates

Addresses escalated issues

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

## REQUIREMENTS

Daily work plan and assignments

Safety topic for the day

Coordination needs with other trades

Material and tool availability status

Schedule milestones and priorities

## PROCEDURE

### Step 1 – Prepare for Huddle

Foreman prepares before crew arrival:

Review daily work plan from Job Plan

Identify safety topic (JHA items)

Note coordination requirements

Identify material/tool needs

### Step 2 – Conduct Huddle

At shift start, gather crew and cover:

Safety moment or JHA review

Daily work assignments by crew member

Production targets and quality reminders

Coordination with other trades

Material staging and tool locations

Questions and concerns

### Step 3 – Monitor and Adjust

Throughout the day:

Monitor progress against plan

Address issues as they arise

Conduct brief afternoon huddle if needed

Note productivity and quantities

### Step 4 – Document

Record daily activities:

Complete timecard with hours by cost code

Record installed quantities

Note any delays or impacts

Prepare for next day huddle

## COMPLIANCE & REVIEW

KPIs:

Daily huddle conducted - 100%

Safety topic covered - 100%

All crew members present at huddle - 95%

Work assignments communicated clearly - 100%

## TRAINING REQUIREMENTS

Personnel performing this SOP must complete the following training:

Foreman: Leadership Essentials (Tab 51)

Foreman: Techniques for Better Communication and Feedback (Tab 51)

Foreman: Chapter 8 Introduction to Effective Communication (Tab 51)

Lead Journeyman: Building and Maintaining Team Morale (Tab 51)

## MANAGEMENT DIRECTIVE ALIGNMENT

This SOP implements MD 9.3 (Execution of the Plan) which requires Field Leadership to layout daily work activities for crews, monitor progress during work shift, and report quantities for crews at end of shift. It ensures Foremen and Lead Men are accountable for crew productivity and direct all electricians to operate efficiently.

## APPENDIX

Daily Huddle Checklist

Safety Topic Calendar

Work Assignment Template

Coordination Log