# SOP: 9.6.070 – Conduct Post-Project Review

Department: Project Management / Operations

## CROSS-REFERENCE SUMMARY

| Related Job Descriptions | Policy 7.3.1 (Project Manager); Policy 7.2.4 (Foreman); Policy 7.2.5 (Project Superintendent); Policy 7.3.3 (Estimator) |
| --- | --- |
| Management Directives | MD 9.5 (Project Closeout - Required Documents) |
| Related Training Modules | Continuous Improvement; Leadership Essentials; Chapter 15 Continuous Improvement |
| Related SOPs | 9.6.085 - Document Lessons Learned; 9.6.080 - Capture Client Feedback; 9.6.010 - Conduct Closeout Meetings |

## PURPOSE

To establish a standardized process for conducting comprehensive post-project reviews to capture lessons learned, evaluate project performance, and drive continuous improvement across the organization.

## SCOPE

Applies to all projects / situations where:

Project substantial completion achieved

Final billing submitted

All closeout documentation complete

## ROLES & RESPONSIBILITIES

Project Manager (R)

Schedules and facilitates review

Prepares performance data

Documents lessons learned

Branch Manager (A)

Ensures reviews occur

Reviews performance results

Implements improvement actions

Field Supervisor/Foreman (C)

Provides field perspective

Identifies what worked well

Suggests improvements

Estimator (C)

Compares bid to actual

Provides estimating insights

Updates labor units database

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

## REQUIREMENTS

Final job cost report

Original estimate vs actual comparison

Schedule performance data

Safety record summary

Quality metrics

Client feedback (SOP 9.6.080)

## PROCEDURE

### Step 1 – Schedule Review Meeting

PM schedules within 30 days of substantial completion:

Invite key project team members

Include Estimating representative

Reserve adequate time (1-2 hours)

Gather performance data

### Step 2 – Review Project Performance

Analyze key metrics:

Budget vs actual (labor, material, equipment)

Schedule performance (milestones, completion)

Safety record (incidents, near misses)

Quality metrics (rework, punch list)

Client satisfaction

### Step 3 – Identify Lessons Learned

Discuss what worked and what to improve:

Pre-construction planning effectiveness

Execution challenges and solutions

Coordination and communication

Estimating accuracy

Field productivity

### Step 4 – Document and Distribute

Capture and share lessons learned:

Complete Lessons Learned form (SOP 9.6.085)

Update estimating database if applicable

Distribute to Branch Management

Share relevant lessons with organization

### Step 5 – Implement Improvements

Take action on findings:

Assign action items for process improvements

Update SOPs if needed

Incorporate into future project planning

Recognize team successes

## COMPLIANCE & REVIEW

KPIs:

Post-project review conducted within 30 days - 100%

Lessons learned documented - 100%

Action items assigned with owners - 100%

Results shared with organization - 100%

## TRAINING REQUIREMENTS

Personnel performing this SOP must complete the following training:

Project Manager: Continuous Improvement (Tab 56)

Project Manager: Chapter 15 Continuous Improvement (Tab 56)

All: Leadership Essentials (Tab 51)

## MANAGEMENT DIRECTIVE ALIGNMENT

This SOP implements MD 9.5 (Project Closeout - Required Documents) which lists Field Leadership Interviews and Employee Evaluations as required closeout items. The post-project review process supports continuous improvement aligned with Lean Construction principles and helps improve future project performance.

## APPENDIX

Post-Project Review Agenda

Performance Metrics Summary Template

Lessons Learned Form

Estimating Feedback Form