# Policy Manual 9.3

## Management Directives for Field Leadership

## CROSS-REFERENCE SUMMARY

| Target Audience | Project Foremen and Project Superintendents |
| --- | --- |
| Related Job Descriptions | Policy 7.2.4 (Foreman); Policy 7.2.5 (Project Superintendent) |
| Implementing SOPs | 9.2.050 Plans Review; 9.41.xxx Field Operations SOPs; 9.41.215 Daily Reports; 9.41.675-680 Huddles and Meetings |
| Required Training | Introduction to Field Leadership (all sections); Foreman Role & Responsibilities; Job Plan Setup; Lean Construction; Performance Management |

## PURPOSE

To establish expectations and requirements for GSL Field Leadership regarding project execution, crew management, productivity, reporting, and compliance.

## SCOPE

Applies to all Project Foremen and Project Superintendents responsible for leading field crews on GSL projects.

## KEY DIRECTIVES

### Objectives

Deliver projects on-time and within budget

Achieve contractual quality requirements

Meet regulatory safety requirements

### Attitude & Self-Discipline

Demonstrate positive attitude about company, projects, clients, people, and work

Show self-discipline to refrain from negative behaviors impacting morale

Be ambassadors of good will for GSL

Address concerns through proper channels (Project Superintendent/Project Manager)

### Pre-Planning

All projects must be pre-planned with Project Manager

Plan from start to finish

Changes to plan handled more efficiently than on-the-fly planning

### Execution of the Plan

Layout daily work activities for crews

Monitor progress during work shift

Report quantities for crews at end of shift

If daily objectives not met, review issues and take corrective action

Ensure labor, materials, tools, equipment available

Quantities installed reported and entered in Job Plan

### Productivity

Foremen and Lead Men accountable for crew productivity

Direct all electricians to operate efficiently

Wear tool belts and bags for anticipated work

Proper material staging critical

Report significant labor, material, equipment overage immediately to PM

Focus on quality control and minimize mistakes/rework

### Reporting

Complete employee timecards daily

Record time worked to appropriate work codes

Foreman timecards completed daily with hours and crew's installed quantities

Accuracy in reporting time and quantity paramount

### Changed Work

Never perform significant changed work without PM consultation and authorization

Report concerns about change order delays to PM

Never assume field changes are clarifications of base bid scope

Only proceed with changed work when authorized by PM

### Daily Reports

Submit Daily Reports with schedule slippage, impacts, productivity impacts

Document work outside contract scope

Information flows to PM for Weekly Project Status Reports

Information is time-sensitive and critical for notice compliance

## IMPLEMENTING STANDARD OPERATING PROCEDURES

The following SOPs implement the requirements of this Management Directive:

SOP 9.2.050 - FS Reviews Plans, Specifications & Schedule

SOP 9.41.675 - Conduct Daily Huddles

SOP 9.41.680 - Conduct Weekly Foreman Meetings

SOP 9.41.690 - Track Manpower Utilization

SOP 9.41.695 - Track Production Quantities

SOP 9.41.215 - Manage Daily Reports

SOP 9.41.720 - Conduct Productivity Analysis

SOP 9.41.470-510 - Safety Management SOPs

All Site Setup SOPs (9.3.xxx)

## TRAINING REQUIREMENTS

Personnel subject to this directive must complete:

Introduction to Field Leadership Section 1 (Tab 51) - First 90 days

Foreman Role & Responsibilities (Tab 51) - First 90 days

Job Plan Setup and Maintenance (Tab 7) - First 6 months

Leadership Essentials (Tab 51) - First 6 months

Lean Construction Fundamentals (Tab 56) - First year

Effective Communication (Tab 51) - First year

Safety Coordinator Certification (Tab 40) - Required for Foreman

## JOB DESCRIPTION ALIGNMENT

This directive applies to positions defined in Policy Manual 7.2.4 (Foreman) and 7.2.5 (Project Superintendent). These job descriptions include compliance with MD 9.3 requirements as an essential duty.

## COMPLIANCE AND ENFORCEMENT

Compliance is mandatory. Job Cost Review must occur at least monthly with Project Manager. Daily reports must be submitted timely. Failure to provide required notice and documentation can have severe financial impact on GSL.

## ACKNOWLEDGEMENT

Field Leadership must acknowledge receipt and understanding of these directives. General Superintendents are responsible for reviewing and obtaining acknowledgements.