PRE-CONSTRUCTION PLANNING

TABLES:

Table 1: Team Selection and Turnover Checklist

Table 2: Scope and Contract Review Checklist

Table 3: Administrative Setup Checklist

Table 4: Buyout Process Checklist

Table 5: Material Handling Planning Process Checklist

Table 6: Budget Preparation Checklist

Table 7: Layout and Sequencing Planning Checklist

Table 8: Schedule Development Planning Checklist

Table 9: Tracking and Control Planning Checklist

Table 10: Construction Execution Kickoff Meeting Checklist

FIGURES:

Figure 1: Standard Change Order Process

Figure 2: Change Order Proposal

Figure 3: Field Change Form

Figure 4: Standard Request for Information Procedure

Figure 5: Request for Information Form

Figure 6: Standard Submittal Procedures

Figure 7: Submittal Transmittal Form

Figure 8: Requirements and Expectations Letter

Figure 9: Letter of Intent

Figure 10: Purchase Order Form

Figure 11: Standard Billing Procedure

Figure 12: Standard Progress Update Procedure

Table 1: Team Selection and Turnover Checklist

| Project Number: ______________________________________________________________________ Project Name: ________________________________________________________________________ Location: ____________________________________________________________________________ Estimator: ___________________________________________________________________________ Project Manager: ______________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| TEAM SELECTION AND TURNOVER CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 1. Finalize selection of project manager, field supervisor, and other key team members |  |  |  |
|  |  | 1 | Assemble a list of project managers and review their current work load and special skills |
|  |  | 2 | Determine whether an ideal match can be made between the project manager and the job, and then select the project manager |
|  |  | 3 | Assemble a list of field supervisors and review their current work load and special skills |
|  |  | 4 | Determine whether an ideal match can be made between the field supervisor and the job, and then select the field supervisor |
|  |  | 5 | Work with the project manager, field supervisor, and/or the director of operations to select key foremen when appropriate |
| 2. Hold turnover meeting between estimator and project manager |  |  |  |
|  |  | 1 | Arrange a meeting time and location, and ensure that enough time has been allocated to transfer knowledge between the estimator and project manager |
|  |  | 2 | Follow, and complete, a checklist that describes the information that should be transferred |
| 3. Hold separate turnover meeting between project manager and field supervisor |  |  |  |
|  |  | 1 | Arrange a meeting time and location that will ensure enough time to transfer knowledge between the project manager and field supervisor |
|  |  | 2 | Follow, and complete, a checklist that describes the information that must be transferred (see Figure 1.5 in the book) |
| 4. Hold pre-job (planning) kickoff meeting with internal team members to assign responsibilities |  |  |  |
|  |  | 1 | Arrange a meeting time and location, and ensure that enough time has been allocated to assign planning responsibilities |
|  |  | 2 | Invite internal team members that will be involved during the construction execution process, such as project manager, field supervisor, accounting, purchasing, director of field operations, etc. |
|  |  | 3 | Complete a checklist that describes the planning activities that must be completed and who is responsible for completion (see Figure 1.6 in the book) |

Table 2: Scope and Contract Review Checklist

| Project Number: _______________________________________________________________________ Project Name: ________________________________________________________________________ Location: ____________________________________________________________________________ Estimator: ____________________________________________________________________________ Bid Due Date: _________________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| SCOPE AND CONTRACT REVIEW CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 5. Review contract for unfavorable or high risk clauses |  |  |  |
|  |  | 1 | Complete the Contract Review checklist (see Figure 1.7 in the book) |
|  |  | 2 | Identify all required bonds, permits and certificates |
|  |  | 3 | Review contractual billing requirements |
|  |  | 4 | Review and understand procedures for requesting change orders |
|  |  | 5 | Identify whether disputes must be resolved through alternative dispute resolution (ADR), such as mediation or arbitration |
| 6. Project manager reviews plans, specifications, and schedule |  |  |  |
|  |  | 1 | Order extra sets of plans and specifications, if necessary |
|  |  | 2 | Complete the Scope and Schedule Review checklist (see Figure 1.8 in the book) |
|  |  | 3 | Compare the scope identified in the contract to the scope from the bid submission to verify that they match |
|  |  | 4 | Compare the plans to the specifications to identify any discrepancies |
|  |  | 5 | Review the schedule provided by the general contractor to determine whether your work can be completed within the contractual timeframe. |
| 7. Field supervisor reviews plans, specifications, and schedule |  |  |  |
|  |  | 1 | Complete the Scope and Schedule Review checklist (see Figure 1.8 in the book) |
|  |  | 2 | Review Best Field Practices or Lessons Learned |
|  |  | 3 | Identify value engineering or prefabrication opportunities (see Activity 11) |
|  |  | 4 | Identify labor requirements and begin selecting foreman |
|  |  | 5 | Identify special tools that will need to be purchased or assembled |
| 8. Create a list of issues that need to be resolved and begin the request for information (RFI) process |  |  |  |
|  |  | 1 | Establish a request for information (RFI) process (see Activity 16) and create a list of questions that require clarification |

Table 2: Scope and Contract Review Checklist (continued)

| Project Number: _____________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
|  |  | 2 | Formalize the RFIs by assigning them a trackable number and submitting them to the owner/CM/GC |
| 9. Conduct site visit |  |  |  |
|  |  | 1 | Complete the Site Visit Checklist (see Figure 1.9 in the book) |
|  |  | 2 | Examine site access and layout, including parking, material delivery points, and material lay-down and storage |
|  |  | 3 | Identify locations and availability of material and personnel lifts, elevators, cranes, scaffolding, and forklifts |
|  |  | 4 | Create a plan for installing temporary power |
|  |  | 5 | Verify existing conditions and compare them to the conditions shown on the plans and described in the specifications |
| 10. Compare estimated (bid) work activities and materials to planned performance |  |  |  |
|  |  | 1 | Compare the estimator’s concept of how to perform the work to typical field operations and document the differences |
|  |  | 2 | Discuss unclear methods or discrepancies with the estimator |
|  |  | 3 | Determine the cost difference between the as-bid and planned performance of the work |
| 11. Identify value engineering and prefabrication opportunities and how to simplify the work |  |  |  |
|  |  | 1 | Review value engineering (VE) or prefabrication opportunities that were identified in the turnover meeting between the estimator and project manager |
|  |  | 2 | Review procedures for formally requesting VE consideration, if required |
|  |  | 3 | Search for, and identify, additional VE and prefabrication items |
|  |  | 4 | Identify additional ways to simplify the work |
|  |  | 5 | Price out the cost difference between the as-bid and VE options |
| 12. Prepare construction takeoff |  |  |  |
|  |  | 1 | Take off the materials, equipment, and systems in the order they will be constructed. |
|  |  | 2 | Code each plan sheet as you take it off so that you can return to it later and immediately identify the quantity of various materials shown on the sheet. |
|  |  | 3 | The final quantities should be identified by the units in which they will be purchased. |
|  |  | 4 | All assumptions should be noted on the quantity takeoff sheets. |
|  |  | 5 | Be sure the quantities that are estimated include a waste factor. |
|  |  | 6 | Compare the construction takeoff to the bid takeoff to identify significant differences or discrepancies |

Table 3: Administrative Setup Checklist

| Project Number: ______________________________________________________________________ Project Name: _______________________________________________________________________ Location: ___________________________________________________________________________ Project Manager: _____________________________________________________________________ Start Date: __________________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| ADMINISTRATIVE SETUP CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 13. Set up project files and create contact list |  |  |  |
|  |  | 1 | Use the File System checklist (see Figure 1.10 in the book) to create paper files |
|  |  | 2 | Create a contact sheet that lists all team members and their company contact information |
| 14. Set up computerized tracking and control system (forms, database, schedule, tracking) |  |  |  |
|  |  | 1 | Verify that the accounting department has assigned a project number and entered initial information in the cost control system |
|  |  | 2 | Use the File System checklist (see Figure 1.10 in the book) to create computer files |
|  |  | 3 | If a separate project management software system is used, set up the project in the system |
|  |  | 4 | If a separate computer scheduling system is used, set up the schedule in the system (see Activity 37) |
| 15. Initiate a change management system |  |  |  |
|  |  | 1 | Review the contract to identify required change order, field change, and time-and-materials procedures |
|  |  | 2 | Review your company’s standard procedures for initiating, requesting, and processing change orders and field changes |
|  |  | 3 | Develop a log, with sequential numbering, to track all changes, including change orders, field changes, and time-and-materials requests (see Figure 1.11 in the book) |
| 16. Initiate a request for information (RFI) tracking and processing system |  |  |  |
|  |  | 1 | Develop a log, with sequential numbering, to track all requests for information (RFIs) (see Figure 1.12 in the book) |
|  |  | 2 | Determine whether RFIs will be submitted by e-mail, fax, or postal mail |
|  |  | 3 | Review your company’s standard procedures for processing RFIs and use a company standard form for submitting RFIs |
|  |  | 4 | Ensure each RFI also identifies a proposed solution and price change |

Table 3: Administrative Setup Checklist (continued)

| Project Number: _____________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| 17. Initiate a submittal tracking and processing system |  |  |  |
|  |  | 1 | Develop a log, with sequential numbering, to track all submittals, including those of vendors and subcontractors (see Figure 1.13 in the book) |
|  |  | 2 | Review your company’s standard procedures for processing submittals and use a company standard form for submissions |
|  |  | 3 | Verify that each submittal processing form identifies a response date, which is associated with timely ordering and delivery of the materials and equipment |
| 18. Develop a Labor Requirements/Expectation letter |  |  |  |
|  |  | 1 | For projects that have special requirements, such as drug testing, background check, or special safety training, develop an expectations letter that must be reviewed and signed by crew members (see Figure 8 in this document) |
|  |  | 2 | For projects that will require hiring workers from the union hall, develop an expectations letter that must be reviewed and signed by crew members |

Table 4: Buyout Process Checklist

| Project Number: ______________________________________________________________________ Project Name: ________________________________________________________________________ Location: ____________________________________________________________________________ Project Manager: ______________________________________________________________________ Start Date: ___________________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| BUYOUT PROCESS CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 19. Request and/or review subcontractor/supplier/vendor prices and qualifications |  |  |  |
|  |  | 1 | Request subcontractor/supplier/vendor pricing if it was not requested or received during the bidding stage |
|  |  | 2 | Compare actual subcontractor/supplier/vendor scope of work with the scope identified in the subcontractor/supplier/vendor bid submission |
|  |  | 3 | Evaluate the subcontractor/supplier/vendor qualifications |
|  |  | 4 | Compare pricing and qualifications among the subcontractors/ suppliers/vendors |
| 20. Negotiate pricing and contract conditions and select subcontractors/suppliers/vendors |  |  |  |
|  |  | 1 | Discuss possible cost savings with potential subcontractors/suppliers/vendors |
|  |  | 2 | Review the contract or purchase order terms and conditions with potential subcontractors/suppliers/vendors prior to award |
|  |  | 3 | Select all successful subcontractors/suppliers/vendors and issue a letter of intent |
| 21. Develop and issue purchase orders and contracts for materials and equipment |  |  |  |
|  |  | 1 | Develop the purchase orders or contracts for subcontractors/suppliers/ vendors |
|  |  | 2 | Process and issue the purchase orders or subcontracts |
| 22. Order long-lead-time materials and equipment |  |  |  |
|  |  | 1 | Compare the sequence, schedule, and materials/equipment to identify long-lead-time items |
|  |  | 2 | Negotiate and issue purchase orders and subcontracts for long-lead-time items before negotiating standard purchase orders and subcontracts |
|  |  | 3 | Issue a letter of intent or purchase order immediately to release long-lead-time items for order and delivery |

Table 4: Buyout Process Checklist (continued)

| Project Number: _____________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| 23. Request submittals, cut sheets, and shop drawings |  |  |  |
|  |  | 1 | Upon issuing the contract document, the subcontractor/supplier/ vendor should be requested to assemble and submit samples, cut sheets, or shop drawings |
|  |  | 2 | Identify a deadline by which the submittals, cut sheets, and shop drawings must be submitted to your company |
| 24. Develop and process log and book of submittals, cut sheets, and shop drawings |  |  |  |
|  |  | 1 | Develop a log, with sequential numbering, to track all submittals, including those of vendors and subcontractors (see Activity 17 and Figure 1.13 in the book) |
|  |  | 2 | Assemble two or more binders of all draft and approved submittals |
|  |  | 3 | Submit and track required submittal items |

Table 5: Material Handling Planning Process Checklist

| Project Number: ______________________________________________________________________ Project Name: ________________________________________________________________________ Location: ____________________________________________________________________________ Project Manager: ______________________________________________________________________ Start Date: ___________________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| MATERIAL HANDLING PROCESS CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 25. Develop material delivery and handling plan |  |  |  |
|  |  | 1 | Review the material delivery/storage and site logistics best practices (see Activity 25 in the book) |
|  |  | 2 | Establish and maintain a file of delivery receipts and packing slips |
|  |  | 3 | Establish a Material and Equipment Delivery and Storage Log |
|  |  | 4 | Create a material and equipment delivery schedule |
|  |  | 5 | Establish standard procedures for receiving, handling, and storage of materials and equipment |
| 26. Develop material storage and staging plan |  |  |  |
|  |  | 1 | Complete the site logistics review checklist (see Figure 1.16 in the book) |
|  |  | 2 | Review the material delivery/storage and site logistics best practices (see Activity 25 in the book) |
|  |  | 3 | Develop a storage site layout that identifies where the materials and equipment are stored |

Table 6: Budget Preparation Checklist

| Project Number: ______________________________________________________________________ Project Name: ________________________________________________________________________ Location: ____________________________________________________________________________ Project Manager: ______________________________________________________________________ Start Date: ___________________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| BUDGET PREPARATION CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 27. Develop, review, or expand the cost code scheme |  |  |  |
|  |  | 1 | Decide whether to use a cost code scheme based upon the Construction Specifications Institute (CSI) MasterFormat |
|  |  | 2 | Review the cost estimate to identify the existing cost code breakdown, and decide whether additional breakdown is necessary |
|  |  | 3 | Review the company standard list of cost codes or use the CSI MasterFormat and decide which codes will be needed for breaking down the work for tracking and billing |
|  |  | 4 | Add new codes for work items that are not on the standard list |
|  |  | 5 | Assign additional codes to specify the costs associated with material, equipment, labor, subcontractors, and other miscellaneous costs |
| 28. Develop budget by breaking down labor, material, overhead, and profit costs |  |  |  |
|  |  | 1 | Create the budget in concert with the labor and materials tracking report |
|  |  | 2 | Establish a budget with sufficient line items to identify potential problems yet simple enough to avoid time-consuming data entry |
|  |  | 3 | Verify that labor and materials can, and will, be reported according to the budget line items |
| 29. Develop schedule of values |  |  |  |
|  |  | 1 | Review the contract to identify the contractual format and process for developing a schedule of values |
|  |  | 2 | Create the schedule of values in concert with the billing process |
|  |  | 3 | Consider rolling up the budget, so that the schedule of values has the same summary line items but fewer sub-line items |

Table 7: Layout and Sequencing Planning Checklist

| Project Number: ______________________________________________________________________ Project Name: ________________________________________________________________________ Location: ____________________________________________________________________________ Project Manager: ______________________________________________________________________ Start Date: ___________________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| LAYOUT AND SEQUENCING CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 30. Develop installation sequence and layout drawings |  |  |  |
|  |  | 1 | Organize the project by areas, by floors, or by systems |
|  |  | 2 | Allocate sufficient time to mentally think through the sequencing of all work processes from start through completion |
|  |  | 3 | Determine whether to create sequence and layout drawings by hand (marked-up drawings) or by creating new CAD drawings |
|  |  | 4 | Create daily installation drawings at least one day prior to the date when the work needs to be performed so that the drawings can be distributed each morning to foremen and field crews |
|  |  | 5 | Review the sequence daily or weekly to ensure the project is progressing as expected |
| 31. Develop field instructions |  |  |  |
|  |  | 1 | Review the sequence and installation process to identify any additional information that might minimize questions and improve productivity |
|  |  | 2 | Develop field instructions and drawings for repetitive work, when repetitive work is scheduled on a project |
| 32. Develop prefabrication drawings for field use |  |  |  |
|  |  | 1 | For systems that are partially or completely prefabricated in a prefabrication shop, develop drawings that show how the prefabricated parts should be assembled and installed in the field |
|  |  | 2 | For systems prefabricated in a shop, ensure the prefabricated parts are clearly labeled and that these labels correspond to an assembly and installation scheme identified on the drawings |
|  |  | 3 | If on-site prefabrication is scheduled, the drawings should identify the step-by-step process of how each piece is assembled into the prefabricated system |

Table 7: Layout and Sequencing Planning Checklist (continued)

| Project Number: ______________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| LAYOUT AND SEQUENCING CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
|  |  | 4 | If off-site prefabrication is scheduled, separate drawings should also be created to identify how the prefabricated parts should be installed |
|  |  | 5 | Distribute the prefabrication drawings to the foremen or field crews that will perform the work |

Table 8: Schedule Development Planning Checklist

| Project Number: ______________________________________________________________________ Project Name: ________________________________________________________________________ Location: ____________________________________________________________________________ Project Manager: ______________________________________________________________________ Start Date: ___________________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| SCHEDULE DEVELOPMENT CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 33. Review general contractor’s schedule and timeline |  |  |  |
|  |  | 1 | Complete the General Contractor’s Schedule Review Items checklist (see Figure 1.19 in the book) |
|  |  | 2 | Initiate or attend a customer schedule review meeting to identify any special requirements and clarify any questions |
| 34. Identify work that impacts your activities |  |  |  |
|  |  | 1 | While reviewing the overall construction schedule, annotate work that must be coordinated with other trades |
|  |  | 2 | While reviewing the overall construction schedule, annotate potential conflicts that will require coordination |
|  |  | 3 | Develop and submit RFIs to resolve open questions or conflicts among systems |
|  |  | 4 | Request an initial (and a recurring) Coordination Meeting to identify and resolve schedule questions and conflicts before installation begins |
| 35. Review the work sequence and long-lead-time material/equipment delivery dates |  |  |  |
|  |  | 1 | Develop a rough draft of your schedule from the sequence and installation plan (See Activity 35 in the book) |
|  |  | 2 | Verify the ordering and delivery dates of long-lead-time materials and equipment |
|  |  | 3 | Perform a three-way coordination between the sequencing/installation plan, material/equipment delivery plan, and the draft schedule |
|  |  | 4 | Modify the draft schedule and sequencing/installation plan to accommodate long-lead-time deliveries |
| 36. Coordinate your schedule with the schedule of the general contractor |  |  |  |
|  |  | 1 | After coordinating the sequencing/installation plan, material/equip-ment delivery plan, and the draft schedule, coordinate the draft schedule with the general contractor’s schedule and adjust as necessary |

Table 8: Schedule Development Planning Checklist (continued)

| Project Number: ______________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| SCHEDULE DEVELOPMENT CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
|  | COMPLETION DATE | ITEM NO. | ACTIVITY |
|  |  | 2 | Review your final schedule with the customer, general contractor, other trade contractors, and suppliers to resolve any final conflicts |
|  |  | 3 | Seek approval of the schedule from the customer and general contractor |
|  |  | 4 | Seek integration of your schedule into the general contractor’s overall project schedule |
| 37. Create bar chart schedule |  |  |  |
|  |  | 1 | In addition to the integration of your schedule into the overall schedule, format your final schedule into an independent bar chart for tracking and control |
|  |  | 2 | Select the type of bar chart to develop and track |
|  |  | 3 | Save the original approved schedule as the baseline so that progress can be tracked and delays can be documented |
|  |  | 4 | Distribute your bar chart schedule to the customer, general contractor, various subcontractors, and suppliers |

Table 9: Tracking and Control Planning Checklist

| Project Number: ______________________________________________________________________ Project Name: ________________________________________________________________________ Location: ____________________________________________________________________________ Project Manager: ______________________________________________________________________ Start Date: ___________________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| TRACKING AND CONTROL CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 38. Customize the computerized tracking and control system (database/ schedule/etc.) for the current project |  |  |  |
|  |  | 1 | Review the tracking and control best practices (see Activity 38 in the book) |
|  |  | 2 | Complete the Tracking and Control Tools Checklist (see Figure 1.20 in the book) |
|  |  | 3 | Select computerized tracking and control tools for the project |
|  |  | 4 | Modify the tracking and control tools for the current project |
| 39. Develop labor and materials tracking report |  |  |  |
|  |  | 1 | Review the cost estimate and associated budget and cost code scheme |
|  |  | 2 | Match the cost estimate/budget work items to crew assignments so that labor and materials can be tracked easily |
|  |  | 3 | Select the reports to be created and used for monitoring progress |
|  |  | 4 | Develop the selected reports by inputting project data into the reporting system (database or accounting system) |

Table 10: Construction Execution Kickoff Meeting Checklist

| Project Number: ______________________________________________________________________ Project Name: ________________________________________________________________________ Location: ____________________________________________________________________________ Project Manager: ______________________________________________________________________ Start Date: ___________________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| CONSTRUCTION EXECUTION KICKOFF CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
| ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES |
| 40. Review meeting schedule |  |  |  |
|  |  | 1 | Review the schedule of weekly internal meetings associated with the project |
|  |  | 2 | Review the schedule of weekly project meetings conducted by the customer or general contractor |
|  |  | 3 | Identify the internal team members that will be responsible for attending the internal and external meetings |
| 41. Review request for information (RFI) process |  |  |  |
|  |  | 1 | Review the contract for a customer-mandated request for information (RFI) process |
|  |  | 2 | Review the company standard procedure for developing, processing, tracking, and closing out a request for information |
|  |  | 3 | Modify the company standard RFI procedure, as necessary, to conform to the contractually-mandated process |
| 42. Review change order process and field change management process |  |  |  |
|  |  | 1 | Review the contract for a customer-mandated change order (CO) process and field change request process |
|  |  | 2 | Review the company standard change order procedure and field change request/management process |
|  |  | 3 | Discuss the process for documenting changes, delays, and disruptions in the work flow and sequence |
|  |  | 4 | Discuss the process for tracking and following up on change order requests and payment for field change directives |
| 43. Review submittal processing procedures |  |  |  |
|  |  | 1 | Review the contract documents for a customer-mandated submittal processing procedures |
|  |  | 2 | Review the company standard procedure for developing, processing, tracking, and receiving approval for project submittals |

Table 10: Construction Execution Kickoff Meeting Checklist (continued)

| Project Number: ______________________________________________________________________ |  |  |  |
| --- | --- | --- | --- |
| CONSTRUCTION EXECUTION KICKOFF CHECKLIST FOR PRE-CONSTRUCTION PLANNING |  |  |  |
|  | COMPLETION DATE | ITEM NO. | ACTIVITY |
|  |  | 3 | Modify the company standard Submittal procedure, as necessary, to conform to the contractually-mandated process |
| 44. Review billing and invoicing procedures |  |  |  |
|  |  | 1 | Review the general contractor’s process and timeline for invoicing, lien waivers, and payment |
|  |  | 2 | Review the internal billing cycle established by the accounting department |
|  |  | 3 | If necessary, adjust the internal billing cycle to conform to the general contractor’s invoicing cycle |
|  |  | 4 | Discuss the process for following up with the general contractor on late unpaid invoices |
| 45. Review project and field reporting and tracking procedures |  |  |  |
|  |  | 1 | Discuss the process for reporting labor hours and submitting timecards to the accounting office |
|  |  | 2 | Discuss the process for reporting progress and percent complete |
|  |  | 3 | Discuss the process for tracking material and equipment costs and purchase orders |
|  |  | 4 | Review and discuss the tracking tools that will be used to monitor progress |
|  |  | 5 | Review the monthly update process |
| 46. Review your schedule and the schedule of the general contractor |  |  |  |
|  |  | 1 | Review your bar chart schedule |
|  |  | 2 | Review the general contractor’s schedule and/or timeline |
|  |  | 3 | Discuss the process for updating the schedule |

STANDARD CHANGE ORDER PROCEDURE

- TYPES OF CHANGES:  Three types of changes are commonly encountered in construction: (1) request for quotation, (2) field change directive, and (3) disputed changes to the work.  A request for quotation (RFQ) typically occurs when the customer acknowledges that a change is needed and requests an estimate of the cost prior to approving the change.  A field change directive is an order given in the field to immediately execute a change before the cost of the work has been negotiated.  Disputed changes are changes to the work that are necessary to continue making progress but are not acknowledged by the customer as a change to the contract requirement.  Disputed changes are difficult to recover and require careful documentation to maximize your chances of receiving compensation.

- REQUEST FOR QUOTATION PROCEDURE:

- Enter the change order request in the Change Order Log and assign it a C.O. number.  The status will remain “OPEN” until the C.O. has been approved by the customer.

- The Project Manager should develop a written recap of the requested scope of work, identifying all inclusions, exclusions, and qualifications.

- The Project Manager should develop a cost estimate for the scope of work.  If the scope is large or complex, the Project Manager may request assistance from the Estimator.

- The cost estimate should include direct costs (labor, materials, equipment, subcontractors, expediting fees, etc.), indirect costs (jobsite overhead, home office overhead, insurance premiums, bonds, etc.), and profit (which is added after all other costs have been tallied).

- The Project Manager will fill out a Change Order Proposal with the scope of work and quoted price.

- The Change Order Proposal is forwarded to the customer for approval.

- Once the approval has been received, the status in the Change Order Log is changed to “APPROVED” and the work is implemented.

- FIELD CHANGE DIRECTIVE PROCEDURE:

- A Field Change Directive (FCD) is often issued by the owner’s representative, architect/engineer, or general contractor.  The Field Superintendent and foremen are authorized to accept an FCD only if the issuing authority signs a Field Change Form.

- If the FCD is received by a foreman, the foreman should notify the Field Supervisor immediately.

- FCDs are typically performed on a Time and Materials (T&M) basis.

- The issuing authority and the Field Supervisor/foreman should verbally agree to the scope of work, and this scope should be documented on the Field Change Form.  The foreman and issuing authority should each sign the Field Change Form.

- The FCD is entered into the Change Order Log and assigned a C.O. number.  The status will remain “OPEN” until the FCD has been paid by the customer.

Figure 1: Standard Change Order Process

STANDARD CHANGE ORDER PROCEDURE (continued)

- All labor, materials, equipment, and subcontracts that are used to complete the work should be annotated on the Field Change Form.

- The Field Change Form is forwarded to the Project Manager, who will add the markup and calculate the total cost of the work.

- The Field Change Form is then forwarded to the Accounting Department where it will be entered into the accounting system as a separate line item and invoiced during the next billing cycle.

- Once the FCD has been paid, the status in the Change Order Log is changed to “APPROVED.”

- PROCEDURE FOR DISPUTED CHANGES:

- The disputed work should be processed similar to an RFQ.

- The Project Manager and/or Field Supervisor should develop a detailed written scope of the work that is outside the original contract scope of work, identifying  plans, specifications, other contract documents, and qualifications that support their position.

- The Project Manager should develop a cost estimate for the scope of work.  If the scope is large or complex, the Project Manager may request assistance from the Estimator.

- The cost estimate should include direct costs (labor, materials, equipment, subcontractors, expediting fees, etc.), indirect costs (jobsite overhead, home office overhead, insurance premiums, bonds, etc.), and profit (which is added after all other costs have been tallied).

- The Project Manager will fill out a Change Order Proposal with the scope of work and quoted price.

- The disputed Change Order Proposal is entered into the Change Order Log and assigned a C.O. number.  The status will remain “OPEN” until the C.O. has been approved or rejected by the customer.

- The Change Order Proposal is forwarded to the customer for approval.

- Once an approval or rejection has been received, the status in the Change Order Log is changed to “APPROVED” or “REJECTED.”

Figure 1: Standard Change Order Process (continued)

COMPANY NAME

COMPANY ADDRESS

CHANGE ORDER PROPOSAL

PROJECT NUMBER: ______________________

PROJECT NAME: ___________________________________________________________________

DATE: ___________________________

TO:	________________________________	FROM:	__________________________________

________________________________		__________________________________

________________________________		__________________________________

________________________________		__________________________________

DESCRIPTION OF CHANGED WORK:

COST OF THE CHANGED WORK:

Description	Labor	Materials	Equipment	Other	Subcontracts	Total

____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Labor Burden  ___________%

Bond Premium  __________%

Liability Insurance ________%

Subtotal  _____________________________________

Overhead  ________________

Profit  ____________________

TOTAL  _____________________________________

TIME EXTENSION ______________ calendar days

APPROVED BY:  __________________________________	DATE:  ______________________

Figure 2: Change Order Proposal

| PROJECT NUMBER: _______________________________________________________________ |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PROJECT NAME: _________________________________________________________________ |  |  |  |  |  |  |  |  |  |  |
| FIELD SUPERVISOR: ______________________________________________________________ |  |  |  |  |  |  |  |  |  |  |
| WORK PERFORMED BY (EMPLOYEE NAME): ___________________________________________ |  |  |  |  |  |  |  |  |  |  |
| DATE: __________________________________ |  |  |  |  |  |  |  |  |  |  |
| WORK AUTHORIZED BY: __________________________________________________________ |  |  |  |  |  |  |  |  |  |  |
| TITLE: _________________________________________________________________________ |  |  |  |  |  |  |  |  |  |  |
| FIELD CHANGE FORM |  |  |  |  |  |  |  |  |  |  |
| SCOPE OF WORK: |  |  |  |  |  |  |  |  |  |  |
| LABOR: |  |  |  |  |  |  |  |  | EQUIPMENT/TOOLS: |  |
| EMPLOYEE | HOURS |  |  |  |  |  | WAGE RATE | TOTAL | EQUIPMENT/TOOL TYPE | COST |
|  | REG |  | OT |  | DT |  |  |  |  |  |
| SUBTOTAL |  |  |  |  |  |  |  |  | SUBTOTAL |  |
| ______ % MARKUP |  |  |  |  |  |  |  |  | ______ % MARKUP |  |
| TOTAL |  |  |  |  |  |  |  |  | TOTAL |  |
| MATERIALS: |  |  |  |  |  |  |  |  | SUBCONTRACTORS: |  |
| MATERIAL TYPE |  | UNITS |  | QTY |  | UNIT COST |  | TOTAL | COMPANY NAME | COST |
|  |  |  |  |  |  |  |  |  | SUBTOTAL |  |
|  |  |  |  |  |  |  |  |  | ______ % MARKUP |  |
|  |  |  |  |  |  |  |  |  | TOTAL |  |
|  |  |  |  |  |  |  |  |  | SUMMARY OF COSTS: |  |
|  |  |  |  |  |  |  |  |  | TOTAL LABOR |  |
|  |  |  |  |  |  |  |  |  | TOTAL MATERIALS |  |
| SUBTOTAL |  |  |  |  |  |  |  |  | TOTAL EQUIPMENT/TOOLS |  |
| ______ % MARKUP |  |  |  |  |  |  |  |  | TOTAL SUBCONTRACTS |  |
| TOTAL |  |  |  |  |  |  |  |  | TOTAL COST |  |

Figure 3: Field Change Form

STANDARD REQUEST FOR INFORMATION PROCEDURE

- TYPES OF INFORMATION:  A Request for Information (RFI) is a formal process for receiving more details about a work process and/or alerting the customer to a potential deficiency in the contract documents.  The types of information that must be cycled through the RFI process include: discrepancies between plans and specifications; incomplete design details; conflicts between systems; clarifications about design intent; identification of a changed condition with a request for instructions; missing scope items that would produce a complete product; and many other issues.

- REQUEST FOR INFORMATION PROCEDURE:

- A hierarchy should be followed when identifying and processing RFIs.  Crew members should address questions to their crew foreman.  The crew foreman should fill out the Request for Information form and forward it to the Field Supervisor.  The Field Supervisor should review the form and forward it to the Project Manager.  The Project Manager should review the form and process it.

- Fill out the Request for Information form, including a detailed description of the requested information and the date that a response is required.  When possible, identify a possible solution to a problem, which might speed up the response time and result in a favorable outcome.

- The Project Manager or Field Supervisor should enter the RFI in the Request for Information Log and assign it an RFI number.  The status will remain “OPEN” until the RFI has received a response from the customer.

- The RFI form is forwarded to the customer for a response.

- Once a response has been received, the status in the RFI Log is changed to “CLOSED” and the response is distributed to all affected parties.

- If the response to the RFI will result in an increase in the scope of work or a change in the contract conditions, the Project Manager should immediately initiate a change order request by processing a Change Order Proposal.

Figure 4: Standard Request for Information Procedure

| COMPANY NAME |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| COMPANY ADDRESS |  |  |  |  |  |  |  |
| REQUEST FOR INFORMATION |  |  |  |  |  |  |  |
| PROJECT NUMBER: |  | PROJECT NAME: |  |  | DATE: |  |  |
| RFI NUMBER: |  |  |  |  |  |  |  |
| TO: |  |  | FROM: |  |  |  |  |
| METHOD SENT: |  FAX |  |  MAIL |  E-MAIL |  |  |  |
| INITIATED BY: |  |  |  |  |  |  |  |
| DESCRIPTION OF REQUEST: |  |  |  |  |  |  |  |
| ADDITIONAL SUPPORT DOCUMENTS  ARE  ARE NOT ATTACHED. |  |  |  |  |  |  |  |
| DATE REQUIRED: |  |  |  |  |  |  |  |
| DATE RESPONSE RECEIVED: |  |  |  |  |  |  |  |
| RESPONSE FROM: |  |  |  |  |  |  |  |
| RESPONSE: |  |  |  |  |  |  |  |

Figure 5: Request for Information Form

STANDARD SUBMITTAL PROCEDURE

- TYPES OF SUBMITTALS:  Three types of submittals are commonly encountered in construction: (1) shop drawings, (2) product data/cut sheets, and (3) samples.  Shop drawings reflect the manufacturer’s or equipment designer’s technical details for the product specified in the plans and specifications and usually include dimensions and quantities.  Product data/cut sheets provide information about the make, model, size, capacity, performance, and finish of a product specified in the plans and specifications.  Samples are physical representations of the specified product, such as paint color, brick finish, floor tile, metal roof style and color, and so on.

- SUBMITTAL PROCESSING PROCEDURE:

- The Project Manager should review the plans and specifications to identify all of the submittals that are required by the contract documents and begin filling out the Submittal Log.

- While preparing purchase orders for the materials and equipment, the required type and number of submittals should be identified on the Purchase Order Form.

- When the submittal item is received from the subcontractor/supplier/vendor, the Project Manager should carefully review the submittal to make sure the proposed product conforms to the plans and specifications.

- The front sheet of each submittal should be stamped with the company submittal stamp and initialed by the Project Manager to signal a review has been completed.

- If binders of submittals are not required, the Project Manager should fill out a Submittal Transmittal Form and forward the proper number of copies to the customer for review and approval.  If binders are required, begin assembling binders of all submittals according to their CSI section.  The Submittal Log should be updated to reflect the date sent to the customer.

- Once copy of each submittal should be retained for the files and one copy should be forwarded to the field.  Make sure the copies are marked with their preliminary status (such as, “DRAFT – For Information Only).

- Once the submittal has been reviewed and returned by the customer, one copy should be returned to the subcontractor/supplier/vendor, and the Submittal Log should be updated.

- If the submittal was approved, one approved copy should be retained for the files and one copy sent to the field with the annotation, “APPROVED FOR CONSTRUCTION.”

- If the submittal was rejected, the submittal process will have to be repeated.

Figure 6: Standard Submittal Procedures

| COMPANY NAME |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| COMPANY ADDRESS |  |  |  |  |  |  |
| SUBMITTAL TRANSMITTAL FORM |  |  |  |  |  |  |
| PROJECT NUMBER: __________________________________ |  |  |  | DATE: _______________________ |  |  |
| PROJECT NAME: ____________________________________________________________________ |  |  |  |  |  |  |
| CSI SECTION: _________________ |  |  |  |  |  |  |
| TO: |  | FROM: |  |  |  |  |
| QTY | SUBMITTAL DESCRIPTION | FOR YOUR REVIEW | FOR YOUR APPROVAL | FOR YOUR FILES | FOR INFORMATION ONLY | DATE REQ’D |
| Please return _______ copies. |  |  |  |  |  |  |
| Additional Comments: ________________________________________________________________ |  |  |  |  |  |  |
| ____________________________________________________________________________________ |  |  |  |  |  |  |
| ____________________________________________________________________________________ |  |  |  |  |  |  |
| ____________________________________________________________________________________ |  |  |  |  |  |  |
| Signature: ___________________________________________ |  |  |  |  |  |  |
| Date: _______________________________________________ |  |  |  |  |  |  |

Figure 7: Submittal Transmittal Form

COMPANY NAME

COMPANY ADDRESS

COMPANY PHONE NUMBER

NAME OF NEW EMPLOYEE: _______________________________________________________

PROJECT NUMBER: ______________________________________________________________

PROJECT NAME: ________________________________________________________________

DATE OF EMPLOYMENT: ______________________

TODAY’S DATE: ______________________________

SUBJECT: Requirements and Expectations of Personnel Employed on Project Number ______________

The purpose of this letter is to notify you of special requirements and expectations of all personnel who will work on Project Number ____________________, entitled __________________________________.  The following requirements and expectations must be met as a necessary condition of employment:

      - This project requires weekly random drug testing, which will be conducted by a private company employed by the customer.  Any employee who fails a drug test or refuses to submit to a random drug test will be immediately dismissed from employment.

      - This project requires a complete background check and the use of a security badge at all times.  Employees who fail to exhibit their security badge, or who arrive at the jobsite without their badge, will be removed from the premises immediately.

      - Entry into certain parts of the facility will require an escort appointed by the customer.  Requests for escorts must be submitted 24 hours in advance.

      - The work hours for this project are Monday through Friday from 7:00 AM to 3:00 PM.

      - No privately owned vehicles or company vehicles will be permitted into the secure work area.  All employees must arrive at the security gate each morning no later than 6:45 AM to board a bus that will take employees to the secure work area.  All employees must be at the pickup point each afternoon at 3:15 PM to board the bus and be escorted out of the secure area.  Late employees will not be permitted into the secure area.

      - Employees may be monitored by closed-circuit television throughout the day.

      - Smoking will not be permitted inside the secure work area.

Please acknowledge your acceptance of the requirements and expectations of this project by signing and dating below.

I understand and accept the above terms of employment.

_____________________________________________	______________________________

NAME	DATE

_____________________________________________	______________________________

WITNESS	DATE

Figure 8: Requirements and Expectations Letter

COMPANY NAME

COMPANY ADDRESS

COMPANY PHONE NUMBER

Subcontractor Representative

Subcontractor Company Name

Subcontractor Company Address

Subcontractor Phone Number

DATE:  December 1, 2005

SUBJECT:  Letter of Intent to Award a Contract

Dear Subcontractor Representative:

You have been selected as the successful bidder on Project Number __________, entitled _________________________________________________________.  Per our telephone conversation, we are in the process of developing a contract for the scope of work identified in your bid submission.  The contract amount will be $XXX,XXX.

The purpose of this letter is to notify you of our intent to award a contract.  You can expect to receive the contract no later than January 1, 20XX.  You are authorized to proceed with the work identified in your bid submission.

Please feel free to contact me at (XXX) XXX-XXXX.

Sincerely,

Company Officer

Title

Figure 9: Letter of Intent

| COMPANY NAME |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| COMPANY ADDRESS |  |  |  |  |  |
| PURCHASE ORDER FORM |  |  |  |  |  |
| DATE: |  |  |  |  |  |
| P.O. NUMBER: |  |  |  |  |  |
| PROJECT NUMBER: |  |  |  |  |  |
| PROJECT NAME: |  |  |  |  |  |
| TO: |  |  |  |  |  |
| SHIP TO: | (Home office or jobsite address) |  |  | SHIP VIA __ _ (jobsite) ___ F.O.B. |  |
| REQUIRED SHIP DATE: |  |  |  |  |  |
| QUANTITY | DESCRIPTION OF ITEM(S) |  |  |  | COST |
| NOTE: MATERIAL SAFETY DATA SHEETS ARE REQUIRED WITH ALL SHIPMENTS |  |  |  |  |  |
| SHIPPING INSTRUCTIONS: |  |  |  |  |  |
| ADDITIONAL REQUIREMENTS: |  |  |  |  |  |
| 1. Submit _____ copies of shop drawings/details/performance data for review/approval |  |  |  |  |  |
| 2. Submit _____ copies of O&M manuals or _____ copies of wiring diagrams for review/ approval |  |  |  |  |  |
| NAME: |  |  | NAME: |  |  |
| SIGNATURE: |  |  | SIGNATURE: |  |  |
| DATE: |  |  | DATE: |  |  |

Figure 10: Purchase Order Form

STANDARD BILLING PROCEDURE

- TYPES OF BILLING:  Most larger projects will require progress billing, where a schedule of values (SOV) is developed to break down, and bill, portions of the work.  These procedures cover the progress billing procedure.  However, other types of billing that might occur include: requisitions, time and materials (T&M) pay request, cost plus pay request, and unit price billing.

- BILLING PROCEDURE:

- The first step to the billing process involves the creation of a schedule of values that breaks down the work into discrete line items that can be tracked and billed.  The schedule of values (SOV) must be approved by the customer prior to the first billing cycle.

- The accounting department will initiate the monthly billing process by distributing the previous month’s bill to the Project Manager for updating.

- The Project Manager will update the percent complete of each line item on the SOV using a pen or pencil.

- The Project Manager returns the marked-up bill to the accounting department, who will then revise the percent complete in the accounting system and print a new bill.

- The accounting department will obtain lien waivers from all subcontractors and suppliers who have line items on the bill.

- The bill will be submitted to the customer for review, approval, and payment.

- Once a month, the accounts receivable will be updated so that all Project Managers can view the most current payments received on their projects.

- It is the Project Manager’s responsibility to follow up on open receivables on a weekly basis.

Figure 11: Standard Billing Procedure

STANDARD PROGRESS UPDATE PROCEDURE

- TYPES OF UPDATES:  Three types of reporting are common in construction: (1) summary progress update reporting, (2) labor productivity reporting, and (3) forecasting.  A summary progress report identifies estimated labor, materials, and other costs and compares them to current expenditures in order to highlight variances.  Labor productivity reporting identifies quantities installed, labor hours expended on the installation, and hours per unit and then compares actual productivity to estimated productivity.  Forecasting involves evaluating the current status plus all outstanding expenditures and predicting the cost and labor hours expended upon completion.

- SUMMARY PROGRESS UPDATING PROCEDURE:

- Summary progress reports can be accessed anytime through the accounting system.  When the budget was developed, the estimated line item values were entered into the system.  As labor, materials, and other purchase orders are expended, these expenditures are entered into the system so that the actual values can be compared to the estimated values.

- Each week, timesheets are turned in and labor hours are recorded against various budget line items by the accounting department.

- As purchase orders are paid, the paid value is entered against their associated line items in the budget.

- The accounting system will automatically calculate the variance between the actual values and estimated values.  A negative variance indicates that the budgeted value has been exceeded.

- Variances greater than 5% should be investigated by the Project Manager, and actions should be taken to address problems, such as poor productivity or disruptions to the work flow.

- LABOR PRODUCTIVITY UPDATING PROCEDURE:

- When the budget was developed, labor and quantities of materials were estimated for each budget line item.  The accounting system was thus able to establish estimated hours per unit and total cost per budget line item.

- Each week, timesheets are submitted to the accounting department and labor hours are recorded against various budget line items.

- Furthermore, each week, the Project Manager and/or Field Supervisor should walk the jobsite to estimate the quantity of materials that have been installed.  These values are entered into the accounting system by the Project Manager or accounting representative.

- Once the actual values are input into the system, the computer can calculate the actual productivity (hours per unit) versus the estimated.

- The Project Manager should then evaluate the variance and investigate differences that exceed 5%.

Figure 12: Standard Progress Update Procedure 
STANDARD PROGRESS UPDATE PROCEDURE

- FORECASTING PROCEDURE:

- Both the summary progress update report and labor productivity report can be modified to permit forecasting of future costs at completion.

- It is the Project Manager’s responsibility to input forecasted costs and hours into the computer, with input provided by the field supervisor.

- The Project Manager should review potential change orders, future equipment and material purchases, and expected labor productivity when preparing the forecast.  The forecast must account for outstanding costs plus any additional adjustment made for better/worse productivity, higher/lower material costs, gain/loss on changed work, etc.  The Project Manager should attempt to be as accurate and candid as possible.

- Once the forecast has been completed, the Project Manager should evaluate whether the project is within budget, under budget, or over budget.  Adjustments may be necessary to get the project back on track if it is over the estimated budget or labor hours.

Figure 12: Standard Progress Update Procedure (continued)