## GSL_SOP_Metadata
SOP ID | Name | SOP File Name | SOP ID | Title | Description | Phase | Category (CCC Tag) | Category Group | Roles (RACI) | Primary JD | Discipline | Revision | Effective Date | Owner | Approver | Formerly | Status | Tags / Keywords | Related SOPs | Department / Division | Last Reviewed Date | Next Review Due | Document Type
9.1.050 | 9.1.050 – Prepare Construction Takeoff | 9.1.050 – Prepare Construction Takeoff | 9.1.050 | Prepare Construction Takeoff | [6 empty] | Operations
9.2.005 | 9.2.005 – Review Contract for High Risk Clauses | 9.2.005 – Review Contract for High Risk Clauses | 9.2.005 | Review Contract for High Risk Clauses
9.2.010 | 9.2.010 – Team Selection | 9.2.010 – Team Selection | 9.2.010 | Team Selection | Identify, assign, approve, and document project team and key support roles prior to turnover and mobilization to ensure manpower capacity, risk coverage, and procurement support. | 2 – Preconstruction | 120 – Coordination | 200–299 Preconstruction Planning | Project Manager; General Superintendent; Branch Manager/Business Manager; Safety Coordinator; Purchasing; Prefabrication Lead; Project Coordinator |  | Operations | 2 | 2026-01-08 | Project Management | Executive Committee | Formerly 9.41.005 | Approved | team selection; staffing plan; resource allocation; manpower projections; workforce planning; turnover meeting; field leadership; safety staffing; procurement support; prefabrication support; risk coverage; branch capacity; admin support | 9.2.015; 9.2.040; 9.4.190 | Project Management / Operations | 2026-01-08 | 2027-01-08 | SOP
9.2.015 | 9.2.015 – Project Turnover Meeting | 9.2.015 – Project Turnover Meeting | 9.2.015 | Project Turnover Meeting | Structured Estimator-led meeting transferring bid knowledge to Operations and aligning project team prior to execution. | 2 – Preconstruction | 120 – Coordination | 200–299 Preconstruction Planning | Estimator; PM; Contract Manager; General Superintendent; Field Leadership; Prefab Lead; Safety Coordinator; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.010 | Draft | turnover; estimating; handoff; Smartsheet; bid review | 9.2.010; 9.2.020 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.020 | 9.2.020 – Procurement of Large Feeder Wire | 9.2.020 – Procurement of Large Feeder Wire | 9.2.020 | Procurement of Large Feeder Wire | Secure early pricing, vendor storage commitments, and delivery expectations for large feeder wire. | 2 – Preconstruction | 190 – Materials Mgmt | 200–299 Preconstruction Planning | PM; APM; Project Coordinator; Purchasing; Vendor; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.2.10; 9.41.010 | Draft | feeder wire; RFQ; vendor storage; delivery plan; PO | 9.2.080; 9.2.110 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.030 | 9.2.030 – Review Contract for Unfavorable or High-Risk Clauses | 9.2.030 – Review Contract for Unfavorable or High-Risk Clauses | 9.2.030 | Review Contract for Unfavorable or High-Risk Clauses | Review contract terms; flag risk, flowdowns, and approvals before baseline planning. | 2 – Preconstruction | 160 – Scope & Change Control | 200–299 Preconstruction Planning | PM; Branch Manager; Contracts Admin |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.015 | Draft | contract risk; flowdowns; terms; exceptions | 9.2.110 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.040 | 9.2.040 – Project Manager Reviews Plans, Specifications & Schedule | 9.2.040 – Project Manager Reviews Plans, Specifications & Schedule | 9.2.040 | Project Manager Reviews Plans, Specifications & Schedule | PM reviews drawings/specs and preliminary schedule to identify gaps and constraints. | 2 – Preconstruction | 130 – Documentation Mgmt | 200–299 Preconstruction Planning | PM; APM |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.020 | Draft | document review; specs; drawings; schedule | 9.2.060; 9.2.110 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.050 | 9.2.050 – Field Supervisor Reviews Plans, Specifications & Schedule | 9.2.050 – Field Supervisor Reviews Plans, Specifications & Schedule | 9.2.050 | Field Supervisor Reviews Plans, Specifications & Schedule | Field review of constructability, logistics, and constraints. | 2 – Preconstruction | 130 – Documentation Mgmt | 200–299 Preconstruction Planning | General Superintendent; Field Supervisor |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.025 | Approved | constructability; logistics; constraints | 9.2.070; 9.2.080 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.055 | 9.2.055 – Compare Estimated vs Planned Performance | 9.2.055 – Compare Estimated vs Planned Performance | 9.2.055 | Compare Estimated vs Planned Performance |  | 3 – Preconstruction |  |  |  |  | Operations
9.2.057 | 9.2.057 – Identify Value Engineering & Prefabrication Opportunities | 9.2.057 – Identify Value Engineering & Prefabrication Opportunities | 9.2.057 | Identify Value Engineering & Prefabrication Opportunities | Identify, evaluate, and document VE and prefabrication opportunities that reduce cost and/or improve productivity while maintaining contract scope, quality, schedule intent, and safety. | 2 – Preconstruction | 120 – Coordination | 200–299 Preconstruction Planning | Project Manager; Prefabrication Lead; Field Supervisor/General Superintendent; Estimator; Contract Manager; Safety Coordinator; BIM/VDC; Branch Manager |  | Operations | 1 | 2026-01-08 | Project Management | Executive Committee |  | Draft | value engineering; VE; prefabrication; prefab; constructability; means and methods; cost comparison; labor hours; material cost; schedule impact; PEP updates; approvals; GC/Owner; submittals; RFI; proposal; log; labeling; packaging; delivery; staging; shop capacity; trade coordination; lessons learned | 9.2.055; 9.2.015; 9.1.050; 9.4.190 | Project Management / Operations / Prefabrication | 2026-01-08 | 2027-01-08 | SOP
9.2.060 | 9.2.060 – Create List of Issues & Begin RFI Process | 9.2.060 – Create List of Issues & Begin RFI Process | 9.2.060 | Create List of Issues & Begin RFI Process | Create an issues log and launch RFIs to resolve ambiguities and conflicts. | 2 – Preconstruction | 130 – Documentation Mgmt | 200–299 Preconstruction Planning | PM; APM; Project Coordinator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.030 | Approved | RFI; issues log; clarifications | 9.2.040; 9.2.110 | Accounting | 2025-10-10 | 2026-10-10 | SOP
9.2.070 | 9.2.070 – Conduct Site Visit | 9.2.070 – Conduct Site Visit | 9.2.070 | Conduct Site Visit | Perform a pre-mobilization site visit to verify site conditions, logistics constraints, and safety hazards; document findings and integrate into the Project Execution Plan (PEP) and RFI process. | 2 – Preconstruction | 120 – Coordination | 200–299 Preconstruction Planning | PM (A); Field Leadership (R); Safety Coordinator (R); General Superintendent (C) |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.035 | Draft | preconstruction; site visit; logistics; access; laydown; staging; utilities; safety hazards; PPE; photos; PEP; RFI; document control | 9.2.060; 9.2.055; 9.4.190 | Field Operations / Project Management | 2026-01-07 | 2027-01-07 | SOP
9.2.080 | 9.2.080 – Prepare Material Handling Plan | 9.2.080 – Prepare Material Handling Plan | 9.2.080 | Prepare Material Handling Plan | Plan delivery, staging, movement, and storage of materials aligned to schedule. | 2 – Preconstruction | 190 – Materials Mgmt | 200–299 Preconstruction Planning | PM; Field Supervisor; Safety; General Superintendent |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.060 | Draft | material flow; staging; equipment; deliveries | 9.2.070; 9.2.020 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.090 | 9.2.090 – Develop Labor Budget | 9.2.090 – Develop Labor Budget | 9.2.090 | Develop Labor Budget | Create the labor budget using takeoffs, productivity, and sequencing; integrate with PEP. | 2 – Preconstruction | 192 – Labor Mgmt | 200–299 Preconstruction Planning | PM; General Superintendent; Estimator; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.065 | Draft | labor hours; productivity; manpower forecast; PEP | 9.2.100; 9.2.110 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.100 | 9.2.100 – Prepare Layout & Sequencing Plan | 9.2.100 – Prepare Layout & Sequencing Plan | 9.2.100 | Prepare Layout & Sequencing Plan | Develop coordinated layout and work sequencing tied to milestones and logistics. | 2 – Preconstruction | 240 – Field Involvement/BIM | 200–299 Preconstruction Planning | PM; Field Supervisor; General Superintendent; Safety |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.070 | Draft | layout; sequencing; BIM; milestones | 9.2.090; 9.2.110 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.110 | 9.2.110 – Develop Project Schedule | 9.2.110 – Develop Project Schedule | 9.2.110 | Develop Project Schedule | Build the baseline schedule integrating procurement, labor, sequencing, and contract milestones. | 2 – Preconstruction | 150 – Scheduling | 200–299 Preconstruction Planning | PM; General Superintendent; Purchasing; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.075 | Draft | baseline schedule; milestones; procurement integration | 9.2.090; 9.2.080; 9.2.120 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.120 | 9.2.120 – Establish Tracking & Control Systems | 9.2.120 – Establish Tracking & Control Systems | 9.2.120 | Establish Tracking & Control Systems | Stand up standardized tracking for labor, procurement, RFIs, submittals, safety, and reporting. | 2 – Preconstruction | 170 – Cost Control & Billing | 200–299 Preconstruction Planning | PM; Field Supervisor; Purchasing; Safety; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.080 | Draft | logs; dashboards; labor tracking; procurement log; safety reports | 9.2.110; 9.2.130 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.130 | 9.2.130 – Construction Execution Kickoff Meeting | 9.2.130 – Construction Execution Kickoff Meeting | 9.2.130 | Construction Execution Kickoff Meeting | Hold a kickoff aligning scope, schedule, safety, manpower, procurement, and communication. | 2 – Preconstruction | 120 – Coordination | 200–299 Preconstruction Planning | PM; General Superintendent; Field Supervisor; Purchasing; Safety; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.085 | Draft | kickoff; mobilization; scope alignment; safety; procurement | 9.2.120 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.140 | 9.2.140 – Develop Project Budget | 9.2.140 – Develop Project Budget | 9.2.140 | Develop Project Budget | Build the project budget from contract and estimate; assign cost codes; approve before mobilization; file per SOP 9.4.190. | 2 – Preconstruction | 170 – Cost Control & Billing | 200–299 Preconstruction Planning | PM; Estimator; Accounting; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.395 | Draft | budget; cost codes; baseline; approval | 9.4.410; 9.4.400; 9.4.405 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.2.160 | 9.2.160 – Develop Procurement Plan | 9.2.160 – Develop Procurement Plan | 9.2.160 | Develop Procurement Plan | Develop a procurement plan identifying major materials, equipment, and subcontracts with lead times and responsibilities. | 2 – Preconstruction | 210 – Pricing & Cost Control | 200–299 Preconstruction Planning | PM; Estimator; Purchasing; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.600 | Draft | procurement plan; lead times; long lead items | 9.2.020; 9.4.605; 9.4.620 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.010 | 9.3.010 – Setup Office Trailer | 9.3.010 – Setup Office Trailer | 9.3.010 | Setup Office Trailer | Set up an operational office trailer with utilities, IT/communications, safety equipment, and furnishings. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Site Administrator; General Superintendent; IT/Communications |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.090 | Draft | trailer; utilities; internet; phones; HVAC; safety | 9.3.020; 9.3.030 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.020 | 9.3.020 – Setup Storage Trailer | 9.3.020 – Setup Storage Trailer | 9.3.020 | Setup Storage Trailer | Install and secure a storage trailer; implement shelving and inventory control for materials/equipment. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Field Supervisor; Safety |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.095 | Draft | storage; locks; shelving; inventory; fire safety | 9.3.010; 9.3.100 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.030 | 9.3.030 – Setup Site Fencing and Access Control | 9.3.030 – Setup Site Fencing and Access Control | 9.3.030 | Setup Site Fencing and Access Control | Install perimeter fencing, secure access points, and implement entry/exit protocols per safety and client requirements. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Field Supervisor; Safety; Security Personnel |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.100 | Draft | fencing; gates; access control; signage; OSHA | 9.3.080; 9.3.090 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.040 | 9.3.040 – Setup Temporary Power | 9.3.040 – Setup Temporary Power | 9.3.040 | Setup Temporary Power | Provide safe, code-compliant temporary power and distribution for construction activities. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Field Supervisor; Electrical Subcontractor; Safety |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.105 | Draft | temporary power; distribution; grounding; GFCI; NEC | 9.3.010; 9.3.070 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.050 | 9.3.050 – Setup Temporary Water | 9.3.050 – Setup Temporary Water | 9.3.050 | Setup Temporary Water | Establish temporary water service and distribution for construction and sanitary needs; ensure environmental compliance. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Field Supervisor; Safety |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.110 | Draft | temporary water; backflow; hydrant meter; dust control | 9.3.060; 9.3.040 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.060 | 9.3.060 – Setup Sanitary Facilities | 9.3.060 – Setup Sanitary Facilities | 9.3.060 | Setup Sanitary Facilities | Provide OSHA-compliant sanitary facilities (toilets, wash stations) with service/cleaning schedules and inspection logs. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Field Supervisor; Safety |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.115 | Draft | sanitary; toilets; wash stations; ADA; inspections | 9.3.050 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.070 | 9.3.070 – Setup Temporary Lighting | 9.3.070 – Setup Temporary Lighting | 9.3.070 | Setup Temporary Lighting | Install temporary lighting to meet OSHA illumination levels for work areas, walkways, and security zones. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Field Supervisor; Electrical Subcontractor; Safety |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.120 | Draft | temporary lighting; OSHA; coverage; cords | 9.3.040 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.080 | 9.3.080 – Setup Signage | 9.3.080 – Setup Signage | 9.3.080 | Setup Signage | Install safety, hazard, directional, and informational signage per OSHA and client standards. | 3 – Mobilization & Job Site Setup | 140 – Communication | 100–199 Project Execution | PM; Field Supervisor; Safety |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.125 | Draft | signage; safety; hazard; PPE; directional | 9.3.030 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.090 | 9.3.090 – Setup Security | 9.3.090 – Setup Security | 9.3.090 | Setup Security | Implement site security plan: locks, cameras, lighting, access protocols, and incident logging. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Field Supervisor; Safety; Security Personnel |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.130 | Draft | security; surveillance; access; incident reports | 9.3.030; 9.3.080 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.100 | 9.3.100 – Setup Laydown Area | 9.3.100 – Setup Laydown Area | 9.3.100 | Setup Laydown Area | Designate, organize, and secure laydown areas; mark access lanes and integrate with the material handling plan. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Field Supervisor; Safety |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.135 | Draft | laydown; staging; lanes; ground protection | 9.3.020; 9.2.080 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.110 | 9.3.110 – Setup Equipment Staging | 9.3.110 – Setup Equipment Staging | 9.3.110 | Setup Equipment Staging | Establish equipment staging areas for safe and efficient deployment of construction equipment. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Field Supervisor; Equipment Operator; Safety Coordinator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.140 | Draft | equipment staging; mobilization; OSHA; traffic control | 9.3.100 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.120 | 9.3.120 – Setup Parking | 9.3.120 – Setup Parking | 9.3.120 | Setup Parking | Designate and manage parking areas for workers and visitors to ensure safe access and traffic flow. | 3 – Mobilization & Job Site Setup | 110 – Mobilization | 100–199 Project Execution | PM; Field Supervisor; Safety Coordinator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.145 | Draft | parking; traffic; ADA; lighting | 9.3.110; 9.3.100 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.3.470 | 9.3.470 – Develop Site – Specific Safety Plan | 9.3.470 – Develop Site – Specific Safety Plan | 9.3.470 | Develop Site – Specific Safety Plan | Prepare and implement a project-specific safety plan addressing hazards and compliance requirements. | 3 – Mobilization & Job Site Setup | 193 – Safety Mgmt | 100–199 Project Execution | Safety Coordinator; PM; Field Supervisor; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.470 | Draft | safety plan; hazard assessment; OSHA; SSSP | 9.3.010; 9.3.115; 9.4.165 | Safety | 2025-10-10 | 2026-10-10 | SOP
9.4.010 | 9.4.010 – Conduct Coordination Meetings | 9.4.010 – Conduct Coordination Meetings | 9.4.010 | Conduct Coordination Meetings | Standard weekly coordination meeting to align stakeholders, track actions, and resolve issues. | 4 – Construction | 120 – Coordination | 100–199 Project Execution | PM; Field Supervisor; Subcontractors; Site Admin |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.150 | Draft | coordination; agenda; minutes; action items | 9.4.020; 9.4.030 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.020 | 9.4.020 – Conduct Subcontractor Coordination Meetings | 9.4.020 – Conduct Subcontractor Coordination Meetings | 9.4.020 | Conduct Subcontractor Coordination Meetings | Weekly meetings to align subcontractor activities with schedule, logistics, and safety requirements. | 4 – Construction | 120 – Coordination | 100–199 Project Execution | PM; Subcontractors; Field Supervisor; Safety |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.155 | Draft | subcontractor; coordination; schedule; logistics | 9.4.010; 9.2.110 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.030 | 9.4.030 – Conduct Client/Owner Meetings | 9.4.030 – Conduct Client/Owner Meetings | 9.4.030 | Conduct Client/Owner Meetings | Hold regular client/owner meetings to review progress and maintain contractual alignment. | 4 – Construction | 140 – Communication | 100–199 Project Execution | PM; Branch Manager; Client/Owner; Safety |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.160 | Draft | client meetings; owner updates; issues; minutes | 9.4.010 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.040 | 9.4.040 – Conduct Safety Meetings | 9.4.040 – Conduct Safety Meetings | 9.4.040 | Conduct Safety Meetings | Conduct regular safety meetings and daily huddles to promote awareness and compliance. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | Safety Coordinator; PM; Field Supervisor; All Employees |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.165 | Draft | safety meetings; toolbox; attendance; OSHA | 9.3.060; 9.3.070 | Safety | 2025-10-10 | 2026-10-10 | SOP
9.4.050 | 9.4.050 – Conduct Prefabrication Coordination Meetings | 9.4.050 – Conduct Prefabrication Coordination Meetings | 9.4.050 | Conduct Prefabrication Coordination Meetings | Coordinate prefab deliverables with construction schedule and manpower plans. | 4 – Construction | 120 – Coordination | 100–199 Project Execution | PM; Prefab Lead; Field Supervisor; General Superintendent |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.170 | Draft | prefab; coordination; delivery; logistics | 9.2.080; 9.2.090 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.060 | 9.4.060 – Conduct Quality Meetings | 9.4.060 – Conduct Quality Meetings | 9.4.060 | Conduct Quality Meetings | Hold quality meetings to review inspection results, NCRs, and corrective actions. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | PM; Field Supervisor; Quality Inspector; Safety Coordinator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.175 | Draft | quality; NCR; inspection; corrective action | 9.4.010 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.190 | 9.4.190 – Document Filing Standards | 9.4.190 – Document Filing Standards | 9.4.190 | Document Filing Standards | Define filing locations, naming rules, and responsibilities in Procore and Windows folders to ensure consistent project documentation and version control. | 4 – Construction | 130 – Documentation Mgmt | 100–199 Project Execution | PM; Field Foreman; Site Administrator; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | 9.41.190A | Draft | document filing, document control, project documentation, folder structure, standard template, file naming conventions, version control, revisions, superseded documents, archive, Procore, Windows folders, submittals, RFIs, drawings, change orders, contracts, daily reports, timecards, closeout package, warranty documents, permissions, audit | 9.6.060; 9.4.195; 9.4.200 | Operations | 2026-01-07 | 2026-10-10 | SOP
9.4.195 | 9.4.195 – Manage Project Documentation System | 9.4.195 – Manage Project Documentation System | 9.4.195 | Manage Project Documentation System | Establish and maintain structured documentation systems ensuring accessibility and compliance with SOP 9.4.190 Document Filing Standards. | 4 – Construction | 130 – Documentation Mgmt | 100–199 Project Execution | PM; Site Administrator; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.195 | Draft | documentation; control logs; audits; archiving | 9.4.190; 9.4.200; 9.6.010 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.200 | 9.4.200 – Manage Submittals | 9.4.200 – Manage Submittals | 9.4.200 | Manage Submittals | Prepare, submit, track, and close out all project submittals in accordance with specifications and schedule. | 4 – Construction | 230 – Submittals | 100–199 Project Execution | PM; Purchasing; Subcontractors |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.200 | Draft | submittals; approvals; log; product data; schedule | 9.4.195; 9.4.225 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.205 | 9.4.205 – Manage RFIs (Requests for Information) | 9.4.205 – Manage RFIs (Requests for Information) | 9.4.205 | Manage RFIs (Requests for Information) | Standardize RFI creation, tracking, and resolution to ensure timely responses and documentation. | 4 – Construction | 130 – Documentation Mgmt | 100–199 Project Execution | PM; Field Supervisor; Estimator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.205 | Draft | RFI; coordination; tracking; Procore | 9.2.060; 9.4.195 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.210 | 9.4.210 – Manage Meeting Minutes | 9.4.210 – Manage Meeting Minutes | 9.4.210 | Manage Meeting Minutes | Standardize recording, approval, and archiving of meeting minutes to ensure accountability and continuity. | 4 – Construction | 120 – Coordination | 100–199 Project Execution | PM; Site Administrator; Meeting Participants |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.210 | Draft | meeting minutes; agenda; actions; distribution | 9.4.010; 9.4.020; 9.4.030 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.215 | 9.4.215 – Manage Daily Reports | 9.4.215 – Manage Daily Reports | 9.4.215 | Manage Daily Reports | Document daily site conditions, manpower, equipment, progress, and incidents using standardized reporting tools. | 4 – Construction | 130 – Documentation Mgmt | 100–199 Project Execution | Field Supervisor; PM; Safety Coordinator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.215 | Draft | daily reports; manpower; progress; weather | 9.4.165; 9.4.175 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.220 | 9.4.220 – Manage Drawing Logs | 9.4.220 – Manage Drawing Logs | 9.4.220 | Manage Drawing Logs | Maintain accurate and current drawing logs to ensure field teams work from the latest approved drawings. | 4 – Construction | 130 – Documentation Mgmt | 100–199 Project Execution | PM; Site Administrator; Field Supervisor |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.220 | Draft | drawings; revisions; Procore; distribution | 9.4.205; 9.4.225 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.225 | 9.4.225 – Manage Specifications | 9.4.225 – Manage Specifications | 9.4.225 | Manage Specifications | Log, track, and distribute specifications to ensure compliance and accessibility for all project stakeholders. | 4 – Construction | 130 – Documentation Mgmt | 100–199 Project Execution | PM; Site Administrator; Field Supervisor |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.225 | Draft | specifications; revisions; compliance; distribution | 9.4.200; 9.4.220 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.230 | 9.4.230 – Manage Correspondence | 9.4.230 – Manage Correspondence | 9.4.230 | Manage Correspondence | Log, track, and store all project correspondence to ensure accountability and claims protection. | 4 – Construction | 130 – Documentation Mgmt | 100–199 Project Execution | PM; Site Administrator; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.230 | Draft | correspondence; emails; letters; logs; filing | 9.4.190; 9.4.195; 9.4.205; 9.4.210 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.235 | 9.4.235 – Manage Permits | 9.4.235 – Manage Permits | 9.4.235 | Manage Permits | Obtain, track, and maintain all project permits and inspection records required by law and contract. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | PM; Safety Coordinator; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.235 | Draft | permits; compliance; regulatory; tracking | 9.3.010; 9.3.060; 9.4.240 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.240 | 9.4.240 – Manage Inspection Reports | 9.4.240 – Manage Inspection Reports | 9.4.240 | Manage Inspection Reports | Ensure safety and quality inspections are logged, distributed, and archived to support corrective actions. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | PM; Safety Coordinator; Quality Inspector; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.240 | Draft | inspection reports; quality; safety; corrective action | 9.4.165; 9.4.175; 9.4.235 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.270 | 9.4.270 – Manage Project Communications | 9.4.270 – Manage Project Communications | 9.4.270 | Manage Project Communications | Establish a consistent process for managing project communications for accountability and traceability. | 4 – Construction | 140 – Communication | 100–199 Project Execution | PM; Field Foreman; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.270 | Draft | communication; correspondence; Procore; email | 9.4.230; 9.4.210 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.275 | 9.4.275 – Manage Internal Communications | 9.4.275 – Manage Internal Communications | 9.4.275 | Manage Internal Communications | Ensure timely and accurate internal communications within the GSL project team. | 4 – Construction | 140 – Communication | 100–199 Project Execution | PM; Superintendent; Field Foreman; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.275 | Draft | internal communication; coordination; meetings; daily updates | 9.4.150; 9.4.165 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.280 | 9.4.280 – Manage External Communications | 9.4.280 – Manage External Communications | 9.4.280 | Manage External Communications | Standardize all external communications with clients, architects, engineers, subcontractors, and vendors routed through the Project Manager. | 4 – Construction | 140 – Communication | 100–199 Project Execution | PM; Site Administrator; Field Foreman |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.280 | Draft | external communication; correspondence; Procore; logging | 9.4.190; 9.4.230; 9.4.160 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.285 | 9.4.285 – Manage Client/Owner Communications | 9.4.285 – Manage Client/Owner Communications | 9.4.285 | Manage Client/Owner Communications | Provide consistent and professional client/owner communications ensuring documentation of all meetings and contractual updates. | 4 – Construction | 140 – Communication | 100–199 Project Execution | PM; Branch Manager; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.285 | Draft | client communication; owner updates; minutes; correspondence | 9.4.160; 9.4.280; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.290 | 9.4.290 – Manage Subcontractor Communications | 9.4.290 – Manage Subcontractor Communications | 9.4.290 | Manage Subcontractor Communications | Define process for issuing, logging, and tracking subcontractor correspondence and directives. | 4 – Construction | 180 – Subcontractor Mgmt | 100–199 Project Execution | PM; Field Supervisor; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.290 | Draft | subcontractor communication; directives; coordination | 9.4.155; 9.4.280; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.295 | 9.4.295 – Manage Vendor Supplier Communications | 9.4.295 – Manage Vendor Supplier Communications | 9.4.295 | Manage Vendor Supplier Communications
9.4.300 | 9.4.300 – Manage Architect/Engineer Communications | 9.4.300 – Manage Architect/Engineer Communications | 9.4.300 | Manage Architect/Engineer Communications | Track and document all architect/engineer communications including RFIs, clarifications, and revisions. | 4 – Construction | 240 – Field Involvement/BIM | 100–199 Project Execution | PM; Field Supervisor; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.300 | Draft | architect; engineer; RFI; design coordination | 9.4.205; 9.4.220; 9.4.225 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.305 | 9.4.305 – Manage Regulatory/Authority Communications | 9.4.305 – Manage Regulatory/Authority Communications | 9.4.305 | Manage Regulatory/Authority Communications | Manage communications with regulatory authorities to coordinate inspections, permits, and approvals. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | PM; Safety Coordinator; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.305 | Draft | AHJ; permits; inspections; authority coordination | 9.4.235; 9.4.240; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.310 | 9.4.310 – Manage General Contractor Communications | 9.4.310 – Manage General Contractor Communications | 9.4.310 | Manage General Contractor Communications | Standardize GC correspondence, directives, and meeting documentation for coordination and compliance. | 4 – Construction | 120 – Coordination | 100–199 Project Execution | PM; Field Supervisor; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.310 | Draft | GC communication; directives; coordination; meetings | 9.2.015; 9.4.150; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.315 | 9.4.315 – Develop Project Schedule | 9.4.315 – Develop Project Schedule | 9.4.315 | Develop Project Schedule | Develop baseline schedule with critical path, milestones, and resource allocations per contract requirements. | 4 – Construction | 150 – Scheduling | 100–199 Project Execution | PM; Superintendent; Scheduler |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.315 | Draft | baseline schedule; milestones; CPM; planning | 9.2.110; 9.4.320; 9.4.325 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.320 | 9.4.320 – Update Project Schedule | 9.4.320 – Update Project Schedule | 9.4.320 | Update Project Schedule | Maintain schedule accuracy through regular updates reflecting actual progress and forecast adjustments. | 4 – Construction | 150 – Scheduling | 100–199 Project Execution | PM; Superintendent; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.320 | Draft | schedule updates; progress; forecast; lookahead | 9.4.315; 9.4.325 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.325 | 9.4.325 – Monitor Schedule Performance | 9.4.325 – Monitor Schedule Performance | 9.4.325 | Monitor Schedule Performance | Monitor baseline vs. actual performance, document variances, and recommend corrective actions. | 4 – Construction | 150 – Scheduling | 100–199 Project Execution | PM; Superintendent; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.325 | Draft | schedule performance; variance; progress tracking | 9.4.315; 9.4.320 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.330 | 9.4.330 – Develop Schedule Recovery Plans | 9.4.330 – Develop Schedule Recovery Plans | 9.4.330 | Develop Schedule Recovery Plans | Create corrective action plans when project schedules deviate from baseline or milestones are at risk. | 4 – Construction | 150 – Scheduling | 100–199 Project Execution | PM; Superintendent; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.330 | Draft | schedule recovery; variance; corrective action; resourcing | 9.4.325; 9.2.040; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.335 | 9.4.335 – Prepare Lookahead Schedules | 9.4.335 – Prepare Lookahead Schedules | 9.4.335 | Prepare Lookahead Schedules | Prepare short-term lookahead schedules detailing upcoming work and resources to guide field activities. | 4 – Construction | 150 – Scheduling | 100–199 Project Execution | PM; Superintendent; Field Foreman |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.335 | Draft | lookahead; weekly schedule; manpower; materials | 9.4.320; 9.4.330 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.340 | 9.4.340 – Manage Resource – Loaded Schedules | 9.4.340 – Manage Resource – Loaded Schedules | 9.4.340 | Manage Resource – Loaded Schedules | Integrate labor, equipment, and materials into schedules to provide realistic forecasts and resource control. | 4 – Construction | 150 – Scheduling | 100–199 Project Execution | PM; Superintendent; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.340 | Draft | resource loading; forecasting; labor planning | 9.4.315; 9.4.335 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.345 | 9.4.345 – Conduct Schedule Review Meetings | 9.4.345 – Conduct Schedule Review Meetings | 9.4.345 | Conduct Schedule Review Meetings | Hold regular schedule review meetings to align planned activities with field progress and identify risks. | 4 – Construction | 150 – Scheduling | 100–199 Project Execution | PM; Superintendent; Field Foreman; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.345 | Draft | schedule review; progress; variance; meetings | 9.4.320; 9.4.325; 9.4.335 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.350 | 9.4.350 – Manage Schedule Change Requests | 9.4.350 – Manage Schedule Change Requests | 9.4.350 | Manage Schedule Change Requests | Evaluate, document, and process schedule change requests ensuring justification and approval tracking. | 4 – Construction | 160 – Scope & Change Control | 100–199 Project Execution | PM; Branch Manager; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.350 | Draft | schedule change; request; variance; approval | 9.4.315; 9.4.325; 9.4.330 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.355 | 9.4.355 – Manage Project Scope | 9.4.355 – Manage Project Scope | 9.4.355 | Manage Project Scope | Define, communicate, and control contractual scope to ensure alignment of execution with contract requirements. | 4 – Construction | 160 – Scope & Change Control | 100–199 Project Execution | PM; Estimator; Field Supervisor; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.355 | Draft | scope definition; contract; responsibilities | 9.2.015; 9.4.350; 9.4.365 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.360 | 9.4.360 – Manage Change Orders | 9.4.360 – Manage Change Orders | 9.4.360 | Manage Change Orders | Document, price, submit, and track all change orders to ensure contractual and financial accuracy. | 4 – Construction | 160 – Scope & Change Control | 100–199 Project Execution | PM; Estimator; Accounting; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.360 | Draft | change order; pricing; approval; billing | 9.4.205; 9.4.355; 9.4.365 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.365 | 9.4.365 – Manage Potential Change Orders (PCOs) | 9.4.365 – Manage Potential Change Orders (PCOs) | 9.4.365 | Manage Potential Change Orders (PCOs) | Identify, log, and track potential change orders before formal approval to manage risk proactively. | 4 – Construction | 160 – Scope & Change Control | 100–199 Project Execution | PM; Estimator; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.365 | Draft | PCO; tracking; pricing; risk | 9.4.360; 9.4.370; 9.4.355 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.370 | 9.4.370 – Manage Owner Directives | 9.4.370 – Manage Owner Directives | 9.4.370 | Manage Owner Directives | Document and manage all owner directives that modify or clarify scope, tracking contractual and financial impact. | 4 – Construction | 160 – Scope & Change Control | 100–199 Project Execution | PM; Estimator; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.370 | Draft | owner directive; scope change; impact; log | 9.4.365; 9.4.360; 9.4.355 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.375 | 9.4.375 – Manage Scope Clarifications | 9.4.375 – Manage Scope Clarifications | 9.4.375 | Manage Scope Clarifications | Capture, track, and communicate scope clarifications arising during design interpretation or owner discussions. | 4 – Construction | 160 – Scope & Change Control | 100–199 Project Execution | PM; Estimator; Field Supervisor; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.375 | Draft | scope clarification; interpretation; contract; RFI | 9.4.355; 9.4.365; 9.4.370 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.380 | 9.4.380 – Manage Backcharges | 9.4.380 – Manage Backcharges | 9.4.380 | Manage Backcharges | Document, track, notify, and process backcharges to subcontractors/vendors; file all records per Document Filing Standards. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Accounting; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.380 | Draft | backcharge; subcontractor; damage; corrective work; notice | 9.4.360; 9.4.290; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.385 | 9.4.385 – Manage Force Account Work | 9.4.385 – Manage Force Account Work | 9.4.385 | Manage Force Account Work | Capture T&M/force-account work outside scope; daily ticketing, signatures, and timely billing; file per SOP 9.4.190. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Field Supervisor; Accounting; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.385 | Draft | force account; T&M; tickets; billing; log | 9.4.360; 9.4.365; 9.4.380; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.390 | 9.4.390 – Manage Claims | 9.4.390 – Manage Claims | 9.4.390 | Manage Claims | Identify, prepare, and submit time/cost claims with evidence; coordinate Estimating and Legal; file per SOP 9.4.190. | 4 – Construction | 160 – Scope & Change Control | 100–199 Project Execution | PM; Estimator; Branch Manager; Legal Counsel; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.390 | Draft | claims; delays; differing conditions; entitlement; evidence | 9.4.360; 9.4.370; 9.4.385; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.400 | 9.4.400 – Monitor Project Costs | 9.4.400 – Monitor Project Costs | 9.4.400 | Monitor Project Costs | Compare actual and committed costs to budget weekly; document variances and corrective actions; file reports/logs. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Accounting; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.400 | Draft | cost monitoring; variance; weekly report | 9.2.140; 9.4.405; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.405 | 9.4.405 – Manage Cost Forecasts | 9.4.405 – Manage Cost Forecasts | 9.4.405 | Manage Cost Forecasts | Prepare monthly cost-to-complete forecasts and narratives; identify overruns/underruns; route for approval; file. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Accounting; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.405 | Draft | forecast; EAC; ETC; variance | 9.4.400; 9.2.140; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.410 | 9.4.410 – Manage Cost Codes | 9.4.410 – Manage Cost Codes | 9.4.410 | Manage Cost Codes | Standardize and maintain cost codes mapped from estimate to budget and reporting; communicate to field/accounting. | 4 – Construction | 165 – Accounting | 100–199 Project Execution | PM; Estimator; Accounting |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.410 | Draft | cost codes; mapping; master list; reporting | 9.2.140; 9.4.400 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.415 | 9.4.415 – Manage Committed Costs | 9.4.415 – Manage Committed Costs | 9.4.415 | Manage Committed Costs | Log and reconcile all POs/subcontracts against budget; maintain weekly commitment log; align with approvals. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Purchasing; Accounting; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.415 | Draft | commitments; POs; subs; log; reconciliation | 9.2.020; 9.2.140; 9.4.400 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.420 | 9.4.420 – Manage Actual Costs | 9.4.420 – Manage Actual Costs | 9.4.420 | Manage Actual Costs | Collect invoices, payroll, and receipts; verify and record actuals; investigate variances; file supporting evidence. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Accounting; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.420 | Draft | actual costs; invoices; payroll; verification | 9.4.415; 9.4.400; 9.4.425 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.425 | 9.4.425 – Manage Job Cost Reports | 9.4.425 – Manage Job Cost Reports | 9.4.425 | Manage Job Cost Reports | Prepare/distribute monthly job cost reports; compare actual/committed vs. budget; document variances for management. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Accounting; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.425 | Draft | job cost report; variance; management review | 9.4.400; 9.4.420; 9.2.140 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.430 | 9.4.430 – Manage Profit Projections | 9.4.430 – Manage Profit Projections | 9.4.430 | Manage Profit Projections | Project and analyze profitability at project and portfolio levels by comparing revenue, costs, and forecasts. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Accounting; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.430 | Draft | profit projections; variance analysis; cost forecasting | 9.4.405; 9.4.425; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.435 | 9.4.435 – Manage Cost – to – Complete | 9.4.435 – Manage Cost – to – Complete | 9.4.435 | Manage Cost – to – Complete | Calculate and monitor cost-to-complete (CTC) values for accurate forecasting of final project costs. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Accounting; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.435 | Draft | cost-to-complete; forecast; variance tracking | 9.4.405; 9.4.420; 9.4.430 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.440 | 9.4.440 – Prepare Billing Schedule | 9.4.440 – Prepare Billing Schedule | 9.4.440 | Prepare Billing Schedule | Develop a billing schedule aligned with contract terms, milestones, and project cash-flow requirements. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Accounting; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.440 | Draft | billing schedule; SOV; contract terms; milestones | 9.2.140; 9.4.445; 9.4.465 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.445 | 9.4.445 – Prepare Monthly Pay Applications | 9.4.445 – Prepare Monthly Pay Applications | 9.4.445 | Prepare Monthly Pay Applications | Prepare and submit accurate monthly pay applications with verified progress and supporting documentation. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Field Supervisor; Accounting; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.445 | Draft | pay application; progress billing; percent complete; approval | 9.4.440; 9.4.450; 9.4.460 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.450 | 9.4.450 – Track Accounts Receivable | 9.4.450 – Track Accounts Receivable | 9.4.450 | Track Accounts Receivable | Track and monitor accounts receivable to ensure timely collection of payments from owners or GCs. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | Accounting; PM; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.450 | Draft | accounts receivable; billing; collections; aging report | 9.4.445; 9.4.425; 9.4.455 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.455 | 9.4.455 – Manage Lien Waivers | 9.4.455 – Manage Lien Waivers | 9.4.455 | Manage Lien Waivers | Collect, verify, and submit lien waivers from subcontractors and vendors to maintain compliance and protect payment rights. | 4 – Construction | 160 – Scope & Change Control | 100–199 Project Execution | PM; Accounting; Subcontractors; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.455 | Draft | lien waiver; subcontractor payment; compliance | 9.4.445; 9.4.450; 9.4.465 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.460 | 9.4.460 – Manage Retainage | 9.4.460 – Manage Retainage | 9.4.460 | Manage Retainage | Track retainage withheld on pay applications and process releases at substantial completion and final closeout. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | PM; Accounting; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.460 | Draft | retainage; billing; release request; closeout | 9.4.445; 9.4.465; 9.6.010 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.465 | 9.4.465 – Manage Final Invoicing | 9.4.465 – Manage Final Invoicing | 9.4.465 | Manage Final Invoicing | Prepare and submit final invoices ensuring all closeout and contractual requirements are met. | 4 – Construction | 195 – Project Closeout | 100–199 Project Execution | PM; Accounting; Branch Manager; Subcontractors |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.465 | Draft | final invoice; closeout; retainage; lien waiver | 9.6.010; 9.4.455; 9.4.460 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.475 | 9.4.475 – Conduct Safety Orientation | 9.4.475 – Conduct Safety Orientation | 9.4.475 | Conduct Safety Orientation | Provide safety orientation for all employees and subcontractors before site access. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | Safety Coordinator; PM; Field Supervisor |  | Safety | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.475 | Draft | safety orientation; training; attendance log; compliance | 9.3.470; 9.4.165; 9.4.480 | Safety | 2025-10-10 | 2026-10-10 | SOP
9.4.480 | 9.4.480 – Conduct Safety Inspections | 9.4.480 – Conduct Safety Inspections | 9.4.480 | Conduct Safety Inspections | Perform scheduled and unscheduled safety inspections to identify hazards, ensure compliance, and document corrective actions. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | Safety Coordinator; Field Supervisor; Project Manager; Branch Manager |  | Safety | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.480 | Draft | safety inspection; OSHA; hazard identification; compliance | 9.3.470; 9.4.485; 9.4.505 | Safety | 2025-10-10 | 2026-10-10 | SOP
9.4.485 | 9.4.485 – Conduct Safety Meetings | 9.4.485 – Conduct Safety Meetings | 9.4.485 | Conduct Safety Meetings | Conduct weekly toolbox talks and monthly formal safety meetings to communicate policies, hazards, and corrective actions. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | Safety Coordinator; Project Manager; Field Supervisor |  | Safety | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.485 | Draft | safety meeting; toolbox talk; attendance; training | 9.4.480; 9.4.490; 9.4.495 | Safety | 2025-10-10 | 2026-10-10 | SOP
9.4.490 | 9.4.490 – Report Safety Incidents | 9.4.490 – Report Safety Incidents | 9.4.490 | Report Safety Incidents | Report all safety incidents, including near misses and injuries, promptly and in compliance with OSHA and company policy. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | All Employees; Field Supervisor; Safety Coordinator; Project Manager |  | Safety | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.490 | Draft | incident report; near miss; injury; notification | 9.4.495; 9.4.480; 9.4.500 | Safety | 2025-10-10 | 2026-10-10 | SOP
9.4.495 | 9.4.495 – Investigate Accidents | 9.4.495 – Investigate Accidents | 9.4.495 | Investigate Accidents | Investigate accidents and near misses to determine root cause, develop corrective actions, and comply with regulations. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | Safety Coordinator; Project Manager; Field Supervisor; Branch Manager |  | Safety | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.495 | Draft | accident investigation; root cause; corrective action | 9.4.490; 9.4.480; 9.4.505 | Safety | 2025-10-10 | 2026-10-10 | SOP
9.4.500 | 9.4.500 – Conduct Emergency Preparedness | 9.4.500 – Conduct Emergency Preparedness | 9.4.500 | Conduct Emergency Preparedness | Develop and maintain emergency preparedness procedures, conduct drills, and ensure personnel are trained. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | Safety Coordinator; Project Manager; Field Supervisor; All Employees |  | Safety | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.500 | Draft | emergency plan; drills; EAP; evacuation | 9.3.470; 9.4.495; 9.4.505 | Safety | 2025-10-10 | 2026-10-10 | SOP
9.4.505 | 9.4.505 – Conduct Safety Compliance Audits | 9.4.505 – Conduct Safety Compliance Audits | 9.4.505 | Conduct Safety Compliance Audits | Perform quarterly safety compliance audits to verify adherence to OSHA, contractual, and company standards. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | Branch Manager; Safety Coordinator; Project Manager |  | Safety | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.505 | Draft | safety audit; compliance; corrective actions | 9.4.480; 9.4.495; 9.4.500 | Safety | 2025-10-10 | 2026-10-10 | SOP
9.4.510 | 9.4.510 – Provide Safety Training | 9.4.510 – Provide Safety Training | 9.4.510 | Provide Safety Training | Deliver and document required safety training for employees and subcontractors to meet OSHA and company standards. | 4 – Construction | 193 – Safety Mgmt | 100–199 Project Execution | Safety Coordinator; HR; Project Manager; Field Supervisor |  | Safety | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.510 | Draft | safety training; attendance log; competency | 9.4.475; 9.4.485; 9.4.500 | Safety | 2025-10-10 | 2026-10-10 | SOP
9.4.515 | 9.4.515 – Develop Quality Management Plan | 9.4.515 – Develop Quality Management Plan | 9.4.515 | Develop Quality Management Plan | Create a project-specific Quality Management Plan defining standards, inspections, and acceptance criteria. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | Project Manager; Quality Inspector; Field Supervisor; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.515 | Draft | quality plan; QMP; inspection and test plan; ITP | 9.4.520; 9.4.525; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.520 | 9.4.520 – Conduct Quality Meetings | 9.4.520 – Conduct Quality Meetings | 9.4.520 | Conduct Quality Meetings | Hold regular quality meetings to review inspection results, nonconformance items, and corrective actions. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | Project Manager; Quality Inspector; Field Supervisor; Subcontractors |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.520 | Draft | quality meetings; NCR; corrective action log | 9.4.515; 9.4.525 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.525 | 9.4.525 – Conduct Quality Inspections | 9.4.525 – Conduct Quality Inspections | 9.4.525 | Conduct Quality Inspections | Perform inspections to verify work complies with specifications, QMP, and quality standards. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | Quality Inspector; Project Manager; Field Supervisor; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.525 | Draft | quality inspection; ITP; deficiency tracking; audit | 9.4.520; 9.4.515; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.530 | 9.4.530 – Manage Quality Testing | 9.4.530 – Manage Quality Testing | 9.4.530 | Manage Quality Testing | Perform and document quality testing in accordance with project specifications, codes, and standards. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | PM; Quality Inspector; Testing Agency; Field Supervisor |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.530 | Draft | testing; inspection; quality control; reports | 9.4.515; 9.4.525; 9.4.540 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.535 | 9.4.535 – Manage Nonconformance Reports (NCRs) | 9.4.535 – Manage Nonconformance Reports (NCRs) | 9.4.535 | Manage Nonconformance Reports (NCRs) | Identify, document, and resolve nonconforming work in a consistent and traceable manner. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | Quality Inspector; PM; Field Supervisor; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.535 | Draft | nonconformance; NCR; corrective action; quality | 9.4.525; 9.4.530; 9.4.540 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.540 | 9.4.540 – Manage Quality Records | 9.4.540 – Manage Quality Records | 9.4.540 | Manage Quality Records | Maintain and archive quality records that demonstrate compliance with project and contractual requirements. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | PM; Site Administrator; Quality Inspector |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.540 | Draft | quality records; documentation; archiving | 9.4.535; 9.4.515; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.545 | 9.4.545 – Manage Punch List Quality | 9.4.545 – Manage Punch List Quality | 9.4.545 | Manage Punch List Quality | Ensure punch list items are corrected and verified for quality compliance prior to project closeout. | 4 – Construction | 195 – Project Closeout | 100–199 Project Execution | PM; Field Supervisor; Subcontractors; Quality Inspector |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.545 | Draft | punch list; corrective actions; quality verification | 9.4.525; 9.4.540; 9.6.020 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.560 | 9.4.560 – Manage Manpower Allocation | 9.4.560 – Manage Manpower Allocation | 9.4.560 | Manage Manpower Allocation | Allocate manpower efficiently to meet project schedule and productivity requirements. | 4 – Construction | 192 – Labor Management | 100–199 Project Execution | PM; Superintendent; Field Supervisor; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.560 | Draft | manpower allocation; labor forecast; staffing | 9.4.335; 9.4.340; 9.4.565 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.560 | 9.4.560 – Manage Subcontractor Resources | 9.4.560 – Manage Subcontractor Resources | 9.4.560 | Manage Subcontractor Resources | Coordinate and track subcontractor manpower, equipment, and materials to align with project schedules. | 4 – Construction | 180 – Subcontractor Management | 100–199 Project Execution | PM; Field Supervisor; Subcontractors; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.575 | Draft | subcontractor resources; manpower; tracking; coordination | 9.4.155; 9.4.560; 9.4.565 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.565 | 9.4.565 – Manage Equipment Allocation | 9.4.565 – Manage Equipment Allocation | 9.4.565 | Manage Equipment Allocation | Allocate and maintain equipment resources across projects for availability and cost efficiency. | 4 – Construction | 191 – Tools Management | 100–199 Project Execution | PM; Superintendent; Equipment Manager; Field Supervisor |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.565 | Draft | equipment allocation; tracking; maintenance; usage logs | 9.4.560; 9.4.340; 9.4.570 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.570 | 9.4.570 – Manage Material Allocation | 9.4.570 – Manage Material Allocation | 9.4.570 | Manage Material Allocation | Manage allocation and delivery of materials to ensure timely availability and minimize waste. | 4 – Construction | 190 – Materials Management | 100–199 Project Execution | PM; Purchasing; Field Supervisor; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.570 | Draft | material allocation; delivery; logistics; forecasting | 9.4.565; 9.4.560; 9.2.010 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.575 | 9.4.575 – Manage Feeder Wire Release | 9.4.575 – Manage Feeder Wire Release | 9.4.575 | Manage Feeder Wire Release |  | 4 – Construction | 190 – Materials Mgmt | 100–199 Project Execution | Field Supervisor; Foremen; Project Manager; Site Administrator |  | Operations | 1 | 2025-10-10 | Field Leadership | Project Manager | nan | Draft | nan | 9.2.020 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.580 | 9.4.580 – Manage Vendor Resources | 9.4.580 – Manage Vendor Resources | 9.4.580 | Manage Vendor Resources | Coordinate vendor-provided resources (materials, deliveries, and technical support) to ensure timely project execution. | 4 – Construction | 190 – Materials Management | 100–199 Project Execution | PM; Purchasing; Vendors; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.580 | Draft | vendor resources; deliveries; procurement; tracking | 9.2.020; 9.4.605; 9.4.625 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.585 | 9.4.585 – Plan Prefabrication Resources | 9.4.585 – Plan Prefabrication Resources | 9.4.585 | Plan Prefabrication Resources | Plan prefabrication labor, space, tools, and materials to optimize efficiency and reduce jobsite congestion. | 4 – Construction | 190 – Materials Management | 100–199 Project Execution | PM; Prefab Manager; Field Supervisor; Purchasing |  | Prefab | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.585 | Draft | prefabrication planning; resources; shop schedules | 9.2.080; 9.4.565; 9.4.570 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.590 | 9.4.590 – Manage Specialty Contractor Resources | 9.4.590 – Manage Specialty Contractor Resources | 9.4.590 | Manage Specialty Contractor Resources | Coordinate specialty contractor resources (e.g., fire alarm, controls, low voltage) to ensure integration with overall project plan. | 4 – Construction | 180 – Subcontractor Management | 100–199 Project Execution | PM; Field Supervisor; Specialty Contractors; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.590 | Draft | specialty contractor; coordination; resources | 9.4.155; 9.4.575; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.595 | 9.4.595 – Prepare Resource Reports | 9.4.595 – Prepare Resource Reports | 9.4.595 | Prepare Resource Reports | Prepare weekly and monthly reports summarizing manpower, equipment, material, and subcontractor usage. | 4 – Construction | 192 – Labor Management | 100–199 Project Execution | PM; Superintendent; Site Administrator; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.595 | Draft | resource report; labor; equipment; tracking | 9.4.560; 9.4.565; 9.4.570; 9.4.575 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.605 | 9.4.605 – Issue Purchase Orders | 9.4.605 – Issue Purchase Orders | 9.4.605 | Issue Purchase Orders | Prepare and issue purchase orders for materials and equipment to ensure cost compliance and delivery coordination. | 4 – Construction | 170 – Cost Control & Billing | 100–199 Project Execution | Purchasing; PM; Accounting; Vendors |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.605 | Draft | purchase order; vendor confirmation; log | 9.4.415; 9.2.160; 9.4.620 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.610 | 9.4.610 – Manage Vendor Prequalification | 9.4.610 – Manage Vendor Prequalification | 9.4.610 | Manage Vendor Prequalification | Prequalify vendors and suppliers based on financial stability, safety, and performance criteria before use. | 4 – Construction | 180 – Subcontractor Management | 100–199 Project Execution | Purchasing; PM; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.610 | Draft | vendor prequalification; review; approval | 9.4.615; 9.4.605; 9.4.580 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.615 | 9.4.615 – Manage Vendor Evaluations | 9.4.615 – Manage Vendor Evaluations | 9.4.615 | Manage Vendor Evaluations | Evaluate vendor performance on quality, timeliness, and cost after project completion and log results for future use. | 4 – Construction | 180 – Subcontractor Management | 100–199 Project Execution | PM; Purchasing; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.615 | Draft | vendor evaluation; performance review; rating | 9.4.610; 9.4.580; 9.4.620 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.620 | 9.4.620 – Manage Expediting | 9.4.620 – Manage Expediting | 9.4.620 | Manage Expediting | Monitor vendor and supplier production to ensure timely delivery of critical materials and equipment. | 4 – Construction | 190 – Materials Management | 100–199 Project Execution | Purchasing; PM; Vendors; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.620 | Draft | expediting; delivery tracking; vendor status | 9.4.605; 9.4.625; 9.4.580 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.625 | 9.4.625 – Manage Delivery Tracking | 9.4.625 – Manage Delivery Tracking | 9.4.625 | Manage Delivery Tracking | Track deliveries to verify schedule compliance and record receipt condition and issues for resolution. | 4 – Construction | 190 – Materials Management | 100–199 Project Execution | Purchasing; PM; Field Supervisor; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.625 | Draft | delivery tracking; packing slips; BOL; condition reports | 9.4.620; 9.4.580; 9.4.415 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.630 | 9.4.630 – Manage Material Receiving | 9.4.630 – Manage Material Receiving | 9.4.630 | Manage Material Receiving | Verify materials received on-site for accuracy, quality, and compliance with purchase orders; log and file records per SOP 190A. | 4 – Construction | 190 – Materials Management | 100–199 Project Execution | Field Supervisor; Project Manager; Purchasing; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.630 | Draft | receiving; inspection; packing slips; BOL; delivery verification | 9.4.625; 9.4.570; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.631 | 9.4.631 – Release of Large Feeder Wire | 9.4.631 – Release of Large Feeder Wire | 9.4.631 | Release of Large Feeder Wire | [6 empty] | Operations
9.4.635 | 9.4.635 – Manage Material Inspection | 9.4.635 – Manage Material Inspection | 9.4.635 | Manage Material Inspection | Inspect delivered materials for compliance with submittals and specifications before installation; quarantine non-conforming items. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | Quality Inspector; Field Supervisor; Project Manager; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.635 | Draft | material inspection; quality; NCR; submittal verification | 9.4.530; 9.4.630; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.640 | 9.4.640 – Manage Storage and Logistics | 9.4.640 – Manage Storage and Logistics | 9.4.640 | Manage Storage and Logistics | Plan and manage on-site storage and logistics to ensure protection and accessibility of materials and equipment. | 4 – Construction | 190 – Materials Management | 100–199 Project Execution | Project Manager; Field Supervisor; Warehouse Staff; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.640 | Draft | storage; logistics; laydown; protection | 9.4.060; 9.4.570; 9.4.630 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.645 | 9.4.645 – Manage Material Handling | 9.4.645 – Manage Material Handling | 9.4.645 | Manage Material Handling | Handle materials safely and efficiently on-site to minimize waste, damage, and productivity loss; maintain handling logs. | 4 – Construction | 190 – Materials Management | 100–199 Project Execution | Field Supervisor; Warehouse Staff; Project Manager; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.645 | Draft | material handling; tracking; damage control; lifting plans | 9.4.060; 9.4.640; 9.4.570 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.650 | 9.4.650 – Manage Inventory | 9.4.650 – Manage Inventory | 9.4.650 | Manage Inventory | Maintain accurate inventory of materials, tools, and equipment to ensure availability and accountability. | 4 – Construction | 191 – Tools Management | 100–199 Project Execution | Project Manager; Field Supervisor; Site Administrator; Purchasing |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.650 | Draft | inventory; tracking; stock levels; reconciliation | 9.4.640; 9.4.645; 9.4.570 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.655 | 9.4.655 – Prepare Procurement Reports | 9.4.655 – Prepare Procurement Reports | 9.4.655 | Prepare Procurement Reports | Prepare weekly and monthly procurement reports summarizing commitments, deliveries, and open issues. | 4 – Construction | 165 – Accounting | 100–199 Project Execution | Purchasing; Project Manager; Branch Manager; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.655 | Draft | procurement reports; POs; tracking; commitments | 9.4.600; 9.4.605; 9.4.650 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.660 | 9.4.660 – Manage Procurement Closeout | 9.4.660 – Manage Procurement Closeout | 9.4.660 | Manage Procurement Closeout | Close all procurement activities ensuring POs, deliveries, and invoices are complete and reconciled. | 4 – Construction | 165 – Accounting | 100–199 Project Execution | Project Manager; Purchasing; Accounting; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.660 | Draft | procurement closeout; invoice reconciliation; PO tracking | 9.4.465; 9.4.655; 9.4.650 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.665 | 9.4.665 – Reconcile Procurement Accounts | 9.4.665 – Reconcile Procurement Accounts | 9.4.665 | Reconcile Procurement Accounts | Reconcile procurement accounts ensuring commitments, invoices, and payments are matched and closed. | 4 – Construction | 165 – Accounting | 100–199 Project Execution | Accounting; Project Manager; Purchasing; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.665 | Draft | account reconciliation; procurement; cost control | 9.4.395; 9.4.420; 9.4.660 | Accounting | 2025-10-10 | 2026-10-10 | SOP
9.4.670 | 9.4.670 – Manage Vendor Closeout | 9.4.670 – Manage Vendor Closeout | 9.4.670 | Manage Vendor Closeout | Formally close vendor accounts verifying completion of deliveries, documentation, and payments. | 4 – Construction | 180 – Subcontractor Management | 100–199 Project Execution | Purchasing; Project Manager; Accounting; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.670 | Draft | vendor closeout; performance review; final payment | 9.4.610; 9.4.615; 9.4.660; 9.4.665 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.675 | 9.4.675 – Conduct Daily Huddles | 9.4.675 – Conduct Daily Huddles | 9.4.675 | Conduct Daily Huddles | Lead daily field huddles to communicate work plans, safety hazards, and coordination updates; document attendance. | 4 – Construction | 120 – Coordination | 100–199 Project Execution | Field Supervisor; Foremen; Project Manager; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.675 | Draft | daily huddles; coordination; communication; safety | 9.4.165; 9.4.335; 9.4.560 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.680 | 9.4.680 – Conduct Weekly Foreman Meetings | 9.4.680 – Conduct Weekly Foreman Meetings | 9.4.680 | Conduct Weekly Foreman Meetings | Conduct weekly meetings with foremen to review schedule, manpower, coordination, and site logistics. | 4 – Construction | 120 – Coordination | 100–199 Project Execution | PM; Field Supervisor; Foremen; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.680 | Draft | foreman meetings; coordination; schedule review; manpower | 9.4.150; 9.4.335; 9.4.675 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.690 | 9.4.690 – Track Manpower Utilization | 9.4.690 – Track Manpower Utilization | 9.4.690 | Track Manpower Utilization | Track and report daily manpower usage by trade to evaluate labor efficiency and identify variances. | 4 – Construction | 192 – Labor Management | 100–199 Project Execution | Field Supervisor; PM; Site Administrator; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.690 | Draft | manpower utilization; tracking; efficiency; variance | 9.4.560; 9.4.595; 9.4.690 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.695 | 9.4.695 – Track Production Quantities | 9.4.695 – Track Production Quantities | 9.4.695 | Track Production Quantities | Track production quantities daily to measure progress and productivity against plan and budget. | 4 – Construction | 192 – Labor Management | 100–199 Project Execution | Field Supervisor; PM; Foremen; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.695 | Draft | production tracking; productivity; installed work; variance | 9.4.690; 9.4.400; 9.4.595 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.700 | 9.4.700 – Track Equipment Utilization | 9.4.700 – Track Equipment Utilization | 9.4.700 | Track Equipment Utilization | Monitor and record daily equipment usage, idle time, and availability for accurate cost tracking and resource planning. | 4 – Construction | 191 – Tools Management | 100–199 Project Execution | Field Supervisor; Equipment Manager; PM; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.700 | Draft | equipment utilization; idle time; maintenance; allocation | 9.4.565; 9.4.595; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.705 | 9.4.705 – Manage Work Packaging | 9.4.705 – Manage Work Packaging | 9.4.705 | Manage Work Packaging | Break project scope into manageable work packages for efficient execution and accountability. | 4 – Construction | 192 – Labor Management | 100–199 Project Execution | PM; Field Supervisor; Foremen; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.705 | Draft | work packaging; scope definition; assignments; tracking | 9.2.070; 9.4.335; 9.4.695 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.710 | 9.4.710 – Manage Workface Planning | 9.4.710 – Manage Workface Planning | 9.4.710 | Manage Workface Planning | Ensure readiness for upcoming field tasks by verifying drawings, materials, and manpower prior to work start. | 4 – Construction | 192 – Labor Management | 100–199 Project Execution | PM; Field Supervisor; Foremen; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.710 | Draft | workface planning; readiness; materials; lookahead | 9.4.705; 9.4.335; 9.4.675 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.715 | 9.4.715 – Manage Field Coordination | 9.4.715 – Manage Field Coordination | 9.4.715 | Manage Field Coordination | Coordinate daily field activities among crews and subcontractors to prevent conflicts and ensure sequencing. | 4 – Construction | 120 – Coordination | 100–199 Project Execution | PM; Field Supervisor; Subcontractors; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.715 | Draft | field coordination; sequencing; daily check-ins; conflict resolution | 9.4.150; 9.4.680; 9.4.705 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.720 | 9.4.720 – Conduct Productivity Analysis | 9.4.720 – Conduct Productivity Analysis | 9.4.720 | Conduct Productivity Analysis | Analyze field productivity weekly by comparing actual labor and production data against planned values. | 4 – Construction | 192 – Labor Management | 100–199 Project Execution | PM; Field Supervisor; Accounting; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.720 | Draft | productivity analysis; variance; cost control; labor efficiency | 9.4.690; 9.4.695; 9.4.400 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.725 | 9.4.725 – Resolve Field Problems | 9.4.725 – Resolve Field Problems | 9.4.725 | Resolve Field Problems | Identify and resolve field issues promptly to prevent rework, delays, or safety incidents. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | Field Supervisor; PM; Quality Inspector; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.725 | Draft | field problems; corrective action; NCR; issue log | 9.4.205; 9.4.715; 9.4.535 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.735 | 9.4.735 – Perform Field Quality Verifications | 9.4.735 – Perform Field Quality Verifications | 9.4.735 | Perform Field Quality Verifications | Perform ongoing field quality verifications to ensure work meets drawings, specifications, and submittals. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | Field Supervisor; Quality Inspector; Project Manager; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.735 | Draft | field quality verification; inspection; deficiency tracking | 9.4.525; 9.4.535; 9.4.720 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.4.745 | 9.4.745 – Manage Field Rework | 9.4.745 – Manage Field Rework | 9.4.745 | Manage Field Rework | Identify, authorize, track, verify, and document field rework to reduce cost/schedule impacts and prevent recurrence. | 4 – Construction | 194 – Quality Control | 100–199 Project Execution | Project Manager; General Superintendent; Foreman; QA/QC |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | 9.41.745 | Draft | field rework, quality, deficiency, punch list, nonconformance, NCR, corrective action, root cause analysis, rework log, photos, schedule impact, daily reports, timecards, cost codes, productivity, changed conditions, RFI, COR, change order, authorization, QA/QC verification, closeout, documentation filing | Document Filing Standards; Nonconformance Reporting; Corrective Action; Change Management | Field Operations / Project Management / Quality | 2026-01-07 | 2027-01-07 | SOP
9.4.755 | 9.4.755 – Implement Field Productivity Improvements | 9.4.755 – Implement Field Productivity Improvements | 9.4.755 | Implement Field Productivity Improvements | Identify, implement, and monitor productivity improvement measures in field operations. | 4 – Construction | 192 – Labor Management | 100–199 Project Execution | Project Manager; Field Supervisor; Foremen; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.755 | Draft | productivity improvement; prefab; efficiency; workflow | 9.4.720; 9.4.695; 9.4.585 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.5.015 | 9.5.015 – Conduct Commissioning Meetings | 9.5.015 – Conduct Commissioning Meetings | 9.5.015 | Conduct Commissioning Meetings | Coordinate commissioning meetings to plan and verify system testing and turnover. | 5 – Testing & Commissioning | 195 – Project Closeout | 100–199 Project Execution | PM; Commissioning Agent; Subcontractors; Quality Inspector |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.180 | Draft | commissioning; startup; testing; handover | 9.4.060 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.5.020 | 9.5.020 – Handling and or Disposing of Excess Materials | 9.5.020 – Handling and or Disposing of Excess Materials | 9.5.020 | Handling and or Disposing of Excess Materials |  | 5 – Project Closeout | 194 – Project Closeout | 100–199 Project Execution |  |  | Operations
9.5.550 | 9.5.550 – Manage Commissioning Activities | 9.5.550 – Manage Commissioning Activities | 9.5.550 | Manage Commissioning Activities | Coordinate and manage commissioning activities for systems and equipment to ensure performance meets contract requirements. | 5 – Testing & Commissioning | 194 – Quality Control | 100–199 Project Execution | PM; Commissioning Agent; Subcontractors; Quality Inspector |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.550 | Draft | commissioning; systems testing; verification; functional tests | 9.4.515; 9.4.530; 9.4.545 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.005 | 9.6.005 – Prepare for Turnover (Field Perspective) | 9.6.005 – Prepare for Turnover (Field Perspective) | 9.6.005 | Prepare for Turnover (Field Perspective) | Prepare field operations for turnover by ensuring punch lists, as-builts, and corrective actions are completed and verified. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | Field Supervisor; Foremen; Project Manager; Quality Inspector |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.760 | Draft | turnover readiness; punch list; as-builts; verification | 9.4.545; 9.6.010; 9.4.555 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.010 | 9.6.010 – Conduct Closeout Meetings | 9.6.010 – Conduct Closeout Meetings | 9.6.010 | Conduct Closeout Meetings | Conduct closeout meetings with the project team, subcontractors, and client to verify punch-list completion and documentation prior to turnover. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | PM; Field Supervisor; Subcontractors; Client/Owner |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.185 | Draft | closeout; punch list; O&M; warranty; turnover | 9.4.060; 9.5.010 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.020 | 9.6.020 – Manage Punch List Closeout | 9.6.020 – Manage Punch List Closeout | 9.6.020 | Manage Punch List Closeout | Complete and verify punch list items before project turnover. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | Project Manager; Field Supervisor; Quality Inspector; Subcontractors |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.770 | Draft | punch list closeout; verification; owner sign-off | 9.4.545; 9.6.005; 9.6.010 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.030 | 9.6.030 – Manage As – Built Drawings | 9.6.030 – Manage As – Built Drawings | 9.6.030 | Manage As – Built Drawings | Maintain accurate red-line and final as-built drawings reflecting field changes for owner submission. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | PM; Field Supervisor; Subcontractors; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.250 | Draft | as-builts; drawings; redlines; field changes | 9.4.220; 9.6.020 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.030 | 9.6.035 – Submit Warranties | 9.6.035 – Submit Warranties | 9.6.035 | Submit Warranties | Collect, verify, and submit warranties to the Owner/GC as part of project turnover documentation. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | Project Manager; Site Administrator; Subcontractors; Vendors |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.775 | Draft | warranty collection; turnover; owner acceptance | 9.6.020; 9.4.555; 9.4.260 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.040 | 9.6.040 – Submit O&M Manuals | 9.6.040 – Submit O&M Manuals | 9.6.040 | Submit O&M Manuals | Collect, review, and submit operations & maintenance manuals for owner acceptance. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | PM; Subcontractors; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.255 | Draft | O&M; manuals; submittals; closeout | 9.6.030; 9.6.050 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.050 | 9.6.050 – Manage Warranties | 9.6.050 – Manage Warranties | 9.6.050 | Manage Warranties | Collect, log, and submit warranty certificates per contract requirements. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | PM; Subcontractors; Site Administrator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.260 | Draft | warranty; log; certificates; owner package | 9.6.040; 9.6.060 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.050 | 9.6.050 – Provide Owner Training | 9.6.050 – Provide Owner Training | 9.6.050 | Provide Owner Training | Provide Owner training on systems and equipment to ensure proper operation and maintenance after turnover. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | Project Manager; Vendors; Subcontractors; Site Administrator; Owner Rep |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.785 | Draft | owner training; commissioning; operations; maintenance | 9.5.550; 9.6.030; 9.6.040 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.060 | 9.6.060 – Manage Closeout Documentation | 9.6.060 – Manage Closeout Documentation | 9.6.060 | Manage Closeout Documentation | Compile, review, and submit final closeout documentation for client acceptance. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | PM; Site Administrator; Subcontractors; Owner/Client |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.265 | Draft | closeout docs; turnover; checklist; owner package | 9.6.030; 9.6.040; 9.6.050 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.065 | 9.6.065 – Archive Project Documentation | 9.6.065 – Archive Project Documentation | 9.6.065 | Archive Project Documentation | Archive all project documentation for future reference, audits, and warranty compliance. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | Project Manager; Site Administrator; Branch Manager |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.790 | Draft | archive; records retention; Procore; closeout | 9.6.030; 9.6.040; 9.6.050 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.070 | 9.6.070 – Conduct Post – Project Review | 9.6.070 – Conduct Post – Project Review | 9.6.070 | Conduct Post – Project Review | Conduct a formal review of project performance to capture lessons learned and continuous-improvement actions. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | Project Manager; Branch Manager; Executive Management |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.795 | Draft | post-project review; lessons learned; performance evaluation | 9.4.400; 9.4.430; 9.6.060 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.080 | 9.6.080 – Capture Client Feedback | 9.6.080 – Capture Client Feedback | 9.6.080 | Capture Client Feedback | Collect and analyze client feedback at project completion to evaluate satisfaction and identify improvements. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | Project Manager; Branch Manager; Business Development |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.800 | Draft | client feedback; survey; satisfaction; lessons learned | 9.6.070; 9.6.085; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP
9.6.085 | 9.6.085 – Document Lessons Learned | 9.6.085 – Document Lessons Learned | 9.6.085 | Document Lessons Learned | Capture and document lessons learned from each project to support continuous improvement and knowledge sharing. | 6 – Project Closeout | 195 – Project Closeout | 100–199 Project Execution | Project Manager; Branch Manager; Quality Coordinator |  | Operations | 1 | 2025-10-10 | Project Management | Executive Committee | Formerly 9.41.805 | Draft | lessons learned; continuous improvement; knowledge base | 9.6.070; 9.6.080; 9.4.190 | Operations | 2025-10-10 | 2026-10-10 | SOP

## Sheet2
| Management Directives |  | Job Descriptions
Position | Policy Manual, 9.2 Management Directives | File Path | Policy Manual, 7.2 Job Descriptions | File Path
Apprentice | Policy Manual, 9.2 Management Directives for Field Employees | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.2 Management Directives for Field Employees.doc | Policy Manual, 7.2.1 Apprentice Electrician | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.2.1 Apprentice Electrician.doc
Journeyman | Policy Manual, 9.2 Management Directives for Field Employees | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.2 Management Directives for Field Employees.doc | Policy Manual, 7.2.2 Journeyman Electrician | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.2.2 Journeyman Electrician.doc
Leadman | Policy Manual, 9.3 Management Directives for Field Leadership | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.3 Management Directives for Field Leadership.doc | Policy Manual, 7.2.3 Lead Journeyman | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.2.3 Lead Journeyman.doc
Foreman | Policy Manual, 9.3 Management Directives for Field Leadership | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.3 Management Directives for Field Leadership.doc | Policy Manual, 7.2.4 Foreman | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.2.4 Foreman.doc
Project Superintendent (General Foreman) | Policy Manual, 9.3 Management Directives for Field Leadership | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.3 Management Directives for Field Leadership.doc | Policy Manual, 7.2.5 Project Superintendent (General Foreman) | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.2.5 Project Superintendent (General Foreman).doc
Safety Coordinator |  |  | Policy Manual, 7.2.6 Project Safety Coordinator | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.2.6 Project Safety Coordinator.doc
Branch Safety Superintendent |  |  | Policy Manual, 7.4.6 Safety and Loss Control | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.6 Safety and Loss Control.doc
General Superintendents | Policy Manual, 9.4 Management Directives for General Superintendents | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.4 Management Directives for General Superintendents.doc | Policy Manual, 7.3.1 Operations Management | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.1 Operations Management.doc
Branch Manager | Policy Manual, 9.6 Management Directives for Branch Management | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.6 Management Directives for Branch Management.doc | Policy Manual, 7.3.1 Operations Management | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.1 Operations Management.doc
Contract Managers | Policy Manual, 9.14 Management Directives for Contract Managers | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.14 Management Directives for Contract Managers.doc | Policy Manual, 7.3.1 Operations Management | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.1 Operations Management.doc
Project Manager | Policy Manual, 9.5 Management Directives for Project Management | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.5 Management Directives for Project Management.doc | Policy Manual, 7.3.1 Operations Management | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.1 Operations Management.doc
Assitant Project Manager | Policy Manual, 9.5 Management Directives for Project Management | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.5 Management Directives for Project Management.doc | Policy Manual, 7.3.1 Operations Management | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.1 Operations Management.doc
Project Coordinator | Policy Manual, 9.5 Management Directives for Project Management | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.5 Management Directives for Project Management.doc | Policy Manual, 7.3.1 Operations Management | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.1 Operations Management.doc
Business Development |  |  | Policy Manual, 7.3.2 Business Development | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.2 Business Development.doc
Estimating | Policy Manual, 9.7 Management Directives for Estimating | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.7 Management Directives for Estimating.doc | Policy Manual, 7.3.3 Estimating | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.3 Estimating.doc
LEVEL I ESTIMATOR ASSISTANT | Policy Manual, 9.7 Management Directives for Estimating | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.7 Management Directives for Estimating.doc | Policy Manual, 7.3.3 Estimating | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.3 Estimating.doc
LEVEL II INTERMEDIATE ESTIMATOR | Policy Manual, 9.7 Management Directives for Estimating | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.7 Management Directives for Estimating.doc | Policy Manual, 7.3.3 Estimating | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.3 Estimating.doc
LEVEL III LEAD ESTIMATOR | Policy Manual, 9.7 Management Directives for Estimating | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.7 Management Directives for Estimating.doc | Policy Manual, 7.3.3 Estimating | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.3 Estimating.doc
CAD and REVIT Operators | Policy Manual, 9.8 Management Directives for Design Build | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.8 Management Directives for Design Build.mht | Policy Manual, 7.3.4 Engineering - Design | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.4 Engineering - Design.doc
ENGINEERING / DESIGN Estimators | Policy Manual, 9.8 Management Directives for Design Build | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.8 Management Directives for Design Build.mht | Policy Manual, 7.3.4 Engineering - Design | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.4 Engineering - Design.doc
Designers | Policy Manual, 9.8 Management Directives for Design Build | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.8 Management Directives for Design Build.mht | Policy Manual, 7.3.4 Engineering - Design | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.4 Engineering - Design.doc
Engineers | Policy Manual, 9.8 Management Directives for Design Build | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.8 Management Directives for Design Build.mht | Policy Manual, 7.3.4 Engineering - Design | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.4 Engineering - Design.doc
LV Estimator |  |  | Policy Manual, 7.3.5 Low Voltage Systems | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.5 Low Voltage Systems.doc
LV Project Manager |  |  | Policy Manual, 7.3.5 Low Voltage Systems | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.5 Low Voltage Systems.doc
LV Department Manager |  |  | Policy Manual, 7.3.5 Low Voltage Systems | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.5 Low Voltage Systems.doc
LV Assistant Projects Manager |  |  | Policy Manual, 7.3.5 Low Voltage Systems | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.5 Low Voltage Systems.doc
LV Project Coordinator |  |  | Policy Manual, 7.3.5 Low Voltage Systems | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.5 Low Voltage Systems.doc
SP Estimator |  |  | Policy Manual, 7.3.6 Special Projects | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.6 Special Projects.doc
SP Project Manager |  |  | Policy Manual, 7.3.6 Special Projects | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.6 Special Projects.doc
SP Department Manager |  |  | Policy Manual, 7.3.6 Special Projects | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.6 Special Projects.doc
SP Assistant Projects Manager |  |  | Policy Manual, 7.3.6 Special Projects | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.6 Special Projects.doc
SP Project Coordinator |  |  | Policy Manual, 7.3.6 Special Projects | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.6 Special Projects.doc
Line Worker |  |  | Policy Manual, 7.3.7 Pre-Fabrication | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.7 Pre-Fabrication.doc
Shop Foreman |  |  | Policy Manual, 7.3.7 Pre-Fabrication | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.7 Pre-Fabrication.doc
Pre-Construction Manager |  |  | Policy Manual, 7.3.7 Pre-Fabrication | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.7 Pre-Fabrication.doc
Human Resource Manager |  |  | Policy Manual, 7.4.1 Human Resource Manager | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.1 Human Resource Manager.doc
Benefits Manager |  |  | Policy Manual, 7.4.2 Benefits Manager | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.2 Benefits Manager.doc
Payroll Manager |  |  | Policy Manual, 7.4.3 Payroll Manager | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.3 Payroll Manager.doc
Purchasing Agent | Policy Manual, 9.16 Management Directives for Purchasing | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.16 Management Directives for Purchasing.docx | Policy Manual, 7.4.4.1 Purchasing Agent | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.4.1 Purchasing Agent (Salt Lake Office).doc
Warehouse Assistant |  |  | Policy Manual, 7.4.4.2 Warehouse Assistant | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.4.2 Warehouse Assistant (Salt Lake Office).doc
Administrative Support |  |  | Policy Manual, 7.4.5 Administrative Support | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.5 Administrative Support.doc
Safety Director |  |  | Policy Manual, 7.4.6 Safety and Loss Control | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.6 Safety and Loss Control.doc
CEO |  |  | Policy Manual, 7.4.7 Corporate Officers | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.7 Corporate Officers.doc
CFO |  |  | Policy Manual, 7.4.7.3 Chief Operations Officer | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.7.3 Chief Operations Officer.docx
COO |  |  | Policy Manual, 7.4.7 Corporate Officers | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3.1 Operations Management.doc
President |  |  | Policy Manual, 7.4.7 Corporate Officers | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.7 Corporate Officers.doc
Board of Directors |  |  | Policy Manual, 7.4.8 Board of Directors | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.8 Board of Directors.doc
Accounting GL Manager |  |  | Policy Manual, 7.5 Accounting GL Manager | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.5 Accounting GL Manager.doc
Business Manager | Policy Manual, 9.9 Management Directives - Continued | C:\Users\tewing\Documents\openai_test\Management Directives\Policy Manual, 9.9 Management Directives - Continued.doc | Policy Manual, 7.3 Operations Office Positions | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.3 Operations Office Positions.doc
PURCHASING MANAGER |  |  | Policy Manual, 7.4.4 Purchasing Manager | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4.4 Purchasing Manager (Salt Lake Office).doc
Marketing Manager |  |  | Policy Manual, 7.4 Business Administration | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4 Business Administration.doc
IT Manager |  |  | Policy Manual, 7.4 Business Administration | C:\Users\tewing\Documents\openai_test\Job Descriptions\Policy Manual, 7.4 Business Administration.doc

## Coverage Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category
9.2.010 – Team Selection | PM defines staffing needs | Project Manager | Sec. 9.5 PM (manpower plan) | ✔ Covered | No change required. | Team selection and turnover
9.2.010 – Team Selection | GS assigns field supervisors | General Superintendent | Sec. 9.4 GS (manpower assignment) | ✔ Covered | No change required. | Team selection and turnover
9.2.010 – Team Selection | Branch Manager approves staffing plan | Branch Manager | Sec. 9.6 Branch Mgmt (operations control) | ⚠ Gap – approval not explicit | Add approval language to Sec. 9.6. | Team selection and turnover
9.2.010 – Team Selection | Safety Coordinator advises on assignments | Safety Coordinator | Sec. 7.2.6 JD (safety hazard identification) | ⚠ Gap – advisory role not explicit | Add cross-check with Safety Coordinator. | Team selection and turnover
9.2.015 – Project Turnover Meeting | Conduct estimator-led turnover meeting | Estimator | Sec. 9.7 Estimating (turnover participation) | ✔ Covered | No change required. | Team selection and turnover
9.2.015 – Project Turnover Meeting | Participate in turnover meeting | PM, Branch Mgr, GS, Field Leadership, Prefab, Safety | Sec. 9.5 PM (turnover), Sec. 9.13 BM, Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Team selection and turnover
9.2.015 – Project Turnover Meeting | Prepare meeting agenda and minutes | Project Manager | Sec. 9.5 PM (meeting leadership) | ⚠ Gap – agenda/minutes not required | Add to Sec. 9.5: PM must issue minutes within 48 hrs. | Team selection and turnover
9.2.020 - Procurement of Large Feeder Wire | Populate Feeder Wire Procurement & Release Log upon NOA/LOI and confirm feeder details with field team. | Project Manager | Sec. 9.5 PM (procurement planning); Sec. 9.16 Purchasing | ⚠ Gap – feeder log use not explicit | Add requirement for Feeder Wire Procurement & Release Log to Sec. 9.5 PM (procurement planning). | Materials Management
9.2.020 - Procurement of Large Feeder Wire | Issue RFQs and obtain 2+ documented vendor quotes for large feeder wire. | Purchasing | Sec. 9.16 Purchasing (pre-buyout procurement) | ⚠ Gap – competitive quote documentation not explicit | Update Sec. 9.16 Purchasing to require at least two documented quotes for large feeder wire purchases. | Materials Management
9.2.020 - Procurement of Large Feeder Wire | Select vendor and set PO terms including pricing lock, lead times, and delivery conditions for feeder wire. | Project Manager | Sec. 9.5 PM (procurement planning); Sec. 9.16 Purchasing | ✔ Covered | No change required. | Materials Management
9.2.020 - Procurement of Large Feeder Wire | Assemble and submit feeder wire submittals; hold releases until submittal approval. | Project Manager | Sec. 9.5 PM (submittals management) | ✔ Covered | No change required. | Materials Management
9.2.020 - Procurement of Large Feeder Wire | Pre-plan logistics and conduit/wire pull schedule with Field Supervision using BOM and scaled drawings. | Project Manager | Sec. 9.5 PM (material handling plan); Sec. 9.3 Field Leadership (pre-planning) | ✔ Covered | No change required. | Materials Management
9.2.020 - Procurement of Large Feeder Wire | Direct vendors to store wire until release, cut and bundle feeders per releases, and bill upon release. | Purchasing | Sec. 9.16 Purchasing (commodities and wire procurement) | ⚠ Gap – storage, release, and billing conditions not defined | Update Sec. 9.16 Purchasing to define storage at vendor warehouse, release after submittal approval, bundling expectations, and billing upon release for large feeder wire. | Materials Management
9.2.030 – Review Contract for High-Risk Clauses | Review contract for unfavorable clauses | Project Manager | Sec. 9.5 PM (contract review) | ✔ Covered | No change required. | Scope and contract review
9.2.030 – Review Contract for High-Risk Clauses | Escalate risks and prepare mitigation plan | PM, Branch Manager | Sec. 9.14 Contract Mgr (risk oversight), Sec. 9.13 BM (contracts) | ⚠ Gap – mitigation plan not explicit | Add checklist/mitigation step. | Scope and contract review
9.2.040 – PM Reviews Plans, Specs & Schedule | Review drawings, specs, and schedules | Project Manager | Sec. 9.5 PM (scope & schedule review) | ✔ Covered | No change required. | Scope and contract review
9.2.040 – PM Reviews Plans, Specs & Schedule | Complete Scope & Schedule Checklist | Project Manager | Not explicit in directives | ⚠ Gap – checklist requirement | Add checklist reference to Sec. 9.5. | Scope and contract review
9.2.040 – PM Reviews Plans, Specs & Schedule | Integrate results into PEP | Project Manager | Sec. 7.3.1 PM JD (planning & PEP) | ⚠ Gap – explicit PEP update not required | Add to PM JD/Directive 9.5. | Scope and contract review
9.2.050 – FS Reviews Plans, Specs & Schedule | Review drawings/specs/schedules for constructability | Field Supervisor | Sec. 9.3 Field Leadership (pre-planning) | ✔ Covered | No change required. | Scope and contract review
9.2.050 – FS Reviews Plans, Specs & Schedule | Submit findings to PM & GS | Field Supervisor | Sec. 9.3 Field Leadership (reporting to PM/GS) | ✔ Covered | No change required. | Scope and contract review
9.2.050 – FS Reviews Plans, Specs & Schedule | Integrate findings into PEP | Project Manager | Sec. 9.5 PM (job planning) | ⚠ Gap – PEP update not explicit | Add to Sec. 9.5: PM integrates FS findings. | Scope and contract review
9.2.060 – Create Issue List & RFI | Identify constructability/scope issues | Field Supervisor | Sec. 9.3 Field Leadership (report issues) | ✔ Covered | No change required. | Scope and contract review
9.2.060 – Create Issue List & RFI | Maintain RFI log | Project Manager | Sec. 9.5 PM (document scope changes) | ✔ Covered | No change required. | Scope and contract review
9.2.060 – Create Issue List & RFI | Escalate major issues to Branch Manager | PM & GS | Sec. 9.14 Contract Mgr (notice requirements) | ⚠ Gap – escalation step not explicit | Add escalation language to Sec. 9.5. | Scope and contract review
9.2.070 – Conduct Site Visit | Perform site walk & complete checklist | Field Leadership (Project Superintendent/Foreman) | Management Directives for Field Leadership – Pre-planning | ✔ Covered | No change required. | Scope and contract review
9.2.070 – Conduct Site Visit | Integrate findings into PEP | Project Manager | Project Manager JD – planning, meetings, and site visits | ✔ Covered | No change required (SOP updated to include PEP integration). | Scope and contract review
9.2.070 – Conduct Site Visit | Identify site-specific hazards | Safety Coordinator | Management Directives – PPE mandatory; Field Leadership objectives (quality/safety) | ✔ Covered | No change required. | Scope and contract review
9.2.070 – Conduct Site Visit | Review manpower/logistics implications | General Superintendent | Management Directives – Pre-planning with PM | ✔ Covered | No change required. | Scope and contract review
9.2.055 – Compare Est. vs. Planned | Provide bid documentation | Estimator | Sec. 9.7 Estimating (bid package review) | ✔ Covered | No change required. | Budget preparation
9.2.055 – Compare Est. vs. Planned | Compare assumptions vs. execution plan | Project Manager | Sec. 9.5 PM (job plan updates) | ✔ Covered | No change required. | Budget preparation
9.2.055 – Compare Est. vs. Planned | Validate manpower implications | General Superintendent | Sec. 9.4 GS (workforce oversight) | ✔ Covered | No change required. | Budget preparation
9.2.055 – Compare Est. vs. Planned | Validate budget alignment | Branch Manager | Sec. 9.6 Branch Mgmt (budget alignment) | ✔ Covered | No change required. | Budget preparation
9.2.057 – VE & Prefab | Facilitate identification of VE/prefab opportunities | Project Manager | Sec. 9.5 PM (prefabrication planning) | ✔ Covered | No change required. | Buyout process
9.2.057 – VE & Prefab | Develop prefab strategy sheet | Prefabrication Lead | Sec. 7.3.7 Prefab JD (prefab strategy) | ✔ Covered | No change required. | Buyout process
9.2.057 – VE & Prefab | Validate constructability/feasibility | Field Supervisor | Sec. 9.3 Field Leadership (field feasibility) | ✔ Covered | No change required. | Buyout process
9.2.057 – VE & Prefab | Confirm VE proposals align with budget | Estimator | Sec. 9.7 Estimating (VE options) | ✔ Covered | No change required. | Buyout process
9.2.057 – VE & Prefab | Record opportunities in VE log | Project Manager | Not explicit in directives | ⚠ Gap – VE log not required | Add VE log requirement in Sec. 9.5. | Buyout process
9.1.050 – Construction Takeoff | Generate detailed material/labor quantities | Project Manager | Sec. 9.5 PM (buyout planning) | ✔ Covered | No change required. | Buyout process
9.1.050 – Construction Takeoff | Provide bid takeoff for reference | Estimator | Sec. 9.7 Estimating (bid takeoff) | ✔ Covered | No change required. | Buyout process
9.1.050 – Construction Takeoff | Review constructability & logistics accuracy | Field Supervisor | Sec. 9.3 Field Leadership (constructability review) | ✔ Covered | No change required. | Buyout process
9.1.050 – Construction Takeoff | Use results for vendor negotiations & procurement | Purchasing | Sec. 9.16 Purchasing (pre-buyout procurement) | ✔ Covered | No change required. | Buyout process
9.1.050 – Construction Takeoff | Finalize & upload takeoff results | Project Manager | Not explicit in directives | ⚠ Gap – upload requirement | Add takeoff upload requirement to Sec. 9.5. | Buyout process
9.2.020 – Procurement of Large Feeder Wire | Prepare BOM & conduit/wire pull schedule | Project Manager | Sec. 9.5 PM (procurement planning); Sec. 9.16 Purchasing | ✔ Covered | No change required. | Buyout process
9.2.020 – Procurement of Large Feeder Wire | Validate lengths and reel assignments | Foreman / Field Supervisor | Sec. 9.3 Field Leadership (materials validation) | ✔ Covered | No change required. | Buyout process
9.2.020 – Procurement of Large Feeder Wire | Confirm manpower/logistics feasibility | General Superintendent | Sec. 9.4 GS (manpower coordination) | ✔ Covered | No change required. | Buyout process
9.2.020 – Procurement of Large Feeder Wire | Approve submittals before release | Project Manager | Not explicit in directives | ⚠ Gap – submittal approval requirement | Add to Sec. 9.5: PM must verify submittals before release. | Buyout process
9.2.080 – Material Handling Plan | Develop logistics plan for delivery/staging | Field Supervisor | Sec. 9.3 Field Leadership (staging/logistics) | ✔ Covered | No change required. | Material handling plan
9.2.080 – Material Handling Plan | Align with procurement & project schedule | Project Manager | Sec. 9.5 PM (logistics, procurement alignment) | ✔ Covered | No change required. | Material handling plan
9.2.080 – Material Handling Plan | Review safety compliance of handling plan | Safety Coordinator | Sec. 7.2.6 JD (safety review) | ✔ Covered | No change required. | Material handling plan
9.2.090 – Develop Labor Budget | Develop detailed labor forecast | Project Manager | Sec. 9.5 PM (labor planning) | ✔ Covered | No change required. | Budget preparation
9.2.090 – Develop Labor Budget | Validate manpower feasibility | General Superintendent | Sec. 9.4 GS (workforce oversight) | ✔ Covered | No change required. | Budget preparation
9.2.090 – Develop Labor Budget | Provide labor assumptions from bid | Estimator | Sec. 9.7 Estimating (labor assumptions) | ✔ Covered | No change required. | Budget preparation
9.2.090 – Develop Labor Budget | Approve labor budget | Branch Manager | Sec. 9.6 Branch Mgmt (budget oversight) | ✔ Covered | No change required. | Budget preparation
9.2.100 – Layout & Sequencing Plan | Develop sequencing plan & integrate into PEP | Project Manager | Sec. 9.5 PM (planning, scheduling) | ✔ Covered | No change required. | Layout and sequencing plan
9.2.100 – Layout & Sequencing Plan | Review constructability & sequencing feasibility | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Layout and sequencing plan
9.2.100 – Layout & Sequencing Plan | Confirm manpower allocations & critical path | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Layout and sequencing plan
9.2.100 – Layout & Sequencing Plan | Identify safety risks in layout/sequencing | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Layout and sequencing plan
9.2.110 – Develop Project Schedule | Develop baseline schedule | Project Manager | Sec. 9.5 PM (schedule ownership) | ✔ Covered | No change required. | Schedule development
9.2.110 – Develop Project Schedule | Validate manpower phasing feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Schedule development
9.2.110 – Develop Project Schedule | Confirm long-lead procurement dates | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Schedule development
9.2.110 – Develop Project Schedule | Approve baseline schedule | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Schedule development
9.2.120 – Tracking & Control Systems | Establish tracking templates/logs | Project Manager | Sec. 9.5 PM (reporting systems) | ✔ Covered | No change required. | Tracking and control
9.2.120 – Tracking & Control Systems | Report daily manpower/progress | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Tracking and control
9.2.120 – Tracking & Control Systems | Maintain procurement log | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Tracking and control
9.2.120 – Tracking & Control Systems | Submit safety inspection reports | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Tracking and control
9.2.120 – Tracking & Control Systems | Review weekly reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Tracking and control
9.2.130 – Kickoff Meeting | Organize & lead kickoff | Project Manager | Sec. 9.5 PM (turnover/kickoff) | ✔ Covered | No change required. | Construction execution kickoff meeting
9.2.130 – Kickoff Meeting | Confirm manpower/sequence feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Construction execution kickoff meeting
9.2.130 – Kickoff Meeting | Review site logistics | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Construction execution kickoff meeting
9.2.130 – Kickoff Meeting | Provide procurement/delivery updates | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Construction execution kickoff meeting
9.2.130 – Kickoff Meeting | Present safety plan | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Construction execution kickoff meeting
9.2.130 – Kickoff Meeting | Provide branch-level oversight | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Construction execution kickoff meeting
9.3.010 – Office Trailer | Secure trailer & utilities setup | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization
9.3.010 – Office Trailer | Setup furniture & documentation systems | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Mobilization
9.3.010 – Office Trailer | Confirm location/logistics feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Mobilization
9.3.010 – Office Trailer | Ensure phone/internet operational | IT/Communications | Sec. 7.4 Business Admin JD (IT) | ✔ Covered | No change required. | Mobilization
9.3.020 – Storage Trailer | Approve trailer placement | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization
9.3.020 – Storage Trailer | Setup shelving & inventory control | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.020 – Storage Trailer | Verify compliance with fire/access standards | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.3.030 – Fencing & Access Control | Approve fencing & access plan | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization
9.3.030 – Fencing & Access Control | Oversee fence/gate installation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.030 – Fencing & Access Control | Verify safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.3.030 – Fencing & Access Control | Monitor access control | Security Personnel | Not explicit in directives | ⚠ Gap – role not formalized | Add security monitoring responsibility to Sec. 9.5. | Mobilization
9.3.040 – Setup Temporary Power | Coordinate power requirements with utility/owner | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization
9.3.040 – Setup Temporary Power | Oversee installation & verify distribution | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.040 – Setup Temporary Power | Install panels/wiring/grounding | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization
9.3.040 – Setup Temporary Power | Verify OSHA/NEC compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.3.050 – Setup Temporary Water | Coordinate utility connection | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization
9.3.050 – Setup Temporary Water | Oversee installation/distribution | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.050 – Setup Temporary Water | Verify safety/environmental compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.3.060 – Setup Sanitary Facilities | Contract vendors for sanitary facilities | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization
9.3.060 – Setup Sanitary Facilities | Determine placement & logistics | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.060 – Setup Sanitary Facilities | Maintain inspection log | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.3.070 – Setup Temporary Lighting | Approve lighting plan & budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.3.070 – Setup Temporary Lighting | Oversee installation & verify coverage | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.070 – Setup Temporary Lighting | Install temporary lighting | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization
9.3.070 – Setup Temporary Lighting | Inspect OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.3.080 – Setup Signage | Determine signage requirements | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.3.080 – Setup Signage | Install signage | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.080 – Setup Signage | Ensure OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.3.090 – Setup Security | Approve security plan & vendors | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.3.090 – Setup Security | Implement physical security | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.090 – Setup Security | Daily monitoring of access points | Security Personnel | Not explicit in directives | ⚠ Gap – security personnel not formalized | Add security responsibilities to Sec. 9.5. | Mobilization
9.3.090 – Setup Security | Ensure plan aligns with safety | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.3.100 – Setup Laydown Area | Approve laydown area location | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.3.100 – Setup Laydown Area | Setup & manage laydown area | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.100 – Setup Laydown Area | Verify safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.3.110 – Setup Equipment Staging | Approve staging location | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.3.110 – Setup Equipment Staging | Direct equipment setup | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.110 – Setup Equipment Staging | Position equipment safely | Equipment Operators | Not explicit in directives | ⚠ Gap – equipment operator role not formalized | Add operator role into mobilization directive. | Mobilization
9.3.110 – Setup Equipment Staging | Verify OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.3.120 – Setup Parking | Approve parking plan | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.3.120 – Setup Parking | Establish parking areas | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.3.120 – Setup Parking | Verify traffic safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.4.010 – Coordination Meetings | Schedule & chair coordination meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination
9.4.010 – Coordination Meetings | Provide field updates & issues | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination
9.4.010 – Coordination Meetings | Record minutes & action items | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Coordination
9.4.010 – Coordination Meetings | Provide design clarifications | Design Team / Consultants | Not explicit in directives | ⚠ Gap – design consultant role not formalized | Add consultant clarification role to Sec. 9.5. | Coordination
9.4.020 – Subcontractor Meetings | Prepare and distribute subcontractor agenda | Project Manager | Sec. 9.5 PM (coordination) | ✔ Covered | No change required. | Coordination
9.4.020 – Subcontractor Meetings | Provide progress/manpower updates | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor reporting requirements. | Coordination
9.4.020 – Subcontractor Meetings | Report logistics needs | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination
9.4.020 – Subcontractor Meetings | Review safety performance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.4.030 – Client Meetings | Lead client/owner meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination
9.4.030 – Client Meetings | Provide executive oversight | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Coordination
9.4.030 – Client Meetings | Approve changes/raise concerns | Client/Owner | Not in directives | ⚠ Gap | Owner role external to GSL; clarify interface protocols. | Coordination
9.4.040 – Safety Meetings | Prepare/lead safety meetings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.4.040 – Safety Meetings | Ensure scheduling and attendance | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.4.040 – Safety Meetings | Reinforce safety in daily huddles | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.4.040 – Safety Meetings | Participate in meetings | All Employees | Not in directives | ⚠ Gap | Include participation expectation in JD handbook. | Safety Management
9.4.050 – Prefab Meetings | Schedule/facilitate prefab meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination
9.4.050 – Prefab Meetings | Provide prefab schedules/deliverables | Prefab Lead | Sec. 7.3.7 Prefab JD | ✔ Covered | No change required. | Coordination
9.4.050 – Prefab Meetings | Validate constructability feasibility | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination
9.4.050 – Prefab Meetings | Confirm manpower sequencing | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management
9.4.060 – Quality Meetings | Schedule/facilitate meetings, track actions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Quality Control
9.4.060 – Quality Meetings | Report quality issues | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Quality Control
9.4.060 – Quality Meetings | Review quality inspections | Quality Inspector | Not in directives | ⚠ Gap | Add inspector responsibilities into QA directive. | Quality Control
9.4.060 – Quality Meetings | Confirm overlap with safety | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.5.010 – Commissioning Meetings | Schedule/facilitate commissioning | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination
9.5.010 – Commissioning Meetings | Define testing requirements | Commissioning Agent | Not in directives | ⚠ Gap | Add commissioning agent scope reference. | Quality Control
9.5.010 – Commissioning Meetings | Provide documentation/manpower | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor commissioning duties. | Coordination
9.5.010 – Commissioning Meetings | Ensure commissioning compliance | Quality Inspector | Not in directives | ⚠ Gap | Add QA/QC commissioning accountability. | Quality Control
9.6.010 – Closeout Meetings | Schedule and lead closeout meeting | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Project Closeout
9.6.010 – Closeout Meetings | Verify completion of punch list | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project Closeout
9.6.010 – Closeout Meetings | Submit closeout docs | Subcontractors | Not in directives | ⚠ Gap | Include subcontractor closeout requirements. | Project Closeout
9.6.010 – Closeout Meetings | Confirm acceptance of deliverables | Client/Owner | Not in directives | ⚠ Gap | Owner external – clarify acceptance protocols. | Project Closeout
9.4.190 – Document Filing Standards | Set up project folder structure using the standard template (Procore + Windows). | Site Administrator | Document Control – | ✔ Covered |  | Documentation Management
9.4.190 – Document Filing Standards | Apply file/folder naming conventions and character rules consistently. | Project Engineer / APM | Document Control – | ✔ Covered |  | Documentation Management
9.4.190 – Document Filing Standards | File incoming/outgoing project documents to the correct system and folder (by document type). | Field Foreman | Document Control – | ✔ Covered |  | Documentation Management
9.4.190 – Document Filing Standards | Maintain version control: keep current docs current and move superseded versions to archive. | Site Administrator | Document Control – | ✔ Covered |  | Documentation Management
9.4.190 – Document Filing Standards | Issue updated drawings/submittals to field and confirm latest versions are accessible. | Project Manager | Document Control – | ✔ Covered |  | Documentation Management
9.4.190 – Document Filing Standards | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Branch Manager | Document Control – | ✔ Covered |  | Documentation Management
9.4.190 – Document Filing Standards | At closeout, compile and archive the final documentation package per closeout requirements. | Project Manager | Project Closeout | ✔ Covered |  | Documentation Management
9.4.195 – Documentation System | Ensure compliance with filing standards | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management
9.4.195 – Documentation System | Organize folders & verify consistency | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management
9.4.195 – Documentation System | Audit system compliance | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Documentation Management
9.4.200 – Submittals | Prepare submittal log & ensure timely submissions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management
9.4.200 – Submittals | Coordinate vendor submittals | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Documentation Management
9.4.200 – Submittals | Provide shop drawings/product data | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor submittal duties. | Documentation Management
9.4.300 – A/E Communications | Issue RFIs and receive design clarifications | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Communication
9.4.300 – A/E Communications | Identify conflicts and escalate | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Communication
9.4.300 – A/E Communications | Log A/E communications | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management
9.4.310 – GC Communications | Lead communications with GC | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Communication
9.4.310 – GC Communications | Escalate field directives | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Communication
9.4.310 – GC Communications | Log GC correspondence | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management
9.4.315 – Develop Project Schedule | Develop baseline schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.4.320 – Update Project Schedule | Update project schedule with progress | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.4.320 – Update Project Schedule | Provide weekly progress | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Scheduling
9.4.325 – Monitor Schedule Performance | Prepare performance reports | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.4.325 – Monitor Schedule Performance | Verify progress in field | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management
9.4.330 – Recovery Plans | Develop recovery strategies | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.4.330 – Recovery Plans | Approve recovery plans | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control
9.4.335 – Lookahead Schedules | Prepare weekly lookaheads | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.4.335 – Lookahead Schedules | Confirm sequencing | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management
9.4.335 – Lookahead Schedules | Use lookahead for crew planning | Field Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management
9.4.340 – Resource-Loaded Schedules | Integrate resources into schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.4.340 – Resource-Loaded Schedules | Confirm resource availability | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management
9.4.340 – Resource-Loaded Schedules | Review resource forecasts | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Materials Management
9.4.345 – Schedule Review Meetings | Prepare agenda and lead meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.4.345 – Schedule Review Meetings | Provide field updates | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Scheduling
9.4.345 – Schedule Review Meetings | Confirm crew availability | Field Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management
9.4.345 – Schedule Review Meetings | Approve mitigation strategies | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Coordination
9.4.205 – RFIs | Subcontractors required to draft/support RFIs | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor RFI responsibilities to directives. | Scope & Change Control
9.4.210 – Meeting Minutes | Minutes responsibility clarity | Site Administrator | Not explicit in directives | ⚠ Gap | Explicitly assign Site Admin responsibility for meeting minutes. | Communication
9.4.215 – Daily Reports | Foremen/Subcontractors required to submit daily reports | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor daily report requirement. | Labor Management
9.4.220 – Drawing Logs | Subcontractors to submit updated drawings | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor drawing log submission. | Documentation Management
9.4.225 – Specifications | Subcontractor input on spec compliance | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor compliance review of specs. | Documentation Management
9.4.230 – Correspondence | Subcontractors required to provide written correspondence trail | Subcontractors | Not explicit in directives | ⚠ Gap | Include subcontractor correspondence duty. | Communication
9.4.235 – Permits | Authority responsibility for inspections | Regulatory Authorities | External role | ⚠ Gap | Clarify external agency responsibility protocol. | Safety Management
9.4.240 – Inspections | Subcontractors must close open deficiencies | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor inspection compliance duties. | Quality Control
9.6.020 – Punch Lists | Subcontractors provide completion evidence | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor punch list responsibilities. | Project Closeout
9.4.315 – Develop Schedule | Superintendent role not explicit in directives | Superintendent | Not explicit in directives | ⚠ Gap | Clarify Superintendent role in directive 9.4 for schedule input. | Scheduling
9.4.330 – Recovery Plans | Superintendent adjustments not explicit | Superintendent | Not explicit in directives | ⚠ Gap | Add Superintendent labor/equipment adjustment duties. | Scheduling
9.4.340 – Resource-Loaded | Foreman role missing for crew-level validation | Field Foreman | Not explicit in directives | ⚠ Gap | Add Foreman resource feedback duty. | Labor Management
9.4.345 – Schedule Review Meetings | Consultant participation not explicit | Consultants | Not explicit in directives | ⚠ Gap | Add consultant role in review meetings if applicable. | Coordination
9.4.350 – Schedule Change Requests | Review schedule change requests | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.4.350 – Schedule Change Requests | Approve/reject requests | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scheduling
9.4.350 – Schedule Change Requests | Log requests | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty to maintain change request log. | Documentation Management
9.4.355 – Project Scope | Define and control project scope | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.4.355 – Project Scope | Approve scope adjustments | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control
9.4.360 – Change Orders | Prepare CO documentation | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.4.360 – Change Orders | Review CO costs | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing
9.4.360 – Change Orders | Approve COs before submission | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control
9.4.360 – Change Orders | Maintain CO log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for CO logs. | Documentation Management
9.4.365 – PCOs | Identify and document potential COs | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.4.365 – PCOs | Provide cost backup | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing
9.4.370 – Owner Directives | Implement and log directives | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.4.370 – Owner Directives | Review directives for cost/schedule impact | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control
9.4.375 – Scope Clarifications | Identify and clarify scope gaps | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.4.375 – Scope Clarifications | Provide bid data for clarifications | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Scope & Change Control
9.4.380 – Backcharges | Approve backcharges | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.380 – Backcharges | Process financial impacts | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for backcharge tracking. | Cost Control & Billing
9.4.385 – Force Account Work | Authorize force account work | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.4.385 – Force Account Work | Track labor/equipment/materials | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management
9.4.385 – Force Account Work | Process billing | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for force account billing. | Cost Control & Billing
9.4.385 – Force Account Work | File and log records | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for FA logs. | Documentation Management
9.4.390 – Claims | Identify/prepare claims | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.4.390 – Claims | Provide cost/time analysis | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing
9.4.390 – Claims | Approve claims | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control
9.4.390 – Claims | Assist with disputes | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role. | Scope & Change Control
9.4.390 – Claims | Maintain claim log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for claim logs. | Documentation Management
9.2.140 – Project Budget | Prepare project budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.2.140 – Project Budget | Provide bid/estimate backup | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing
9.2.140 – Project Budget | Review/input budget | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to record project budget. | Cost Control & Billing
9.2.140 – Project Budget | Approve budget | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.400 – Monitor Project Costs | Monitor project costs vs. budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.400 – Monitor Project Costs | Validate cost reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.400 – Monitor Project Costs | Maintain detailed cost tracking | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for cost monitoring. | Cost Control & Billing
9.4.405 – Manage Cost Forecasts | Prepare updated cost forecasts | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.405 – Manage Cost Forecasts | Provide backup and adjustments | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting responsibility for forecast inputs. | Cost Control & Billing
9.4.410 – Manage Cost Codes | Assign and maintain cost codes | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.410 – Manage Cost Codes | Ensure alignment with company standards | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to align cost codes with financial systems. | Cost Control & Billing
9.4.415 – Manage Committed Costs | Review purchase orders & contracts | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Materials Management
9.4.415 – Manage Committed Costs | Approve commitments | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.415 – Manage Committed Costs | Maintain records | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for committed cost records. | Cost Control & Billing
9.4.420 – Manage Actual Costs | Track invoices and payroll | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting role for actual costs. | Cost Control & Billing
9.4.420 – Manage Actual Costs | Validate costs against budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.425 – Manage Job Cost Reports | Prepare monthly job cost reports | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.425 – Manage Job Cost Reports | Validate reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.425 – Manage Job Cost Reports | Provide accounting input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for job cost reports. | Cost Control & Billing
9.4.430 – Manage Profit Projections | Prepare profit projections | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.430 – Manage Profit Projections | Review projections | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.430 – Manage Profit Projections | Verify financial data | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify data for projections. | Cost Control & Billing
9.4.435 – Manage Cost-to-Complete | Update cost-to-complete projections | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.435 – Manage Cost-to-Complete | Validate projections | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.435 – Manage Cost-to-Complete | Provide actual data input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for actuals in cost-to-complete. | Cost Control & Billing
9.4.440 – Prepare Billing Schedule | Prepare billing schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.440 – Prepare Billing Schedule | Review billing schedule | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.440 – Prepare Billing Schedule | Confirm owner agreement | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for billing schedule. | Communication
9.4.445 – Monthly Pay Applications | Prepare pay application package | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.445 – Monthly Pay Applications | Review and approve pay apps | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.445 – Monthly Pay Applications | Provide invoices/payment records | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to provide records for pay apps. | Cost Control & Billing
9.4.445 – Monthly Pay Applications | Approve payment | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for pay applications. | Communication
9.4.450 – Track Accounts Receivable | Track AR aging and follow up on collections | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to maintain AR aging and collections follow-up. | Cost Control & Billing
9.4.450 – Track Accounts Receivable | Review AR status and escalate non-payment | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.450 – Track Accounts Receivable | Approve escalation actions for delinquent accounts | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.455 – Manage Lien Waivers | Collect executed lien waivers from subs/vendors | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management
9.4.455 – Manage Lien Waivers | Track lien waivers and verify with pay apps | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to track lien waivers with pay apps. | Documentation Management
9.4.455 – Manage Lien Waivers | Maintain lien waiver log | Site Administrator | Not explicit in directives | ⚠ Gap | Assign Site Admin to maintain lien waiver log. | Documentation Management
9.4.455 – Manage Lien Waivers | Provide executed lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor submission of lien waivers before payment. | Documentation Management
9.4.460 – Manage Retainage | Track retainage withheld and prepare release requests | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.460 – Manage Retainage | Verify amounts withheld and released | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify retainage withheld/released. | Cost Control & Billing
9.4.460 – Manage Retainage | Approve final retainage release | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.465 – Manage Final Invoicing | Prepare final invoice and ensure supporting docs complete | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.4.465 – Manage Final Invoicing | Review final invoice and submit for payment | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to review and submit final invoice. | Cost Control & Billing
9.4.465 – Manage Final Invoicing | Approve final invoice prior to release | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.4.465 – Manage Final Invoicing | Submit final pay apps and lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor final pay apps and lien waivers. | Cost Control & Billing
9.3.470 – Site-Specific Safety Plan | Draft and maintain SSSP | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.3.470 – Site-Specific Safety Plan | Review and approve SSSP | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.3.470 – Site-Specific Safety Plan | Audit SSSP for compliance | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management
9.3.470 – Site-Specific Safety Plan | Implement SSSP in field operations | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.4.475 – Safety Orientation | Conduct orientation sessions and maintain records | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.4.475 – Safety Orientation | Ensure all personnel complete orientation before work | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.4.475 – Safety Orientation | Verify crew participation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.4.480 – Safety Inspections | Conduct inspections and document findings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.4.480 – Safety Inspections | Correct hazards identified during inspections | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.4.480 – Safety Inspections | Review reports and ensure corrective action | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.4.480 – Safety Inspections | Audit safety inspection process | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management
9.4.485 – Safety Meetings | Prepare agenda and conduct meetings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.4.485 – Safety Meetings | Ensure meetings are held as scheduled | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.4.485 – Safety Meetings | Reinforce safety policies with crews | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.4.490 – Report Safety Incidents | Complete official incident report and submit | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.4.490 – Report Safety Incidents | Document initial details and notify PM/Safety | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.4.490 – Report Safety Incidents | Review and escalate incidents as required | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.4.490 – Report Safety Incidents | Submit report to Branch Manager within 24 hrs | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.4.495 – Investigate Accidents | Lead investigation and document findings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.4.495 – Investigate Accidents | Support investigation and implement corrective actions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.4.495 – Investigate Accidents | Provide incident details and ensure crew cooperation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.4.495 – Investigate Accidents | Review investigation and approve corrective measures | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management
9.4.495 – Investigate Accidents | Advise on legal implications as needed | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role in accident investigations. | Safety Management
9.6.070 – Conduct Post-Project Review | Schedule post-project review and invite project and branch stakeholders. | Project Manager | Sec. 9.5 PM (project closeout) | ⚠ Gap – formal review meeting not defined | Add explicit requirement for a post-project review meeting in Sec. 9.5 PM closeout section. | Project Closeout
9.6.070 – Conduct Post-Project Review | Prepare performance data (safety, schedule, cost, quality) and project documentation for review. | Project Manager | Sec. 9.5 PM (job monitoring and reporting) | ✔ Covered | No change required. | Project Closeout
9.6.070 – Conduct Post-Project Review | Lead review discussion of outcomes, successes, and improvement opportunities. | Branch Manager | Sec. 9.6 Branch Mgmt (operations oversight) | ✔ Covered | No change required. | Project Closeout
9.6.070 – Conduct Post-Project Review | Document post-project review outcomes in a summary report and file per SOP 9.4.190. | Project Manager | Sec. 9.5 PM (project documentation); SOP 9.4.190 | ✔ Covered | No change required. | Project Closeout
9.6.080 – Capture Client Feedback | Issue client feedback survey and/or interview request at project completion. | Project Manager | Sec. 9.5 PM (client relations at closeout) | ⚠ Gap – structured client feedback not defined | Amend Sec. 9.5 PM to require a standard client feedback survey or interview at closeout. | Project Closeout
9.6.080 – Capture Client Feedback | Conduct client feedback interview and clarify satisfaction, issues, and improvement ideas. | Project Manager | Sec. 9.5 PM (client relations at closeout) | ⚠ Gap – formal closeout interview not specified | Clarify in Sec. 9.5 PM that PM should conduct a closeout feedback interview when practical. | Project Closeout
9.6.080 – Capture Client Feedback | Review client feedback, prepare summary, and share with Branch Manager and Business Development. | Business Development | Business Development directives (client relationship management) | ⚠ Gap – BD feedback handling not documented | Create or update BD directives to assign responsibility for analyzing client feedback and updating client records. | Project Closeout
9.6.080 – Capture Client Feedback | Approve client feedback summary and incorporate into branch/market strategy. | Branch Manager | Sec. 9.6 Branch Mgmt (client relations and quality) | ✔ Covered | No change required. | Project Closeout
9.6.085 – Document Lessons Learned | Collect lessons learned input from project team, subcontractors, and stakeholders. | Project Manager | Sec. 9.5 PM (project closeout and improvement) | ⚠ Gap – structured lessons-learned process not defined | Add requirement in Sec. 9.5 PM for the PM to gather lessons learned at project closeout. | Project Closeout
9.6.085 – Document Lessons Learned | Review and validate lessons learned for accuracy, risk, and applicability. | Branch Manager | Sec. 9.6 Branch Mgmt (operations oversight) | ✔ Covered | No change required. | Project Closeout
9.6.085 – Document Lessons Learned | Enter approved lessons learned into the company knowledge base or tracking system. | Quality Coordinator | Quality / continuous improvement directives | ⚠ Gap – knowledge base ownership not documented | Create or update Quality/CI directives assigning responsibility for maintaining lessons-learned knowledge base. | Project Closeout
9.6.085 – Document Lessons Learned | Share key lessons learned with future project teams and leadership forums. | Quality Coordinator | Sec. 7.3 Operations Office Positions (knowledge sharing expectations) | ⚠ Gap – formal lessons sharing mechanism not defined | Define standard channels (PM meetings, training, communications) for distributing lessons learned. | Project Closeout
9.5.010 – Handling and/or Disposing of Excess Materials | Use 3-week lookahead to plan and request materials and order roughly 1–3 weeks of stock. | Field Supervisor | Sec. 9.3 Field Leadership (pre-planning) | ⚠ Gap – explicit 3-week material planning not defined | Add guidance in Sec. 9.3 Field Leadership to use the 3-week lookahead to plan material needs and limit orders to roughly 1–3 weeks of work. | Materials Management
9.5.010 – Handling and/or Disposing of Excess Materials | Maintain defined, labeled storage areas and perform weekly material walks to consolidate, find slow-moving stock, and verify on-hand quantities before reordering. | Field Supervisor | Sec. 9.3 Field Leadership (staging/logistics) | ✔ Covered | No change required. | Materials Management
9.5.010 – Handling and/or Disposing of Excess Materials | At demob/closeout, identify and stage excess materials, restore shelf condition where practical, and create a simple list for review. | Field Supervisor | Sec. 9.3 Field Leadership (demobilization and closeout) | ⚠ Gap – systematic excess identification at closeout not defined | Add language in Sec. 9.3 Field Leadership requiring field leadership to identify, stage, and list excess materials at demob/closeout. | Materials Management
9.5.010 – Handling and/or Disposing of Excess Materials | Approve the material release and excess-material handling strategy using Options 1–5 based on total cost to the project. | Project Manager | Sec. 9.5 PM (project closeout and improvement) | ✔ Covered | No change required. | Materials Management
9.5.010 – Handling and/or Disposing of Excess Materials | Confirm vendor return rules and costs and assist PM in selecting the most cost-effective option for excess materials. | Purchasing | Sec. 9.16 Purchasing (vendor terms and returns) | ✔ Covered | No change required. | Materials Management
9.5.010 – Handling and/or Disposing of Excess Materials | Accept only materials likely to be used within 6 months into the shop/warehouse and prevent long-term dumping of obsolete or low-value leftovers. | Shop/Warehouse | Sec. 7.3 Operations Office Positions (shop/warehouse expectations) | ⚠ Gap – warehouse acceptance rules not documented | Clarify in Sec. 7.3 Operations Office Positions that shop/warehouse will only accept materials with reasonable near-term use and is not long-term storage for job leftovers. | Materials Management
9.4.745 – Manage Field Rework | Identify & Log Rework | Foreman | Ch.9: Productivity- Foremen and Lead Men shall be accountable... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Classify & Route | QA/QC | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Authorize & Plan | Project Manager | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Assign Corrective Work | Foreman | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Execute & Track | Foreman | Ch.9: Productivity- Foremen and Lead Men shall be accountable... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Verify & Close | QA/QC | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | File & Report | Project Manager | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.2.010 – Team Selection | Confirm early purchasing and prefabrication support needs for precon and mobilization. | PM | Sec. 9.5 – Submittals and Purchasing; Sec. 9.5 – Prefabrication | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Confirm early purchasing and prefabrication support needs for precon and mobilization. | Prefab Lead | Sec. 9.5 – Submittals and Purchasing; Sec. 9.5 – Prefabrication | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Confirm early purchasing and prefabrication support needs for precon and mobilization. | Purchasing | Sec. 9.5 – Submittals and Purchasing; Sec. 9.5 – Prefabrication | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Confirm required attendees (BM, PM, GS, Foreman, Contract Manager and key support roles) are invited and prepared. | PM | Sec. 9.5 – Project Turnover Meetings; Sec. 9.13 – Project Turnover Meetings – Project Managers and Foremen | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Confirm safety coverage requirements based on project risk profile. | PM | Sec. 9.5 – Field Leadership and Manpower Requirements | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Confirm safety coverage requirements based on project risk profile. | Safety | Sec. 9.5 – Field Leadership and Manpower Requirements | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Finalize staffing plan with assigned names, responsibilities, and start dates. | PM | Sec. 7.3.1 – Project Manager – Essential Job Functions | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | GS assigns field supervisors | GS | Sec. 9.4 GS (manpower assignment) | ✔ Covered | No change required. | Team selection and turnover
9.2.010 – Team Selection | GS assigns field supervisors | PM | Sec. 9.4 GS (manpower assignment) | ✔ Covered | No change required. | Team selection and turnover
9.2.010 – Team Selection | Revalidate and update staffing plan when material scope/schedule/contract changes occur; re-communicate changes. | GS | Sec. 9.5 – Contract Changes; Sec. 9.13 – Upon receipt of any new documents… notice | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Revalidate and update staffing plan when material scope/schedule/contract changes occur; re-communicate changes. | PM | Sec. 9.5 – Contract Changes; Sec. 9.13 – Upon receipt of any new documents… notice | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Review award documents, scope, schedule, and risk profile; define required roles and start dates. | PM | Sec. 7.3.1 – Project Manager – Essential Job Functions; Sec. 9.5 – Project Pre-Planning and Developing the Construction Plan | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Schedule Project Turnover Meeting per SOP 9.2.015 and send invite to all assigned leadership/support roles. | PM | Sec. 9.5 – Project Turnover Meetings; Sec. 9.13 – Project Turnover Meetings – Project Managers and Foremen | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Submit draft Project Staffing Plan for BM/Biz Mgr review and approval; resolve resource conflicts. | BM | Sec. 9.5 – Field Leadership and Manpower Requirements; Sec. 9.13 – GSL Electric’s Branch Management Directives | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Submit draft Project Staffing Plan for BM/Biz Mgr review and approval; resolve resource conflicts. | Biz Mgr | Sec. 9.5 – Field Leadership and Manpower Requirements; Sec. 9.13 – GSL Electric’s Branch Management Directives | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Update Manpower Projections in Workforce Planning software consistent with staffing plan. | GS | Sec. 9.4 – Update Manpower Projections each week through Workforce Planning software | ✔ Covered |  | Precon / Mobilization
9.2.010 – Team Selection | Upload staffing plan to the project folder and distribute to assigned team members and stakeholders. | PM | Sec. 9.5 – Daily Reports and Project Administration Support (document control intent) | ⚠ Gap – partial coverage | Consider adding explicit 'Project Staffing Plan uploaded to project folder prior to turnover' language to Sec. 9.5 directives and PM JD. | Precon / Mobilization
9.2.010 – Team Selection | Upload staffing plan to the project folder and distribute to assigned team members and stakeholders. | Project Coordinator | Sec. 9.5 – Daily Reports and Project Administration Support (document control intent) | ⚠ Gap – partial coverage | Consider adding explicit 'Project Staffing Plan uploaded to project folder prior to turnover' language to Sec. 9.5 directives and PM JD. | Precon / Mobilization
9.4.190 – Document Filing Standards | File incoming/outgoing project documents to the correct system and folder (by document type). | Project Manager | Document Control – | ✔ Covered |  | Documentation Management
9.4.190 – Document Filing Standards | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Site Administrator | Document Control – | ✔ Covered |  | Documentation Management
9.4.745 – Manage Field Rework | Authorize & Plan | Foreman | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Classify & Route | APM | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Classify & Route | Project Engineer | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Classify & Route | Project Manager | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Execute & Track | General Superintendent | Ch.9: Productivity- Foremen and Lead Men shall be accountable... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | File & Report | APM | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | File & Report | Project Engineer | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Verify & Close | QA | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management
9.4.745 – Manage Field Rework | Verify & Close | QC | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management

## RACI Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category | RACI
9.2.010 - Team Selection | PM defines staffing needs | Project Manager | Sec. 9.5 PM (manpower plan) | ✔ Covered | No change required. | Team selection and turnover | A
9.2.010 - Team Selection | GS assigns field supervisors | General Superintendent | Sec. 9.4 GS (manpower assignment) | ✔ Covered | No change required. | Team selection and turnover | I
9.2.010 - Team Selection | Branch Manager approves staffing plan | Branch Manager | Sec. 9.6 Branch Mgmt (operations control) | ⚠ Gap – approval not explicit | Add approval language to Sec. 9.6. | Team selection and turnover | A
9.2.010 - Team Selection | Safety Coordinator advises on assignments | Safety Coordinator | Sec. 7.2.6 JD (safety hazard identification) | ⚠ Gap – advisory role not explicit | Add cross-check with Safety Coordinator. | Team selection and turnover | R
9.2.015 - Project Turnover Meeting | Conduct estimator-led turnover meeting | Estimator | Sec. 9.7 Estimating (turnover participation) | ✔ Covered | No change required. | Team selection and turnover | C
9.2.015 - Project Turnover Meeting | Participate in turnover meeting | PM, Branch Mgr, GS, Field Leadership, Prefab, Safety | Sec. 9.5 PM (turnover), Sec. 9.13 BM, Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Team selection and turnover | I
9.2.015 - Project Turnover Meeting | Prepare meeting agenda and minutes | Project Manager | Sec. 9.5 PM (meeting leadership) | ⚠ Gap – agenda/minutes not required | Add to Sec. 9.5: PM must issue minutes within 48 hrs. | Team selection and turnover | A
9.2.020 - Procurement of Large Feeder Wire | Populate Feeder Wire Procurement & Release Log upon NOA/LOI and confirm feeder details with field team. | Project Manager | Sec. 9.5 PM (procurement planning); Sec. 9.16 Purchasing | ⚠ Gap – feeder log use not explicit | Add requirement for Feeder Wire Procurement & Release Log to Sec. 9.5 PM (procurement planning). | Materials Management | A
9.2.020 - Procurement of Large Feeder Wire | Issue RFQs and obtain 2+ documented vendor quotes for large feeder wire. | Purchasing | Sec. 9.16 Purchasing (pre-buyout procurement) | ⚠ Gap – competitive quote documentation not explicit | Update Sec. 9.16 Purchasing to require at least two documented quotes for large feeder wire purchases. | Materials Management | R
9.2.020 - Procurement of Large Feeder Wire | Select vendor and set PO terms including pricing lock, lead times, and delivery conditions for feeder wire. | Project Manager | Sec. 9.5 PM (procurement planning); Sec. 9.16 Purchasing | ✔ Covered | No change required. | Materials Management | A
9.2.020 - Procurement of Large Feeder Wire | Assemble and submit feeder wire submittals; hold releases until submittal approval. | Project Manager | Sec. 9.5 PM (submittals management) | ✔ Covered | No change required. | Materials Management | A
9.2.020 - Procurement of Large Feeder Wire | Pre-plan logistics and conduit/wire pull schedule with Field Supervision using BOM and scaled drawings. | Project Manager | Sec. 9.5 PM (material handling plan); Sec. 9.3 Field Leadership (pre-planning) | ✔ Covered | No change required. | Materials Management | A
9.2.020 - Procurement of Large Feeder Wire | Direct vendors to store wire until release, cut and bundle feeders per releases, and bill upon release. | Purchasing | Sec. 9.16 Purchasing (commodities and wire procurement) | ⚠ Gap – storage, release, and billing conditions not defined | Update Sec. 9.16 Purchasing to define storage at vendor warehouse, release after submittal approval, bundling expectations, and billing upon release for large feeder wire. | Materials Management | R
9.2.020 - Procurement of Large Feeder Wire | Prepare BOM & conduit/wire pull schedule | Project Manager | Sec. 9.5 PM (procurement planning); Sec. 9.16 Purchasing | ✔ Covered | No change required. | Buyout process | A
9.2.020 - Procurement of Large Feeder Wire | Validate lengths and reel assignments | Foreman / Field Supervisor | Sec. 9.3 Field Leadership (materials validation) | ✔ Covered | No change required. | Buyout process | R
9.2.020 - Procurement of Large Feeder Wire | Confirm manpower/logistics feasibility | General Superintendent | Sec. 9.4 GS (manpower coordination) | ✔ Covered | No change required. | Buyout process | I
9.2.020 - Procurement of Large Feeder Wire | Approve submittals before release | Project Manager | Not explicit in directives | ⚠ Gap – submittal approval requirement | Add to Sec. 9.5: PM must verify submittals before release. | Buyout process | A
9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | Review contract for unfavorable clauses | Project Manager | Sec. 9.5 PM (contract review) | ✔ Covered | No change required. | Scope and contract review | A
9.2.030 - Review Contract for Unfavorable or High-Risk Clauses | Escalate risks and prepare mitigation plan | PM, Branch Manager | Sec. 9.14 Contract Mgr (risk oversight), Sec. 9.13 BM (contracts) | ⚠ Gap – mitigation plan not explicit | Add checklist/mitigation step. | Scope and contract review | A
9.2.040 - Project Manager Reviews Plans, Specifications & Schedule | Review drawings, specs, and schedules | Project Manager | Sec. 9.5 PM (scope & schedule review) | ✔ Covered | No change required. | Scope and contract review | A
9.2.040 - Project Manager Reviews Plans, Specifications & Schedule | Complete Scope & Schedule Checklist | Project Manager | Not explicit in directives | ⚠ Gap – checklist requirement | Add checklist reference to Sec. 9.5. | Scope and contract review | A
9.2.040 - Project Manager Reviews Plans, Specifications & Schedule | Integrate results into PEP | Project Manager | Sec. 7.3.1 PM JD (planning & PEP) | ⚠ Gap – explicit PEP update not required | Add to PM JD/Directive 9.5. | Scope and contract review | A
9.2.050 - Field Supervisor Reviews Plans, Specifications & Schedule | Review drawings/specs/schedules for constructability | Field Supervisor | Sec. 9.3 Field Leadership (pre-planning) | ✔ Covered | No change required. | Scope and contract review | R
9.2.050 - Field Supervisor Reviews Plans, Specifications & Schedule | Submit findings to PM & GS | Field Supervisor | Sec. 9.3 Field Leadership (reporting to PM/GS) | ✔ Covered | No change required. | Scope and contract review | R
9.2.050 - Field Supervisor Reviews Plans, Specifications & Schedule | Integrate findings into PEP | Project Manager | Sec. 9.5 PM (job planning) | ⚠ Gap – PEP update not explicit | Add to Sec. 9.5: PM integrates FS findings. | Scope and contract review | A
9.2.060 - Create List of Issues & Begin RFI Process | Identify constructability/scope issues | Field Supervisor | Sec. 9.3 Field Leadership (report issues) | ✔ Covered | No change required. | Scope and contract review | R
9.2.060 - Create List of Issues & Begin RFI Process | Maintain RFI log | Project Manager | Sec. 9.5 PM (document scope changes) | ✔ Covered | No change required. | Scope and contract review | A
9.2.060 - Create List of Issues & Begin RFI Process | Escalate major issues to Branch Manager | PM & GS | Sec. 9.14 Contract Mgr (notice requirements) | ⚠ Gap – escalation step not explicit | Add escalation language to Sec. 9.5. | Scope and contract review | I
9.2.070 - Conduct Site Visit | Perform site walk & complete checklist | Field Leadership (Project Superintendent/Foreman) | Management Directives for Field Leadership – Pre-planning | ✔ Covered | No change required. | Scope and contract review | R
9.2.070 - Conduct Site Visit | Integrate findings into PEP | Project Manager | Project Manager JD – planning, meetings, and site visits | ✔ Covered | No change required (SOP updated). | Scope and contract review | A
9.2.070 - Conduct Site Visit | Identify site-specific hazards | Safety Coordinator | Management Directives – PPE mandatory | ✔ Covered | No change required. | Scope and contract review | R
9.2.070 - Conduct Site Visit | Review manpower/logistics implications | General Superintendent | Management Directives – Pre-planning with PM | ✔ Covered | No change required. | Scope and contract review | C
9.2.080 - Prepare Material Handling Plan | Develop logistics plan for delivery/staging | Field Supervisor | Sec. 9.3 Field Leadership (staging/logistics) | ✔ Covered | No change required. | Material handling plan | R
9.2.080 - Prepare Material Handling Plan | Align with procurement & project schedule | Project Manager | Sec. 9.5 PM (logistics, procurement alignment) | ✔ Covered | No change required. | Material handling plan | A
9.2.080 - Prepare Material Handling Plan | Review safety compliance of handling plan | Safety Coordinator | Sec. 7.2.6 JD (safety review) | ✔ Covered | No change required. | Material handling plan | R
9.2.090 - Develop Labor Budget | Develop detailed labor forecast | Project Manager | Sec. 9.5 PM (labor planning) | ✔ Covered | No change required. | Budget preparation | A
9.2.090 - Develop Labor Budget | Validate manpower feasibility | General Superintendent | Sec. 9.4 GS (workforce oversight) | ✔ Covered | No change required. | Budget preparation | I
9.2.090 - Develop Labor Budget | Provide labor assumptions from bid | Estimator | Sec. 9.7 Estimating (labor assumptions) | ✔ Covered | No change required. | Budget preparation | C
9.2.090 - Develop Labor Budget | Approve labor budget | Branch Manager | Sec. 9.6 Branch Mgmt (budget oversight) | ✔ Covered | No change required. | Budget preparation | A
9.2.0200 - Prepare Layout & Sequencing Plan | Develop sequencing plan & integrate into PEP | Project Manager | Sec. 9.5 PM (planning, scheduling) | ✔ Covered | No change required. | Layout and sequencing plan | A
9.2.0200 - Prepare Layout & Sequencing Plan | Review constructability & sequencing feasibility | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Layout and sequencing plan | R
9.2.0200 - Prepare Layout & Sequencing Plan | Confirm manpower allocations & critical path | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Layout and sequencing plan | I
9.2.0200 - Prepare Layout & Sequencing Plan | Identify safety risks in layout/sequencing | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Layout and sequencing plan | R
9.2.110 - Develop Project Schedule | Develop baseline schedule | Project Manager | Sec. 9.5 PM (schedule ownership) | ✔ Covered | No change required. | Schedule development | A
9.2.110 - Develop Project Schedule | Validate manpower phasing feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Schedule development | I
9.2.110 - Develop Project Schedule | Confirm long-lead procurement dates | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Schedule development | C
9.2.110 - Develop Project Schedule | Approve baseline schedule | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Schedule development | A
9.2.120 - Establish Tracking & Control Systems | Establish tracking templates/logs | Project Manager | Sec. 9.5 PM (reporting systems) | ✔ Covered | No change required. | Tracking and control | A
9.2.120 - Establish Tracking & Control Systems | Report daily manpower/progress | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Tracking and control | R
9.2.120 - Establish Tracking & Control Systems | Maintain procurement log | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Tracking and control | C
9.2.120 - Establish Tracking & Control Systems | Submit safety inspection reports | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Tracking and control | R
9.2.120 - Establish Tracking & Control Systems | Review weekly reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Tracking and control | A
9.2.130 - Construction Execution Kickoff Meeting | Organize & lead kickoff | Project Manager | Sec. 9.5 PM (turnover/kickoff) | ✔ Covered | No change required. | Construction execution kickoff meeting | A
9.2.130 - Construction Execution Kickoff Meeting | Confirm manpower/sequence feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Construction execution kickoff meeting | I
9.2.130 - Construction Execution Kickoff Meeting | Review site logistics | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Construction execution kickoff meeting | R
9.2.130 - Construction Execution Kickoff Meeting | Provide procurement/delivery updates | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Construction execution kickoff meeting | C
9.2.130 - Construction Execution Kickoff Meeting | Present safety plan | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Construction execution kickoff meeting | R
9.2.130 - Construction Execution Kickoff Meeting | Provide branch-level oversight | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Construction execution kickoff meeting | A
9.3.010 - Setup Office Trailer | Secure trailer & utilities setup | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization | A
9.3.010 - Setup Office Trailer | Setup furniture & documentation systems | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Mobilization | R
9.3.010 - Setup Office Trailer | Confirm location/logistics feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Mobilization | I
9.3.010 - Setup Office Trailer | Ensure phone/internet operational | IT/Communications | Sec. 7.4 Business Admin JD (IT) | ✔ Covered | No change required. | Mobilization | I
9.3.020 - Setup Storage Trailer | Approve trailer placement | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization | A
9.3.020 - Setup Storage Trailer | Setup shelving & inventory control | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.020 - Setup Storage Trailer | Verify compliance with fire/access standards | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.3.030 - Setup Site Fencing and Access Control | Approve fencing & access plan | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization | A
9.3.030 - Setup Site Fencing and Access Control | Oversee fence/gate installation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.030 - Setup Site Fencing and Access Control | Verify safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.3.030 - Setup Site Fencing and Access Control | Monitor access control | Security Personnel | Not explicit in directives | ⚠ Gap – role not formalized | Add security monitoring responsibility to Sec. 9.5. | Mobilization | I
9.3.040 - Setup Temporary Power | Coordinate power requirements with utility/owner | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization | A
9.3.040 - Setup Temporary Power | Oversee installation & verify distribution | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.040 - Setup Temporary Power | Install panels/wiring/grounding | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization | R
9.3.040 - Setup Temporary Power | Verify OSHA/NEC compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.3.050 - Setup Temporary Water | Coordinate utility connection | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization | A
9.3.050 - Setup Temporary Water | Oversee installation/distribution | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.050 - Setup Temporary Water | Verify safety/environmental compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.3.060 - Setup Sanitary Facilities | Contract vendors for sanitary facilities | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization | A
9.3.060 - Setup Sanitary Facilities | Determine placement & logistics | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.060 - Setup Sanitary Facilities | Maintain inspection log | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.3.070 - Setup Temporary Lighting | Approve lighting plan & budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.3.070 - Setup Temporary Lighting | Oversee installation & verify coverage | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.070 - Setup Temporary Lighting | Install temporary lighting | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization | R
9.3.070 - Setup Temporary Lighting | Inspect OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.3.080 - Setup Signage | Determine signage requirements | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.3.080 - Setup Signage | Install signage | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.080 - Setup Signage | Ensure OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.3.090 - Setup Security | Approve security plan & vendors | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.3.090 - Setup Security | Implement physical security | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.090 - Setup Security | Daily monitoring of access points | Security Personnel | Not explicit in directives | ⚠ Gap – security personnel not formalized | Add security responsibilities to Sec. 9.5. | Mobilization | I
9.3.090 - Setup Security | Ensure plan aligns with safety | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.3.100 - Setup Laydown Area | Approve laydown area location | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.3.100 - Setup Laydown Area | Setup & manage laydown area | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.100 - Setup Laydown Area | Verify safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.3.110 - Setup Equipment Staging | Approve staging location | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.3.110 - Setup Equipment Staging | Direct equipment setup | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.110 - Setup Equipment Staging | Position equipment safely | Equipment Operators | Not explicit in directives | ⚠ Gap – equipment operator role not formalized | Add operator role into mobilization directive. | Mobilization | I
9.3.110 - Setup Equipment Staging | Verify OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.3.120 - Setup Parking | Approve parking plan | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.3.120 - Setup Parking | Establish parking areas | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.3.120 - Setup Parking | Verify traffic safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.4.010 - Conduct Coordination Meetings | Schedule & chair coordination meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination | A
9.4.010 - Conduct Coordination Meetings | Provide field updates & issues | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination | R
9.4.010 - Conduct Coordination Meetings | Record minutes & action items | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Coordination | R
9.4.010 - Conduct Coordination Meetings | Provide design clarifications | Design Team / Consultants | Not explicit in directives | ⚠ Gap – design consultant role not formalized | Add consultant clarification role to Sec. 9.5. | Coordination | I
9.4.020 - Conduct Subcontractor Coordination Meetings | Prepare and distribute subcontractor agenda | Project Manager | Sec. 9.5 PM (coordination) | ✔ Covered | No change required. | Coordination | A
9.4.020 - Conduct Subcontractor Coordination Meetings | Provide progress/manpower updates | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor reporting requirements. | Coordination | R
9.4.020 - Conduct Subcontractor Coordination Meetings | Report logistics needs | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination | R
9.4.020 - Conduct Subcontractor Coordination Meetings | Review safety performance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.4.030 - Conduct Client/Owner Meetings | Lead client/owner meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination | A
9.4.030 - Conduct Client/Owner Meetings | Provide executive oversight | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Coordination | A
9.4.030 - Conduct Client/Owner Meetings | Approve changes/raise concerns | Client/Owner | Not in directives | ⚠ Gap | Owner role external to GSL; clarify interface protocols. | Coordination | C
9.4.040 - Conduct Safety Meetings | Prepare/lead safety meetings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.4.040 - Conduct Safety Meetings | Ensure scheduling and attendance | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.4.040 - Conduct Safety Meetings | Reinforce safety in daily huddles | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.4.040 - Conduct Safety Meetings | Participate in meetings | All Employees | Not in directives | ⚠ Gap | Include participation expectation in JD handbook. | Safety Management | I
9.4.040 - Conduct Safety Meetings | Schedule/facilitate prefab meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination | A
9.4.040 - Conduct Safety Meetings | Provide prefab schedules/deliverables | Prefab Lead | Sec. 7.3.7 Prefab JD | ✔ Covered | No change required. | Coordination | I
9.4.040 - Conduct Safety Meetings | Validate constructability feasibility | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination | R
9.4.040 - Conduct Safety Meetings | Confirm manpower sequencing | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management | I
9.4.060 - Conduct Quality Meetings | Schedule/facilitate meetings, track actions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Quality Control | A
9.4.060 - Conduct Quality Meetings | Report quality issues | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Quality Control | R
9.4.060 - Conduct Quality Meetings | Review quality inspections | Quality Inspector | Not in directives | ⚠ Gap | Add inspector responsibilities into QA directive. | Quality Control | I
9.4.060 - Conduct Quality Meetings | Confirm overlap with safety | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.4.190 – Document Filing Standards | Set up project folder structure using the standard template (Procore + Windows). | Site Administrator | Document Control – | ✔ Covered |  | Documentation Management | PM=A; Site Admin=R; BM=C
9.4.190 – Document Filing Standards | Apply file/folder naming conventions and character rules consistently. | Project Engineer / APM | Document Control – | ✔ Covered |  | Documentation Management | PM=A; PE/APM=R; Site Admin=C
9.4.190 – Document Filing Standards | File incoming/outgoing project documents to the correct system and folder (by document type). | Field Foreman | Document Control – | ✔ Covered |  | Documentation Management | PM=A; Foreman=R; Site Admin=C
9.4.190 – Document Filing Standards | Maintain version control: keep current docs current and move superseded versions to archive. | Site Administrator | Document Control – | ✔ Covered |  | Documentation Management | PM=A; Site Admin=R; PE/APM=C
9.4.190 – Document Filing Standards | Issue updated drawings/submittals to field and confirm latest versions are accessible. | Project Manager | Document Control – | ✔ Covered |  | Documentation Management | PM=A/R; GS=C; Foreman=I; Site Admin=C
9.4.190 – Document Filing Standards | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Branch Manager | Document Control – | ✔ Covered |  | Documentation Management | BM=A; PM=R; Site Admin=R
9.4.190 – Document Filing Standards | At closeout, compile and archive the final documentation package per closeout requirements. | Project Manager | Project Closeout | ✔ Covered |  | Documentation Management | PM=A/R; Site Admin=R; BM=C
9.4.195 - Manage Project Documentation System | Ensure compliance with filing standards | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management | A
9.4.195 - Manage Project Documentation System | Organize folders & verify consistency | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management | R
9.4.195 - Manage Project Documentation System | Audit system compliance | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Documentation Management | A
9.4.200 - Manage Submittals | Prepare submittal log & ensure timely submissions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management | A
9.4.200 - Manage Submittals | Coordinate vendor submittals | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Documentation Management | C
9.4.200 - Manage Submittals | Provide shop drawings/product data | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor submittal duties. | Documentation Management | R
9.4.205 - Manage RFIs (Requests for Information) | Subcontractors required to draft/support RFIs | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor RFI responsibilities to directives. | Scope & Change Control | R
9.4.210 - Manage Meeting Minutes | Minutes responsibility clarity | Site Administrator | Not explicit in directives | ⚠ Gap | Explicitly assign Site Admin responsibility for meeting minutes. | Communication | R
9.4.215 - Manage Daily Reports | Foremen/Subcontractors required to submit daily reports | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor daily report requirement. | Labor Management | R
9.4.220 - Manage Drawing Logs | Subcontractors to submit updated drawings | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor drawing log submission. | Documentation Management | R
9.4.225 - Manage Specifications | Subcontractor input on spec compliance | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor compliance review of specs. | Documentation Management | R
9.4.230 - Manage Correspondence | Subcontractors required to provide written correspondence trail | Subcontractors | Not explicit in directives | ⚠ Gap | Include subcontractor correspondence duty. | Communication | R
9.4.235 - Manage Permits | Authority responsibility for inspections | Regulatory Authorities | External role | ⚠ Gap | Clarify external agency responsibility protocol. | Safety Management | I
9.4.240 - Manage Inspection Reports | Subcontractors must close open deficiencies | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor inspection compliance duties. | Quality Control | R
9.2.055 – Compare Est. vs. Planned | Provide bid documentation | Estimator | Sec. 9.7 Estimating (bid package review) | ✔ Covered | No change required. | Budget preparation | C
9.2.055 – Compare Est. vs. Planned | Compare assumptions vs. execution plan | Project Manager | Sec. 9.5 PM (job plan updates) | ✔ Covered | No change required. | Budget preparation | A
9.2.055 – Compare Est. vs. Planned | Validate manpower implications | General Superintendent | Sec. 9.4 GS (workforce oversight) | ✔ Covered | No change required. | Budget preparation | I
9.2.055 – Compare Est. vs. Planned | Validate budget alignment | Branch Manager | Sec. 9.6 Branch Mgmt (budget alignment) | ✔ Covered | No change required. | Budget preparation | A
9.2.057 – VE & Prefab | Facilitate identification of VE/prefab opportunities | Project Manager | Sec. 9.5 PM (prefabrication planning) | ✔ Covered | No change required. | Buyout process | A
9.2.057 – VE & Prefab | Develop prefab strategy sheet | Prefabrication Lead | Sec. 7.3.7 Prefab JD (prefab strategy) | ✔ Covered | No change required. | Buyout process | R
9.2.057 – VE & Prefab | Validate constructability/feasibility | Field Supervisor | Sec. 9.3 Field Leadership (field feasibility) | ✔ Covered | No change required. | Buyout process | R
9.2.057 – VE & Prefab | Confirm VE proposals align with budget | Estimator | Sec. 9.7 Estimating (VE options) | ✔ Covered | No change required. | Buyout process | C
9.2.057 – VE & Prefab | Record opportunities in VE log | Project Manager | Not explicit in directives | ⚠ Gap – VE log not required | Add VE log requirement in Sec. 9.5. | Buyout process | A
9.1.050 – Construction Takeoff | Generate detailed material/labor quantities | Project Manager | Sec. 9.5 PM (buyout planning) | ✔ Covered | No change required. | Buyout process | A
9.1.050 – Construction Takeoff | Provide bid takeoff for reference | Estimator | Sec. 9.7 Estimating (bid takeoff) | ✔ Covered | No change required. | Buyout process | C
9.1.050 – Construction Takeoff | Review constructability & logistics accuracy | Field Supervisor | Sec. 9.3 Field Leadership (constructability review) | ✔ Covered | No change required. | Buyout process | R
9.1.050 – Construction Takeoff | Use results for vendor negotiations & procurement | Purchasing | Sec. 9.16 Purchasing (pre-buyout procurement) | ✔ Covered | No change required. | Buyout process | C
9.1.050 – Construction Takeoff | Finalize & upload takeoff results | Project Manager | Not explicit in directives | ⚠ Gap – upload requirement | Add takeoff upload requirement to Sec. 9.5. | Buyout process | A
9.4.300 - Manage Architect/Engineer Communications | Issue RFIs and receive design clarifications | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Communication | A
9.4.300 - Manage Architect/Engineer Communications | Identify conflicts and escalate | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Communication | R
9.4.300 - Manage Architect/Engineer Communications | Log A/E communications | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management | R
9.4.310 - Manage General Contractor Communications | Lead communications with GC | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Communication | A
9.4.310 - Manage General Contractor Communications | Escalate field directives | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Communication | R
9.4.310 - Manage General Contractor Communications | Log GC correspondence | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management | R
9.4.315 - Develop Project Schedule | Develop baseline schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.4.315 - Develop Project Schedule | Superintendent role not explicit in directives | Superintendent | Not explicit in directives | ⚠ Gap | Clarify Superintendent role in directive 9.4 for schedule input. | Scheduling | I
9.4.320 - Update Project Schedule | Update project schedule with progress | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.4.320 - Update Project Schedule | Provide weekly progress | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Scheduling | I
9.4.325 - Monitor Schedule Performance | Prepare performance reports | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.4.325 - Monitor Schedule Performance | Verify progress in field | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management | I
9.4.330 - Develop Schedule Recovery Plans | Develop recovery strategies | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.4.330 - Develop Schedule Recovery Plans | Approve recovery plans | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control | A
9.4.330 - Develop Schedule Recovery Plans | Superintendent adjustments not explicit | Superintendent | Not explicit in directives | ⚠ Gap | Add Superintendent labor/equipment adjustment duties. | Scheduling | I
9.4.335 - Prepare Lookahead Schedules | Prepare weekly lookaheads | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.4.335 - Prepare Lookahead Schedules | Confirm sequencing | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management | I
9.4.335 - Prepare Lookahead Schedules | Use lookahead for crew planning | Field Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management | R
9.4.340 – Resource-Loaded | Foreman role missing for crew-level validation | Field Foreman | Not explicit in directives | ⚠ Gap | Add Foreman resource feedback duty. | Labor Management | R
9.4.340 - Manage Resource-Loaded Schedules | Integrate resources into schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.4.340 - Manage Resource-Loaded Schedules | Confirm resource availability | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management | I
9.4.340 - Manage Resource-Loaded Schedules | Review resource forecasts | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Materials Management | A
9.4.345 - Conduct Schedule Review Meetings | Prepare agenda and lead meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.4.345 - Conduct Schedule Review Meetings | Provide field updates | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Scheduling | I
9.4.345 - Conduct Schedule Review Meetings | Confirm crew availability | Field Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management | R
9.4.345 - Conduct Schedule Review Meetings | Approve mitigation strategies | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Coordination | A
9.4.345 - Conduct Schedule Review Meetings | Consultant participation not explicit | Consultants | Not explicit in directives | ⚠ Gap | Add consultant role in review meetings if applicable. | Coordination | I
9.4.350 - Manage Schedule Change Requests | Review schedule change requests | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.4.350 - Manage Schedule Change Requests | Approve/reject requests | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scheduling | A
9.4.350 - Manage Schedule Change Requests | Log requests | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty to maintain change request log. | Documentation Management | R
9.4.355 - Manage Project Scope | Define and control project scope | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.4.355 - Manage Project Scope | Approve scope adjustments | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control | A
9.4.360 - Manage Change Orders | Prepare CO documentation | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.4.360 - Manage Change Orders | Review CO costs | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing | C
9.4.360 - Manage Change Orders | Approve COs before submission | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control | A
9.4.360 - Manage Change Orders | Maintain CO log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for CO logs. | Documentation Management | R
9.4.365 - Manage Potential Change Orders (PCOs) | Identify and document potential COs | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.4.365 - Manage Potential Change Orders (PCOs) | Provide cost backup | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing | C
9.4.370 - Manage Owner Directives | Implement and log directives | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.4.370 - Manage Owner Directives | Review directives for cost/schedule impact | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control | A
9.4.375 - Manage Scope Clarifications | Identify and clarify scope gaps | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.4.375 - Manage Scope Clarifications | Provide bid data for clarifications | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Scope & Change Control | C
9.4.380 - Manage Backcharges | Approve backcharges | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.380 - Manage Backcharges | Process financial impacts | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for backcharge tracking. | Cost Control & Billing | R
9.4.385 - Manage Force Account Work | Authorize force account work | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.4.385 - Manage Force Account Work | Track labor/equipment/materials | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management | R
9.4.385 - Manage Force Account Work | Process billing | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for force account billing. | Cost Control & Billing | R
9.4.385 - Manage Force Account Work | File and log records | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for FA logs. | Documentation Management | R
9.4.390 - Manage Claims | Identify/prepare claims | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.4.390 - Manage Claims | Provide cost/time analysis | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing | C
9.4.390 - Manage Claims | Approve claims | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control | A
9.4.390 - Manage Claims | Assist with disputes | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role. | Scope & Change Control | C
9.4.390 - Manage Claims | Maintain claim log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for claim logs. | Documentation Management | R
9.2.140 - Develop Project Budget | Prepare project budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.2.140 - Develop Project Budget | Provide bid/estimate backup | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing | C
9.2.140 - Develop Project Budget | Review/input budget | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to record project budget. | Cost Control & Billing | R
9.2.140 - Develop Project Budget | Approve budget | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.400 - Monitor Project Costs | Monitor project costs vs. budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.400 - Monitor Project Costs | Validate cost reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.400 - Monitor Project Costs | Maintain detailed cost tracking | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for cost monitoring. | Cost Control & Billing | R
9.4.405 - Manage Cost Forecasts | Prepare updated cost forecasts | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.405 - Manage Cost Forecasts | Provide backup and adjustments | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting responsibility for forecast inputs. | Cost Control & Billing | R
9.4.410 - Manage Cost Codes | Assign and maintain cost codes | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.410 - Manage Cost Codes | Ensure alignment with company standards | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to align cost codes with financial systems. | Cost Control & Billing | R
9.4.415 - Manage Committed Costs | Review purchase orders & contracts | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Materials Management | A
9.4.415 - Manage Committed Costs | Approve commitments | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.415 - Manage Committed Costs | Maintain records | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for committed cost records. | Cost Control & Billing | R
9.4.420 - Manage Actual Costs | Track invoices and payroll | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting role for actual costs. | Cost Control & Billing | R
9.4.420 - Manage Actual Costs | Validate costs against budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.425 - Manage Job Cost Reports | Prepare monthly job cost reports | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.425 - Manage Job Cost Reports | Validate reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.425 - Manage Job Cost Reports | Provide accounting input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for job cost reports. | Cost Control & Billing | R
9.4.430 - Manage Profit Projections | Prepare profit projections | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.430 - Manage Profit Projections | Review projections | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.430 - Manage Profit Projections | Verify financial data | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify data for projections. | Cost Control & Billing | R
9.4.435 - Manage Cost-to-Complete | Update cost-to-complete projections | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.435 - Manage Cost-to-Complete | Validate projections | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.435 - Manage Cost-to-Complete | Provide actual data input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for actuals in cost-to-complete. | Cost Control & Billing | R
9.4.440 - Prepare Billing Schedule | Prepare billing schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.440 - Prepare Billing Schedule | Review billing schedule | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.440 - Prepare Billing Schedule | Confirm owner agreement | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for billing schedule. | Communication | C
9.4.445 - Prepare Monthly Pay Applications | Prepare pay application package | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.445 - Prepare Monthly Pay Applications | Review and approve pay apps | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.445 - Prepare Monthly Pay Applications | Provide invoices/payment records | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to provide records for pay apps. | Cost Control & Billing | R
9.4.445 - Prepare Monthly Pay Applications | Approve payment | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for pay applications. | Communication | C
9.4.450 - Track Accounts Receivable | Track AR aging and follow up on collections | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to maintain AR aging and collections follow-up. | Cost Control & Billing | R
9.4.450 - Track Accounts Receivable | Review AR status and escalate non-payment | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.450 - Track Accounts Receivable | Approve escalation actions for delinquent accounts | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.455 - Manage Lien Waivers | Collect executed lien waivers from subs/vendors | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management | A
9.4.455 - Manage Lien Waivers | Track lien waivers and verify with pay apps | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to track lien waivers with pay apps. | Documentation Management | R
9.4.455 - Manage Lien Waivers | Maintain lien waiver log | Site Administrator | Not explicit in directives | ⚠ Gap | Assign Site Admin to maintain lien waiver log. | Documentation Management | R
9.4.455 - Manage Lien Waivers | Provide executed lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor submission of lien waivers before payment. | Documentation Management | R
9.4.460 - Manage Retainage | Track retainage withheld and prepare release requests | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.460 - Manage Retainage | Verify amounts withheld and released | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify retainage withheld/released. | Cost Control & Billing | R
9.4.460 - Manage Retainage | Approve final retainage release | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.465 - Manage Final Invoicing | Prepare final invoice and ensure supporting docs complete | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.465 - Manage Final Invoicing | Review final invoice and submit for payment | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to review and submit final invoice. | Cost Control & Billing | R
9.4.465 - Manage Final Invoicing | Approve final invoice prior to release | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.4.465 - Manage Final Invoicing | Submit final pay apps and lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor final pay apps and lien waivers. | Cost Control & Billing | R
9.3.470 - Develop Site-Specific Safety Plan | Draft and maintain SSSP | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.3.470 - Develop Site-Specific Safety Plan | Review and approve SSSP | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.3.470 - Develop Site-Specific Safety Plan | Audit SSSP for compliance | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management | A
9.3.470 - Develop Site-Specific Safety Plan | Implement SSSP in field operations | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.4.475 - Conduct Safety Orientation | Conduct orientation sessions and maintain records | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.4.475 - Conduct Safety Orientation | Ensure all personnel complete orientation before work | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.4.475 - Conduct Safety Orientation | Verify crew participation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.4.480 - Conduct Safety Inspections | Conduct inspections and document findings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.4.480 - Conduct Safety Inspections | Correct hazards identified during inspections | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.4.480 - Conduct Safety Inspections | Review reports and ensure corrective action | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.4.480 - Conduct Safety Inspections | Audit safety inspection process | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management | A
9.4.485 - Conduct Safety Meetings | Prepare agenda and conduct meetings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.4.485 - Conduct Safety Meetings | Ensure meetings are held as scheduled | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.4.485 - Conduct Safety Meetings | Reinforce safety policies with crews | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.4.490 - Report Safety Incidents | Complete official incident report and submit | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.4.490 - Report Safety Incidents | Document initial details and notify PM/Safety | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.4.490 - Report Safety Incidents | Review and escalate incidents as required | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.4.490 - Report Safety Incidents | Submit report to Branch Manager within 24 hrs | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.4.495 - Investigate Accidents | Lead investigation and document findings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.4.495 - Investigate Accidents | Support investigation and implement corrective actions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.4.495 - Investigate Accidents | Provide incident details and ensure crew cooperation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.4.495 - Investigate Accidents | Review investigation and approve corrective measures | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management | A
9.4.495 - Investigate Accidents | Advise on legal implications as needed | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role in accident investigations. | Safety Management | C
9.5.010 - Conduct Commissioning Meetings | Schedule/facilitate commissioning | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination | A
9.5.010 - Conduct Commissioning Meetings | Define testing requirements | Commissioning Agent | Not in directives | ⚠ Gap | Add commissioning agent scope reference. | Quality Control | I
9.5.010 - Conduct Commissioning Meetings | Provide documentation/manpower | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor commissioning duties. | Coordination | R
9.5.010 - Conduct Commissioning Meetings | Ensure commissioning compliance | Quality Inspector | Not in directives | ⚠ Gap | Add QA/QC commissioning accountability. | Quality Control | I
9.5.010 – Handling and/or Disposing of Excess Materials | Use 3-week lookahead to plan and request materials and order roughly 1–3 weeks of stock. | Field Supervisor | Sec. 9.3 Field Leadership (pre-planning) | ⚠ Gap – explicit 3-week material planning not defined | Add guidance in Sec. 9.3 Field Leadership to use the 3-week lookahead to plan material needs and limit orders to roughly 1–3 weeks of work. | Materials Management | R
9.5.010 – Handling and/or Disposing of Excess Materials | Maintain defined, labeled storage areas and perform weekly material walks to consolidate, find slow-moving stock, and verify on-hand quantities before reordering. | Field Supervisor | Sec. 9.3 Field Leadership (staging/logistics) | ✔ Covered | No change required. | Materials Management | R
9.5.010 – Handling and/or Disposing of Excess Materials | At demob/closeout, identify and stage excess materials, restore shelf condition where practical, and create a simple list for review. | Field Supervisor | Sec. 9.3 Field Leadership (demobilization and closeout) | ⚠ Gap – systematic excess identification at closeout not defined | Add language in Sec. 9.3 Field Leadership requiring field leadership to identify, stage, and list excess materials at demob/closeout. | Materials Management | R
9.5.010 – Handling and/or Disposing of Excess Materials | Approve the material release and excess-material handling strategy using Options 1–5 based on total cost to the project. | Project Manager | Sec. 9.5 PM (project closeout and improvement) | ✔ Covered | No change required. | Materials Management | A
9.5.010 – Handling and/or Disposing of Excess Materials | Confirm vendor return rules and costs and assist PM in selecting the most cost-effective option for excess materials. | Purchasing | Sec. 9.16 Purchasing (vendor terms and returns) | ✔ Covered | No change required. | Materials Management | R
9.5.010 – Handling and/or Disposing of Excess Materials | Accept only materials likely to be used within 6 months into the shop/warehouse and prevent long-term dumping of obsolete or low-value leftovers. | Shop/Warehouse | Sec. 7.3 Operations Office Positions (shop/warehouse expectations) | ⚠ Gap – warehouse acceptance rules not documented | Clarify in Sec. 7.3 Operations Office Positions that shop/warehouse will only accept materials with reasonable near-term use and is not long-term storage for job leftovers. | Materials Management | R
9.6.010 - Conduct Closeout Meetings | Schedule and lead closeout meeting | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Project Closeout | A
9.6.010 - Conduct Closeout Meetings | Verify completion of punch list | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project Closeout | R
9.6.010 - Conduct Closeout Meetings | Submit closeout docs | Subcontractors | Not in directives | ⚠ Gap | Include subcontractor closeout requirements. | Project Closeout | R
9.6.010 - Conduct Closeout Meetings | Confirm acceptance of deliverables | Client/Owner | Not in directives | ⚠ Gap | Owner external – clarify acceptance protocols. | Project Closeout | C
9.6.020 - Manage Punch Lists | Subcontractors provide completion evidence | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor punch list responsibilities. | Project Closeout | R
9.6.070 - Conduct Post-Project Review | Schedule post-project review and invite project and branch stakeholders. | Project Manager | Sec. 9.5 PM (project closeout) | ⚠ Gap – formal review meeting not defined | Add explicit requirement for a post-project review meeting in Sec. 9.5 PM closeout section. | Project Closeout | A
9.6.070 - Conduct Post-Project Review | Prepare performance data (safety, schedule, cost, quality) and project documentation for review. | Project Manager | Sec. 9.5 PM (job monitoring and reporting) | ✔ Covered | No change required. | Project Closeout | A
9.6.070 - Conduct Post-Project Review | Lead review discussion of outcomes, successes, and improvement opportunities. | Branch Manager | Sec. 9.6 Branch Mgmt (operations oversight) | ✔ Covered | No change required. | Project Closeout | A
9.6.070 - Conduct Post-Project Review | Document post-project review outcomes in a summary report and file per SOP 9.4.190. | Project Manager | Sec. 9.5 PM (project documentation); SOP 9.4.190 | ✔ Covered | No change required. | Project Closeout | A
9.6.080 - Capture Client Feedback | Issue client feedback survey and/or interview request at project completion. | Project Manager | Sec. 9.5 PM (client relations at closeout) | ⚠ Gap – structured client feedback not defined | Amend Sec. 9.5 PM to require a standard client feedback survey or interview at closeout. | Project Closeout | A
9.6.080 - Capture Client Feedback | Conduct client feedback interview and clarify satisfaction, issues, and improvement ideas. | Project Manager | Sec. 9.5 PM (client relations at closeout) | ⚠ Gap – formal closeout interview not specified | Clarify in Sec. 9.5 PM that PM should conduct a closeout feedback interview when practical. | Project Closeout | A
9.6.080 - Capture Client Feedback | Review client feedback, prepare summary, and share with Branch Manager and Business Development. | Business Development | Business Development directives (client relationship management) | ⚠ Gap – BD feedback handling not documented | Create or update BD directives to assign responsibility for analyzing client feedback and updating client records. | Project Closeout | R
9.6.080 - Capture Client Feedback | Approve client feedback summary and incorporate into branch/market strategy. | Branch Manager | Sec. 9.6 Branch Mgmt (client relations and quality) | ✔ Covered | No change required. | Project Closeout | A
9.6.085 - Document Lessons Learned | Collect lessons learned input from project team, subcontractors, and stakeholders. | Project Manager | Sec. 9.5 PM (project closeout and improvement) | ⚠ Gap – structured lessons-learned process not defined | Add requirement in Sec. 9.5 PM for the PM to gather lessons learned at project closeout. | Project Closeout | A
9.6.085 - Document Lessons Learned | Review and validate lessons learned for accuracy, risk, and applicability. | Branch Manager | Sec. 9.6 Branch Mgmt (operations oversight) | ✔ Covered | No change required. | Project Closeout | A
9.6.085 - Document Lessons Learned | Enter approved lessons learned into the company knowledge base or tracking system. | Quality Coordinator | Quality / continuous improvement directives | ⚠ Gap – knowledge base ownership not documented | Create or update Quality/CI directives assigning responsibility for maintaining lessons-learned knowledge base. | Project Closeout | R
9.6.085 - Document Lessons Learned | Share key lessons learned with future project teams and leadership forums. | Quality Coordinator | Sec. 7.3 Operations Office Positions (knowledge sharing expectations) | ⚠ Gap – formal lessons sharing mechanism not defined | Define standard channels (PM meetings, training, communications) for distributing lessons learned. | Project Closeout | R
9.4.575 - Manage Feeder Wire Release | nan | nan | nan | nan | nan | nan | nan
9.4.745 – Manage Field Rework | Identify & Log Rework | Foreman | Ch.9: Productivity- Foremen and Lead Men shall be accountable... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | PM=A; Foreman=R; GS=C; QA/QC=C
9.4.745 – Manage Field Rework | Classify & Route | QA/QC | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | PM=A; QA/QC=R; GS=C; Foreman=C
9.4.745 – Manage Field Rework | Authorize & Plan | Project Manager | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | PM=A/R; GS=C; QA/QC=C; Foreman=I
9.4.745 – Manage Field Rework | Assign Corrective Work | Foreman | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | GS=A; Foreman=R; PM=C; QA/QC=C
9.4.745 – Manage Field Rework | Execute & Track | Foreman | Ch.9: Productivity- Foremen and Lead Men shall be accountable... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | GS=A; Foreman=R; PM=C; QA/QC=I
9.4.745 – Manage Field Rework | Verify & Close | QA/QC | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | PM=A; QA/QC=R; Foreman=C; GS=C
9.4.745 – Manage Field Rework | File & Report | Project Manager | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | PM=A; Foreman=C; GS=C; QA/QC=C
9.2.010 – Team Selection | Confirm early purchasing and prefabrication support needs for precon and mobilization. | PM | Sec. 9.5 – Submittals and Purchasing; Sec. 9.5 – Prefabrication | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Confirm early purchasing and prefabrication support needs for precon and mobilization. | Prefab Lead | Sec. 9.5 – Submittals and Purchasing; Sec. 9.5 – Prefabrication | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Confirm early purchasing and prefabrication support needs for precon and mobilization. | Purchasing | Sec. 9.5 – Submittals and Purchasing; Sec. 9.5 – Prefabrication | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Confirm required attendees (BM, PM, GS, Foreman, Contract Manager and key support roles) are invited and prepared. | PM | Sec. 9.5 – Project Turnover Meetings; Sec. 9.13 – Project Turnover Meetings – Project Managers and Foremen | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Confirm safety coverage requirements based on project risk profile. | PM | Sec. 9.5 – Field Leadership and Manpower Requirements | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Confirm safety coverage requirements based on project risk profile. | Safety | Sec. 9.5 – Field Leadership and Manpower Requirements | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Finalize staffing plan with assigned names, responsibilities, and start dates. | PM | Sec. 7.3.1 – Project Manager – Essential Job Functions | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | GS assigns field supervisors | GS | Sec. 9.4 GS (manpower assignment) | ✔ Covered | No change required. | Team selection and turnover | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | GS assigns field supervisors | PM | Sec. 9.4 GS (manpower assignment) | ✔ Covered | No change required. | Team selection and turnover | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Revalidate and update staffing plan when material scope/schedule/contract changes occur; re-communicate changes. | GS | Sec. 9.5 – Contract Changes; Sec. 9.13 – Upon receipt of any new documents… notice | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Revalidate and update staffing plan when material scope/schedule/contract changes occur; re-communicate changes. | PM | Sec. 9.5 – Contract Changes; Sec. 9.13 – Upon receipt of any new documents… notice | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Review award documents, scope, schedule, and risk profile; define required roles and start dates. | PM | Sec. 7.3.1 – Project Manager – Essential Job Functions; Sec. 9.5 – Project Pre-Planning and Developing the Construction Plan | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Schedule Project Turnover Meeting per SOP 9.2.015 and send invite to all assigned leadership/support roles. | PM | Sec. 9.5 – Project Turnover Meetings; Sec. 9.13 – Project Turnover Meetings – Project Managers and Foremen | ✔ Covered |  | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Submit draft Project Staffing Plan for BM/Biz Mgr review and approval; resolve resource conflicts. | BM | Sec. 9.5 – Field Leadership and Manpower Requirements; Sec. 9.13 – GSL Electric’s Branch Management Directives | ✔ Covered |  | Precon / Mobilization | BM=A; PM=R; GS=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Submit draft Project Staffing Plan for BM/Biz Mgr review and approval; resolve resource conflicts. | Biz Mgr | Sec. 9.5 – Field Leadership and Manpower Requirements; Sec. 9.13 – GSL Electric’s Branch Management Directives | ✔ Covered |  | Precon / Mobilization | BM=A; PM=R; GS=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Update Manpower Projections in Workforce Planning software consistent with staffing plan. | GS | Sec. 9.4 – Update Manpower Projections each week through Workforce Planning software | ✔ Covered |  | Precon / Mobilization | PM=A; GS=R; BM=I
9.2.010 – Team Selection | Upload staffing plan to the project folder and distribute to assigned team members and stakeholders. | PM | Sec. 9.5 – Daily Reports and Project Administration Support (document control intent) | ⚠ Gap – partial coverage | Consider adding explicit 'Project Staffing Plan uploaded to project folder prior to turnover' language to Sec. 9.5 directives and PM JD. | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.2.010 – Team Selection | Upload staffing plan to the project folder and distribute to assigned team members and stakeholders. | Project Coordinator | Sec. 9.5 – Daily Reports and Project Administration Support (document control intent) | ⚠ Gap – partial coverage | Consider adding explicit 'Project Staffing Plan uploaded to project folder prior to turnover' language to Sec. 9.5 directives and PM JD. | Precon / Mobilization | PM=A/R; GS=R; BM=C; Safety=C; Purchasing=C; Prefab=C
9.4.190 – Document Filing Standards | File incoming/outgoing project documents to the correct system and folder (by document type). | Project Manager | Document Control – | ✔ Covered |  | Documentation Management | A
9.4.190 – Document Filing Standards | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Site Administrator | Document Control – | ✔ Covered |  | Documentation Management | R
9.4.745 – Manage Field Rework | Authorize & Plan | Foreman | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | A: Project Manager ¦ R: Foreman ¦ C: General Superintendent; Project Engineer / APM; QA/QC ¦ I: Crew
9.4.745 – Manage Field Rework | Classify & Route | APM | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | A: Project Manager ¦ R: Project Engineer / APM ¦ C: General Superintendent; QA/QC ¦ I: Foreman
9.4.745 – Manage Field Rework | Classify & Route | Project Engineer | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | A: Project Manager ¦ R: Project Engineer / APM ¦ C: General Superintendent; QA/QC ¦ I: Foreman
9.4.745 – Manage Field Rework | Classify & Route | Project Manager | Ch.9: Changed Work or Changed Conditions – GSL’s Field Leadership... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | A: Project Manager ¦ R: Project Engineer / APM ¦ C: General Superintendent; QA/QC ¦ I: Foreman
9.4.745 – Manage Field Rework | Execute & Track | General Superintendent | Ch.9: Productivity- Foremen and Lead Men shall be accountable... | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | A: Project Manager ¦ R: Foreman ¦ C: General Superintendent; Project Engineer / APM ¦ I: Accounting
9.4.745 – Manage Field Rework | File & Report | APM | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | A: Project Engineer / APM ¦ R: Project Engineer / APM ¦ C: Project Manager; QA/QC ¦ I: Foreman; General Superintendent
9.4.745 – Manage Field Rework | File & Report | Project Engineer | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | A: Project Engineer / APM ¦ R: Project Engineer / APM ¦ C: Project Manager; QA/QC ¦ I: Foreman; General Superintendent
9.4.745 – Manage Field Rework | Verify & Close | QA | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | A: QA/QC ¦ R: QA/QC ¦ C: Foreman; Project Manager ¦ I: Project Engineer / APM; General Superintendent
9.4.745 – Manage Field Rework | Verify & Close | QC | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered | No change required (SOP rewritten and aligned). | Quality / Rework Management | A: QA/QC ¦ R: QA/QC ¦ C: Foreman; Project Manager ¦ I: Project Engineer / APM; General Superintendent

## Redline Recs
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category | Redline Proposal
9.2.010 – Team Selection | Branch Manager approves staffing plan | Branch Manager | Sec. 9.6 Branch Mgmt (operations control) | ⚠ Gap – approval not explicit | Add approval language to Sec. 9.6. | Team selection and turnover | Amend Sec. 9.6 Branch Mgmt (operations control) to include: Add approval language to Sec. 9.6.
9.2.010 – Team Selection | Safety Coordinator advises on assignments | Safety Coordinator | Sec. 7.2.6 JD (safety hazard identification) | ⚠ Gap – advisory role not explicit | Add cross-check with Safety Coordinator. | Team selection and turnover | Amend Sec. 7.2.6 JD (safety hazard identification) to include: Add cross-check with Safety Coordinator.
9.2.020 – Project Turnover Meeting | Prepare meeting agenda and minutes | Project Manager | Sec. 9.5 PM (meeting leadership) | ⚠ Gap – agenda/minutes not required | Add to Sec. 9.5: PM must issue minutes within 48 hrs. | Team selection and turnover | Amend Sec. 9.5 PM (meeting leadership) to include: Add to Sec. 9.5: PM must issue minutes within 48 hrs.
9.2.030 – Review Contract for High-Risk Clauses | Escalate risks and prepare mitigation plan | PM, Branch Manager | Sec. 9.14 Contract Mgr (risk oversight), Sec. 9.13 BM (contracts) | ⚠ Gap – mitigation plan not explicit | Add checklist/mitigation step. | Scope and contract review | Amend Sec. 9.14 Contract Mgr (risk oversight), Sec. 9.13 BM (contracts) to include: Add checklist/mitigation step.
9.2.040 – PM Reviews Plans, Specs & Schedule | Complete Scope & Schedule Checklist | Project Manager | Not explicit in directives | ⚠ Gap – checklist requirement | Add checklist reference to Sec. 9.5. | Scope and contract review | Amend Not explicit in directives to include: Add checklist reference to Sec. 9.5.
9.2.040 – PM Reviews Plans, Specs & Schedule | Integrate results into PEP | Project Manager | Sec. 7.3.1 PM JD (planning & PEP) | ⚠ Gap – explicit PEP update not required | Add to PM JD/Directive 9.5. | Scope and contract review | Amend Sec. 7.3.1 PM JD (planning & PEP) to include: Add to PM JD/Directive 9.5.
9.2.050 – FS Reviews Plans, Specs & Schedule | Integrate findings into PEP | Project Manager | Sec. 9.5 PM (job planning) | ⚠ Gap – PEP update not explicit | Add to Sec. 9.5: PM integrates FS findings. | Scope and contract review | Amend Sec. 9.5 PM (job planning) to include: Add to Sec. 9.5: PM integrates FS findings.
9.2.060 – Create Issue List & RFI | Escalate major issues to Branch Manager | PM & GS | Sec. 9.14 Contract Mgr (notice requirements) | ⚠ Gap – escalation step not explicit | Add escalation language to Sec. 9.5. | Scope and contract review | Amend Sec. 9.14 Contract Mgr (notice requirements) to include: Add escalation language to Sec. 9.5.
9.2.070 – Conduct Site Visit | Integrate findings into PEP | Project Manager | Sec. 9.5 PM (site visits, job planning) | ✔ Covered | No change required (SOP updated). | Scope and contract review | No redline required; SOP updated to explicitly require PEP integration and action tracking.
9.2.057 – VE & Prefab | Record opportunities in VE log | Project Manager | Not explicit in directives | ⚠ Gap – VE log not required | Add VE log requirement in Sec. 9.5. | Buyout process | Amend Not explicit in directives to include: Add VE log requirement in Sec. 9.5.
9.1.050 – Construction Takeoff | Finalize & upload takeoff results | Project Manager | Not explicit in directives | ⚠ Gap – upload requirement | Add takeoff upload requirement to Sec. 9.5. | Buyout process | Amend Not explicit in directives to include: Add takeoff upload requirement to Sec. 9.5.
9.2.020 – Procurement of Large Feeder Wire | Approve submittals before release | Project Manager | Not explicit in directives | ⚠ Gap – submittal approval requirement | Add to Sec. 9.5: PM must verify submittals before release. | Buyout process | Amend Not explicit in directives to include: Add to Sec. 9.5: PM must verify submittals before release.
9.3.030 – Fencing & Access Control | Monitor access control | Security Personnel | Not explicit in directives | ⚠ Gap – role not formalized | Add security monitoring responsibility to Sec. 9.5. | Mobilization | Amend Not explicit in directives to include: Add security monitoring responsibility to Sec. 9.5.
9.3.040 – Setup Temporary Power | Install panels/wiring/grounding | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization | Amend Not explicit in directives to include: Add subcontractor accountability to Sec. 9.5.
9.3.070 – Setup Temporary Lighting | Install temporary lighting | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization | Amend Not explicit in directives to include: Add subcontractor accountability to Sec. 9.5.
9.3.090 – Setup Security | Daily monitoring of access points | Security Personnel | Not explicit in directives | ⚠ Gap – security personnel not formalized | Add security responsibilities to Sec. 9.5. | Mobilization | Amend Not explicit in directives to include: Add security responsibilities to Sec. 9.5.
9.3.110 – Setup Equipment Staging | Position equipment safely | Equipment Operators | Not explicit in directives | ⚠ Gap – equipment operator role not formalized | Add operator role into mobilization directive. | Mobilization | Amend Not explicit in directives to include: Add operator role into mobilization directive.
9.4.010 – Coordination Meetings | Provide design clarifications | Design Team / Consultants | Not explicit in directives | ⚠ Gap – design consultant role not formalized | Add consultant clarification role to Sec. 9.5. | Coordination | Amend Not explicit in directives to include: Add consultant clarification role to Sec. 9.5.
9.4.020 – Subcontractor Meetings | Provide progress/manpower updates | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor reporting requirements. | Coordination | Amend Not explicit in directives to include: Add subcontractor reporting requirements.
9.4.030 – Client Meetings | Approve changes/raise concerns | Client/Owner | Not in directives | ⚠ Gap | Owner role external to GSL; clarify interface protocols. | Coordination | Amend Not in directives to include: Owner role external to GSL; clarify interface protocols.
9.4.040 – Safety Meetings | Participate in meetings | All Employees | Not in directives | ⚠ Gap | Include participation expectation in JD handbook. | Safety Management | Amend Not in directives to include: Include participation expectation in JD handbook.
9.4.060 – Quality Meetings | Review quality inspections | Quality Inspector | Not in directives | ⚠ Gap | Add inspector responsibilities into QA directive. | Quality Control | Amend Not in directives to include: Add inspector responsibilities into QA directive.
9.5.010 – Commissioning Meetings | Define testing requirements | Commissioning Agent | Not in directives | ⚠ Gap | Add commissioning agent scope reference. | Quality Control | Amend Not in directives to include: Add commissioning agent scope reference.
9.5.010 – Commissioning Meetings | Provide documentation/manpower | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor commissioning duties. | Coordination | Amend Not in directives to include: Add subcontractor commissioning duties.
9.5.010 – Commissioning Meetings | Ensure commissioning compliance | Quality Inspector | Not in directives | ⚠ Gap | Add QA/QC commissioning accountability. | Quality Control | Amend Not in directives to include: Add QA/QC commissioning accountability.
9.6.010 – Closeout Meetings | Submit closeout docs | Subcontractors | Not in directives | ⚠ Gap | Include subcontractor closeout requirements. | Project Closeout | Amend Not in directives to include: Include subcontractor closeout requirements.
9.6.010 – Closeout Meetings | Confirm acceptance of deliverables | Client/Owner | Not in directives | ⚠ Gap | Owner external – clarify acceptance protocols. | Project Closeout | Amend Not in directives to include: Owner external – clarify acceptance protocols.
9.4.190 – Document Filing Standards | Standardize filing structure, naming, version control, audits, and closeout archiving. | Site Administrator | Document Control – | ✔ Covered |  | Documentation Management | Rewrite SOP in template; expand procedure to include folder setup, naming rules, version control, periodic audits, and closeout package archiving; normalize roles.
9.4.200 – Submittals | Provide shop drawings/product data | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor submittal duties. | Documentation Management | Amend Not in directives to include: Add subcontractor submittal duties.
9.4.205 – RFIs | Subcontractors required to draft/support RFIs | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor RFI responsibilities to directives. | Scope & Change Control | Amend Not explicit in directives to include: Add subcontractor RFI responsibilities to directives.
9.4.210 – Meeting Minutes | Minutes responsibility clarity | Site Administrator | Not explicit in directives | ⚠ Gap | Explicitly assign Site Admin responsibility for meeting minutes. | Communication | Amend Not explicit in directives to include: Explicitly assign Site Admin responsibility for meeting minutes.
9.4.215 – Daily Reports | Foremen/Subcontractors required to submit daily reports | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor daily report requirement. | Labor Management | Amend Not explicit in directives to include: Add subcontractor daily report requirement.
9.4.220 – Drawing Logs | Subcontractors to submit updated drawings | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor drawing log submission. | Documentation Management | Amend Not explicit in directives to include: Add subcontractor drawing log submission.
9.4.225 – Specifications | Subcontractor input on spec compliance | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor compliance review of specs. | Documentation Management | Amend Not explicit in directives to include: Require subcontractor compliance review of specs.
9.4.230 – Correspondence | Subcontractors required to provide written correspondence trail | Subcontractors | Not explicit in directives | ⚠ Gap | Include subcontractor correspondence duty. | Communication | Amend Not explicit in directives to include: Include subcontractor correspondence duty.
9.4.235 – Permits | Authority responsibility for inspections | Regulatory Authorities | External role | ⚠ Gap | Clarify external agency responsibility protocol. | Safety Management | Amend External role to include: Clarify external agency responsibility protocol.
9.4.240 – Inspections | Subcontractors must close open deficiencies | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor inspection compliance duties. | Quality Control | Amend Not explicit in directives to include: Add subcontractor inspection compliance duties.
9.6.020 – Punch Lists | Subcontractors provide completion evidence | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor punch list responsibilities. | Project Closeout | Amend Not explicit in directives to include: Add subcontractor punch list responsibilities.
9.4.315 – Develop Schedule | Superintendent role not explicit in directives | Superintendent | Not explicit in directives | ⚠ Gap | Clarify Superintendent role in directive 9.4 for schedule input. | Scheduling | Amend Not explicit in directives to include: Clarify Superintendent role in directive 9.4 for schedule input.
9.4.330 – Recovery Plans | Superintendent adjustments not explicit | Superintendent | Not explicit in directives | ⚠ Gap | Add Superintendent labor/equipment adjustment duties. | Scheduling | Amend Not explicit in directives to include: Add Superintendent labor/equipment adjustment duties.
9.4.340 – Resource-Loaded | Foreman role missing for crew-level validation | Field Foreman | Not explicit in directives | ⚠ Gap | Add Foreman resource feedback duty. | Labor Management | Amend Not explicit in directives to include: Add Foreman resource feedback duty.
9.4.345 – Schedule Review Meetings | Consultant participation not explicit | Consultants | Not explicit in directives | ⚠ Gap | Add consultant role in review meetings if applicable. | Coordination | Amend Not explicit in directives to include: Add consultant role in review meetings if applicable.
9.4.350 – Schedule Change Requests | Log requests | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty to maintain change request log. | Documentation Management | Amend Not explicit in directives to include: Add Site Admin duty to maintain change request log.
9.4.360 – Change Orders | Maintain CO log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for CO logs. | Documentation Management | Amend Not explicit in directives to include: Add Site Admin duty for CO logs.
9.4.380 – Backcharges | Process financial impacts | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for backcharge tracking. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty for backcharge tracking.
9.4.385 – Force Account Work | Process billing | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for force account billing. | Cost Control & Billing | Amend Not explicit in directives to include: Add explicit Accounting duty for force account billing.
9.4.385 – Force Account Work | File and log records | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for FA logs. | Documentation Management | Amend Not explicit in directives to include: Add Site Admin duty for FA logs.
9.4.390 – Claims | Assist with disputes | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role. | Scope & Change Control | Amend Not explicit in directives to include: Add Legal Counsel advisory role.
9.4.390 – Claims | Maintain claim log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for claim logs. | Documentation Management | Amend Not explicit in directives to include: Add Site Admin duty for claim logs.
9.2.140 – Project Budget | Review/input budget | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to record project budget. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to record project budget.
9.4.400 – Monitor Project Costs | Maintain detailed cost tracking | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for cost monitoring. | Cost Control & Billing | Amend Not explicit in directives to include: Add explicit Accounting duty for cost monitoring.
9.4.405 – Manage Cost Forecasts | Provide backup and adjustments | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting responsibility for forecast inputs. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting responsibility for forecast inputs.
9.4.410 – Manage Cost Codes | Ensure alignment with company standards | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to align cost codes with financial systems. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to align cost codes with financial systems.
9.4.415 – Manage Committed Costs | Maintain records | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for committed cost records. | Cost Control & Billing | Amend Not explicit in directives to include: Add explicit Accounting duty for committed cost records.
9.4.420 – Manage Actual Costs | Track invoices and payroll | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting role for actual costs. | Cost Control & Billing | Amend Not explicit in directives to include: Add explicit Accounting role for actual costs.
9.4.425 – Manage Job Cost Reports | Provide accounting input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for job cost reports. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty for job cost reports.
9.4.430 – Manage Profit Projections | Verify financial data | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify data for projections. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to verify data for projections.
9.4.435 – Manage Cost-to-Complete | Provide actual data input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for actuals in cost-to-complete. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty for actuals in cost-to-complete.
9.4.440 – Prepare Billing Schedule | Confirm owner agreement | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for billing schedule. | Communication | Amend Not explicit in directives to include: Add client approval protocol for billing schedule.
9.4.445 – Monthly Pay Applications | Provide invoices/payment records | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to provide records for pay apps. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to provide records for pay apps.
9.4.445 – Monthly Pay Applications | Approve payment | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for pay applications. | Communication | Amend Not explicit in directives to include: Add client approval protocol for pay applications.
9.4.450 – Track Accounts Receivable | Track AR aging and follow up on collections | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to maintain AR aging and collections follow-up. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to maintain AR aging and collections follow-up.
9.4.455 – Manage Lien Waivers | Track lien waivers and verify with pay apps | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to track lien waivers with pay apps. | Documentation Management | Amend Not explicit in directives to include: Add Accounting duty to track lien waivers with pay apps.
9.4.455 – Manage Lien Waivers | Maintain lien waiver log | Site Administrator | Not explicit in directives | ⚠ Gap | Assign Site Admin to maintain lien waiver log. | Documentation Management | Amend Not explicit in directives to include: Assign Site Admin to maintain lien waiver log.
9.4.455 – Manage Lien Waivers | Provide executed lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor submission of lien waivers before payment. | Documentation Management | Amend Not explicit in directives to include: Require subcontractor submission of lien waivers before payment.
9.4.460 – Manage Retainage | Verify amounts withheld and released | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify retainage withheld/released. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to verify retainage withheld/released.
9.4.465 – Manage Final Invoicing | Review final invoice and submit for payment | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to review and submit final invoice. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to review and submit final invoice.
9.4.465 – Manage Final Invoicing | Submit final pay apps and lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor final pay apps and lien waivers. | Cost Control & Billing | Amend Not explicit in directives to include: Require subcontractor final pay apps and lien waivers.
9.4.495 – Investigate Accidents | Advise on legal implications as needed | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role in accident investigations. | Safety Management | Amend Not explicit in directives to include: Add Legal Counsel advisory role in accident investigations.
9.4.745 – Manage Field Rework | Rewrite SOP in Master Template | Project Manager | Ch.7 JD (Foreman): Maintain all field records for the projects; Ch.9: Schedule Delays or Impacts – ... | ✔ Closed – Updated | Complete. | Quality / Rework Management | Rebuilt SOP using GSL_SOP_Master_Template; normalized roles; added timecard/job plan + daily report controls; added authorization routing for changed conditions.
9.2.010 – Team Selection | Add explicit deliverable control: staffing plan upload/distribution prior to turnover. | PM | Sec. 9.5 (document control intent) | N/A | N/A | Precon / Mobilization | Add to PM JD and/or directives as needed.
9.2.010 – Team Selection | Expand Procedure steps to include manpower projection update, risk-based safety coverage, and procurement/prefab support. | PM | Sec. 9.4; Sec. 9.5 | N/A | N/A | Precon / Mobilization | Update SOP procedure per v4 rewrite.
9.2.010 – Team Selection | Update Related SOPs to 9.2.015 and 9.2.040; remove legacy numbering from SOP body. | PM | Crosswalk governance | N/A | N/A | Precon / Mobilization | Update related SOP references.
9.4.190 – Document Filing Standards | Maintain field-level docs in Procore | Field Foreman | Not in directives | ⚠ Gap | Add field documentation requirement. | Documentation Management | Amend Not in directives to include: Add field documentation requirement.
9.4.745 – Manage Field Rework | Standardize roles and tracking requirements for field rework (timecards/job plans, daily reports, authorization routing). | Project Manager | Time Cards and Job Plans –; Schedule Delays or Impacts –; Changed Work or Changed Conditions – | Aligned |  | 194 – Quality Control | Applied in rewritten SOP 9.4.745 (template-based).

## Conflict Matrix
SOP Title | Conflict Description | Conflict Type | Resolution Recommendation
9.2.010 – Team Selection | Staffing responsibility split between PM, GS, Branch Manager | Cadence Clash / Authority Chain | Clarify final approver in Directive 9.6.
9.2.020 – Project Turnover Meeting | Agenda/minutes responsibility unclear between Estimator and PM | Document Control | Assign PM as A, Estimator as R.
9.2.030 – Review Contract | Contract risk review split across PM, BM, CM | Authority Chain / Financial Accountability | Define PM as R, CM as C, BM as A.
9.2.040 – Plan Review | PM and GS both reviewing manpower/schedule | Schedule Ownership | PM = A, GS = C.
9.2.050 – FS Plan Review | FS and PM both reviewing constructability | Schedule Ownership | FS = R, PM = A.
9.2.060 – RFI Process | PM, FS, BM all involved in escalation | Authority Chain / Document Control | Define PM = A, FS = R, BM = I.
9.2.070 – Site Visit | FS, PM, GS, Safety Coordinator all reviewing site conditions | Cadence Clash / Safety Accountability | FS = R, Safety = C, PM = A.
9.2.055 – Est. vs. Planned | PM, GS, BM all validating manpower/budget | Financial Accountability | PM = A, GS = C, BM = I.
9.2.057 – VE & Prefab | PM, Estimator, Prefab Lead, FS all inputting | Authority Chain / Document Control | PM = A, Prefab = R, Estimator = C, FS = I.
9.1.050 – Takeoff | PM, Estimator, FS, Purchasing all using takeoff | Document Control / Financial Accountability | PM = A, Estimator = C, FS = C, Purchasing = R.
9.3.040 – Temporary Power | PM, FS, and Subcontractor roles overlap in installation oversight | Authority Chain / Safety Accountability | Define Subcontractor = R, FS = C, PM = A, Safety = C.
9.3.050 – Temporary Water | PM vs. FS overlap on utility coordination | Authority Chain | PM = A (coordination), FS = R (execution).
9.3.060 – Sanitary Facilities | PM contracts vendors, FS decides placement | Authority Chain | PM = A, FS = R, Safety = C.
9.3.070 – Temporary Lighting | FS and Subcontractor both installing/verifying lighting | Authority Chain | Subcontractor = R, FS = C.
9.3.090 – Security | PM, FS, Safety, Security Personnel all involved in monitoring | Authority Chain / Cadence Clash | PM = A, FS = C, Safety = C, Security = R.
9.3.110 – Equipment Staging | FS and Operators overlap in positioning equipment | Authority Chain | Operators = R, FS = A.
9.4.010 – Coordination Meetings | PM leads, FS contributes, Site Admin records, Consultant clarifies | Document Control | PM = A, FS = C, Site Admin = R (minutes), Consultants = I.
9.4.020 – Subcontractor Meetings | PM, FS, and subcontractors overlap on logistics & manpower reporting | Authority Chain | PM = A, Subcontractors = R, FS = C.
9.4.030 – Client Meetings | PM and BM both leading/representing GSL to client | Authority Chain | PM = R, BM = A.
9.4.040 – Safety Meetings | PM, FS, Safety all reinforcing messages | Cadence Clash | Safety = R, PM = A, FS = C.
9.4.050 – Prefab Meetings | PM, Prefab Lead, FS, GS all validating strategies | Authority Chain | Prefab Lead = R, PM = A, FS/GS = C.
9.4.060 – Quality Meetings | PM, FS, Safety, Quality Inspector all reviewing compliance | Authority Chain | Quality Inspector = R, PM = A, FS/Safety = C.
9.5.010 – Commissioning Meetings | PM, Commissioning Agent, Subs, QA all accountable for deliverables | Authority Chain | Commissioning Agent = R, PM = A, QA/Subs = C.
9.6.010 – Closeout Meetings | PM, FS, Subs, Client all determining readiness | Authority Chain / Client Interface | PM = A, Subs = R, FS = C, Client = I.
9.4.190 – Document Filing Standards | Accountability overlap: PM vs Site Administrator vs Branch Manager for documentation governance and compliance. | Document Control | PM = A (project execution); Site Administrator = R (implementation + maintenance); Branch Manager = A (governance/audit cadence).
9.4.200 – Submittals | PM, Purchasing, Subs all responsible for submittal flow | Document Control | PM = A, Purchasing = C, Subs = R.
9.4.300 – A/E Communications | PM and FS both addressing design issues | Authority Chain | PM = A, FS = C, SA = R (logging).
9.4.310 – GC Communications | PM vs. Site Admin overlap in correspondence control | Document Control | PM = A, SA = R.
9.4.320 – Update Schedule | PM and Superintendent roles overlap in schedule updates | Schedule Ownership | PM = A, Superintendent = C.
9.4.325 – Monitor Performance | PM and BM overlap in review authority | Authority Chain | PM = R, BM = A, Superintendent = C.
9.4.335 – Lookahead Schedules | PM, Superintendent, and Foreman overlap in short-term planning | Cadence Clash | PM = A, Superintendent = C, Foreman = R.
9.4.340 – Resource-Loaded | PM, Superintendent, BM all approving resources | Authority Chain | PM = A, Superintendent = C, BM = C.
9.4.350 – Schedule Change Requests | PM vs. Branch Manager overlap in approval authority | Authority Chain | PM = R, BM = A.
9.4.360 – Change Orders | PM, Estimator, BM all touching COs | Authority Chain | PM = R, Estimator = C, BM = A.
9.4.380 – Backcharges | PM approves, Accounting tracks — overlap risk | Financial Accountability | PM = A, Accounting = R.
9.4.385 – Force Account Work | PM, FS, Accounting, SA all handling documents | Document Control | PM = A, FS = R, Accounting = C, SA = C.
9.4.390 – Claims | PM, Estimator, BM, Legal all involved | Authority Chain | PM = R, BM = A, Estimator = C, Legal = C, SA = I.
9.2.140 – Project Budget | PM, Estimator, Accounting, BM overlap on budget ownership | Financial Accountability | PM = R, BM = A, Estimator = C, Accounting = C.
9.4.400 – Monitor Costs | PM and Accounting both monitoring costs | Financial Accountability | PM = A, Accounting = R.
9.4.410 – Cost Codes | PM vs. Accounting overlap on maintaining codes | Document Control | PM = A, Accounting = C.
9.4.415 – Committed Costs | PM, BM, and Accounting all approving/recording commitments | Financial Accountability | PM = R, BM = A, Accounting = C.
9.4.425 – Job Cost Reports | PM, BM, Accounting overlap in preparing/validating reports | Authority Chain | PM = R, BM = A, Accounting = C.
9.4.430 – Profit Projections | PM, BM, Accounting overlap in projections | Financial Accountability | PM = R, BM = A, Accounting = C.
9.4.440 – Billing Schedule | PM prepares, BM reviews, Owner approves | Authority Chain / Client Interface | PM = R, BM = A, Owner = I.
9.4.445 – Pay Applications | PM, BM, Accounting, and Owner all involved in approvals | Financial Accountability | PM = R, BM = A, Accounting = C, Owner = I.
9.4.450 – Accounts Receivable | PM vs. Accounting escalation vs. tracking | Financial Accountability | PM = A (escalation), Accounting = R (tracking), BM = C.
9.4.455 – Lien Waivers | PM, Accounting, Site Admin, Subs all touching waivers | Document Control | PM = A, Site Admin = R (log), Accounting = C, Subs = R (submission).
9.4.460 – Retainage | PM, Accounting, BM overlap on release | Financial Accountability | PM = R, Accounting = C, BM = A.
9.4.465 – Final Invoicing | PM prepares, Accounting submits, BM approves | Authority Chain | PM = R, Accounting = C, BM = A, Subs = R (final pay apps).
9.3.470 – SSSP | Safety drafts, PM approves, BM audits, FS implements | Authority Chain / Safety Accountability | Safety = R, PM = A, BM = C, FS = R (implementation).
9.4.490 – Incident Reporting | FS initial report vs. Safety official report vs. PM escalation | Document Control / Safety Accountability | Safety = R, FS = R (initial), PM = A, BM = I.
9.4.495 – Accident Investigation | Safety leads, PM/FS support, BM approves, Legal advises | Authority Chain | Safety = R, PM = C, FS = C, BM = A, Legal = C.
9.4.745 – Manage Field Rework | Roles in SOP did not match standard role naming (e.g., Site Administrator; Quality Inspector). | Role mismatch | Normalize to PM/GS/Foreman/QA-QC and update matrices.
9.4.745 – Manage Field Rework | Procedure did not require timecard/job plan and daily report capture for rework impacts. | Control gap | Add explicit tracking requirements and reporting steps; update RACI/Coverage matrices.
9.4.745 – Manage Field Rework | No explicit routing for changed conditions / authorization prior to performing work. | Authorization gap | Add classification + PM authorization + change-management routing in Steps 2–3.
9.2.010 – Team Selection | Legacy SOP number referenced in source; remove from SOP output per governance (legacy stays only in crosswalk/metadata). | Governance | Ensure rewritten SOP uses current SOP ID and excludes legacy alias in title/body/related SOPs.
9.4.190 – Document Filing Standards | PM vs. Site Admin vs. Branch Mgr all accountable for documentation | Document Control | PM = A, Site Admin = R, BM = C.
9.4.745 – Manage Field Rework | Legacy SOP used non-standard roles (Quality Inspector/Site Administrator) and lacked explicit directive controls for timecards/job plans, schedule impacts, and changed work authorization. | Role mismatch / control gap | Rewrite SOP with standardized roles (PM/GS/Foreman/PE-APM/QA-QC) and add directive-required controls (timecards/job plans, daily report schedule impacts, changed work authorization).

## Closeout Checklist
Role | Closeout Task | Directive Section | Coverage Status
Project Manager | Submit O&M manuals and warranty letters | Sec. 9.13 PM Directives | ✔ Covered
Project Manager | Ensure all RFIs, Submittals, and Change Orders are closed | Sec. 9.5 PM Directives | ✔ Covered
Field Supervisor | Submit daily reports and as-built drawings | Sec. 9.3 Field Leadership | ✔ Covered
General Superintendent | Confirm apprentice/journeyman ratios and manpower demobilization | Sec. 9.4 GS | ✔ Covered
Safety Coordinator | Conduct final site safety audit and turnover report | Sec. 7.2.6 JD | ✔ Covered
Branch Manager | Approve final project closeout package | Sec. 9.6 Branch Mgmt | ✔ Covered
Purchasing | Ensure all POs and vendor accounts are closed | Sec. 9.16 Purchasing | ✔ Covered
Business Manager | Submit retention billings and financial closeout | Sec. 9.13 BM | ✔ Covered
Contract Manager | Confirm all notices and claims are resolved | Sec. 9.14 CM | ✔ Covered
Project Manager | Compile and submit final As-Built Drawings to Owner | SOP 9.6.030 | ✔ Covered
Field Supervisor | Record field changes and update redline drawings | SOP 9.6.030 | ✔ Covered
Subcontractors | Provide redline markups of installed work | SOP 9.6.030 | ⚠ Gap – not explicit in directives
Project Manager | Review and confirm completeness of O&M Manuals | SOP 9.6.040 | ✔ Covered
Subcontractors | Submit O&M manuals per specifications | SOP 9.6.040 | ⚠ Gap – not explicit in directives
Project Manager | Review warranty requirements and ensure compliance | SOP 9.6.050 | ✔ Covered
Subcontractors | Submit warranty certificates | SOP 9.6.050 | ⚠ Gap – not explicit in directives
Site Administrator | Log and organize warranty documentation | SOP 9.6.050 | ✔ Covered
Project Manager | Oversee full closeout documentation package | SOP 9.6.060 | ✔ Covered
Site Administrator | Compile documents into closeout package | SOP 9.6.060 | ✔ Covered
Subcontractors | Provide final deliverables for closeout | SOP 9.6.060 | ⚠ Gap – not explicit in directives
Owner/Client | Review and accept final closeout documentation | SOP 9.6.060 | ⚠ Gap – external role, requires protocol
Project Manager | Ensure final billing aligns with contract | SOP 9.4.440 / 445 | ✔ Covered
Branch Manager | Approve final pay applications | SOP 9.4.445 | ✔ Covered
Accounting | Process and record final invoices | SOP 9.4.445 | ⚠ Gap – not explicit in directives
Client/Owner | Approve final payment | SOP 9.4.445 | ⚠ Gap – external role, requires protocol
Project Manager | Collect and confirm all lien waivers before final payment | SOP 9.4.455 / 465 | ✔ Covered
Accounting | Verify lien waivers with each pay app and track retainage balances | SOP 9.4.455 / 460 | ⚠ Gap – add directive coverage
Branch Manager | Approve final retainage release and final invoice | SOP 9.4.460 / 465 | ✔ Covered
Foreman | Confirm all rework items are logged, assigned, and labor hours captured in timecards/job plans. | Ch.7 JD (Foreman): Maintain all field records for the projects | ✔ Covered
QA/QC | Verify corrected work meets acceptance criteria and sign off closure in rework log / NCR as applicable. | Ch.9: Productivity- ... / Quality expectations; Ch.7 (Foreman): Quality | ✔ Covered
General Superintendent | Review open rework items in weekly field planning; remove blockers; confirm schedule impacts documented. | Ch.9: Schedule Delays or Impacts – ... | ✔ Covered
Project Manager | Ensure all rework documentation is filed and rework trends are reviewed; ensure change-management applied if billable. | Ch.9: Changed Work or Changed Conditions – ... | ✔ Covered
Project Manager | Verify final project documentation is complete and folders are standardized/archived per SOP 9.4.190 (final versions, closeout package ready). | SOP 9.4.190 | ✔ Covered
Site Administrator | Audit and archive project folders per SOP 9.4.190; ensure current vs archived separation and closeout package compiled. | SOP 9.4.190 | ✔ Covered
Foreman | Confirm rework hours/quantities captured on timecards/job plans and schedule impacts documented in daily reports. | Time Cards and Job Plans –; Schedule Delays or Impacts – | ✔ Covered
Project Engineer / APM | Ensure Rework Log is closed and all supporting records (photos, verification, NCR/field problem docs) are filed in project records. | Document Control – | ✔ Covered
QA/QC | Verify corrected work meets drawings/specs and document verification; release item for closeout. | Pre-Fab and Quality Control – | ✔ Covered

## Role Alignment Matrix
SOP Title | Category | Accounting | All Employees | Branch Manager | Client/Owner | Commissioning Agent | Consultants | Design Team / Consultants | Electrical Subcontractor | Equipment Operators | Estimator | Field Foreman | Field Supervisor | Foreman / Field Supervisor | General Superintendent | IT/Communications | Legal Counsel | PM & GS | PM, Branch Manager | PM, Branch Mgr, GS, Field Leadership, Prefab, Safety | Prefab Lead | Prefabrication Lead | Project Manager | Project Engineer / APM | Purchasing | Quality Inspector | Regulatory Authorities | Safety Coordinator | Security Personnel | Site Administrator | Subcontractors | Superintendent
9.2.010 – Team Selection | Team selection and turnover |  |  | X | [10 empty] | X | [7 empty] | X |  |  |  |  | X
9.2.020 – Project Turnover Meeting | Team selection and turnover | [9 empty] | X | [8 empty] | X |  |  | X
9.2.030 – Review Contract for High-Risk Clauses | Scope and contract review | [17 empty] | X |  |  |  | X
9.2.040 – PM Reviews Plans, Specs & Schedule | Scope and contract review | [21 empty] | X
9.2.050 – FS Reviews Plans, Specs & Schedule | Scope and contract review | [11 empty] | X | [9 empty] | X
9.2.060 – Create Issue List & RFI | Scope and contract review | [11 empty] | X |  |  |  |  | X |  |  |  |  | X
9.2.070 – Conduct Site Visit | Scope and contract review | [10 empty] | X | X | X | X | [7 empty] | X |  |  |  |  | X
9.2.055 – Compare Est. vs. Planned | Budget preparation |  |  | X | [6 empty] | X |  |  |  | X | [7 empty] | X
9.2.057 – VE & Prefab | Buyout process | [9 empty] | X |  | X | [8 empty] | X | X
9.1.050 – Construction Takeoff | Buyout process | [9 empty] | X |  | X | [9 empty] | X |  | X
9.2.020 – Procurement of Large Feeder Wire | Buyout process | [12 empty] | X | X | [7 empty] | X
9.2.080 – Material Handling Plan | Material handling plan | [11 empty] | X | [9 empty] | X |  |  |  |  | X
9.2.090 – Develop Labor Budget | Budget preparation |  |  | X | [6 empty] | X |  |  |  | X | [7 empty] | X
9.2.100 – Layout & Sequencing Plan | Layout and sequencing plan | [11 empty] | X |  | X | [7 empty] | X |  |  |  |  | X
9.2.110 – Develop Project Schedule | Schedule development |  |  | X | [10 empty] | X | [7 empty] | X |  | X
9.2.120 – Tracking & Control Systems | Tracking and control |  |  | X | [8 empty] | X | [9 empty] | X |  | X |  |  | X
9.2.130 – Kickoff Meeting | Construction execution kickoff meeting |  |  | X | [8 empty] | X |  | X | [7 empty] | X |  | X |  |  | X
9.3.010 – Office Trailer | Mobilization | [13 empty] | X | X | [6 empty] | X | [6 empty] | X
9.3.020 – Storage Trailer | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  |  | X
9.3.030 – Fencing & Access Control | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  |  | X | X
9.3.040 – Setup Temporary Power | Mobilization | [7 empty] | X |  |  |  | X | [9 empty] | X |  |  |  |  | X
9.3.050 – Setup Temporary Water | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  |  | X
9.3.060 – Setup Sanitary Facilities | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  |  | X
9.3.070 – Setup Temporary Lighting | Mobilization | [7 empty] | X |  |  |  | X | [9 empty] | X |  |  |  |  | X
9.3.080 – Setup Signage | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  |  | X
9.3.090 – Setup Security | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  |  | X | X
9.3.100 – Setup Laydown Area | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  |  | X
9.3.110 – Setup Equipment Staging | Mobilization | [8 empty] | X |  |  | X | [9 empty] | X |  |  |  |  | X
9.3.120 – Setup Parking | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  |  | X
9.4.010 – Coordination Meetings | Coordination | [6 empty] | X |  |  |  |  | X | [9 empty] | X | [6 empty] | X
9.4.020 – Subcontractor Meetings | Coordination | [11 empty] | X | [9 empty] | X | [7 empty] | X
9.4.020 – Subcontractor Meetings | Safety Management | [26 empty] | X
9.4.030 – Client Meetings | Coordination |  |  | X | X | [17 empty] | X
9.4.040 – Safety Meetings | Safety Management |  | X | [9 empty] | X | [9 empty] | X |  |  |  |  | X
9.4.050 – Prefab Meetings | Coordination | [11 empty] | X | [7 empty] | X |  | X
9.4.050 – Prefab Meetings | Labor Management | [13 empty] | X
9.4.060 – Quality Meetings | Quality Control | [11 empty] | X | [9 empty] | X |  |  | X
9.4.060 – Quality Meetings | Safety Management | [26 empty] | X
9.5.010 – Commissioning Meetings | Coordination | [21 empty] | X | [7 empty] | X
9.5.010 – Commissioning Meetings | Quality Control |  |  |  |  | X | [19 empty] | X
9.6.010 – Closeout Meetings | Project Closeout |  |  |  | X | [7 empty] | X | [9 empty] | X | [7 empty] | X
9.4.190 – Document Filing Standards | Documentation Management |  |  | X | [7 empty] | X | [10 empty] | X | [6 empty] | X
9.4.195 – Documentation System | Documentation Management |  |  | X | [18 empty] | X | [6 empty] | X
9.4.200 – Submittals | Documentation Management | [21 empty] | X |  | X | [5 empty] | X
9.4.205 – RFIs | Scope & Change Control | [29 empty] | X
9.4.210 – Meeting Minutes | Communication | [28 empty] | X
9.4.215 – Daily Reports | Labor Management | [29 empty] | X
9.4.220 – Drawing Logs | Documentation Management | [29 empty] | X
9.4.225 – Specifications | Documentation Management | [29 empty] | X
9.4.230 – Correspondence | Communication | [29 empty] | X
9.4.235 – Permits | Safety Management | [25 empty] | X
9.4.240 – Inspections | Quality Control | [29 empty] | X
9.6.020 – Punch Lists | Project Closeout | [29 empty] | X
9.4.300 – A/E Communications | Communication | [11 empty] | X | [9 empty] | X
9.4.300 – A/E Communications | Documentation Management | [28 empty] | X
9.4.310 – GC Communications | Communication | [11 empty] | X | [9 empty] | X
9.4.310 – GC Communications | Documentation Management | [28 empty] | X
9.4.315 – Develop Project Schedule | Scheduling | [21 empty] | X
9.4.315 – Develop Schedule | Scheduling | [30 empty] | X
9.4.320 – Update Project Schedule | Scheduling | [21 empty] | X | [8 empty] | X
9.4.325 – Monitor Schedule Performance | Labor Management | [30 empty] | X
9.4.325 – Monitor Schedule Performance | Scheduling | [21 empty] | X
9.4.330 – Recovery Plans | Cost Control |  |  | X
9.4.330 – Recovery Plans | Scheduling | [21 empty] | X | [8 empty] | X
9.4.335 – Lookahead Schedules | Labor Management | [10 empty] | X | [19 empty] | X
9.4.335 – Lookahead Schedules | Scheduling | [21 empty] | X
9.4.340 – Resource-Loaded | Labor Management | [10 empty] | X
9.4.340 – Resource-Loaded Schedules | Labor Management | [30 empty] | X
9.4.340 – Resource-Loaded Schedules | Materials Management |  |  | X
9.4.340 – Resource-Loaded Schedules | Scheduling | [21 empty] | X
9.4.345 – Schedule Review Meetings | Coordination |  |  | X |  |  | X
9.4.345 – Schedule Review Meetings | Labor Management | [10 empty] | X
9.4.345 – Schedule Review Meetings | Scheduling | [21 empty] | X | [8 empty] | X
9.4.350 – Schedule Change Requests | Documentation Management | [28 empty] | X
9.4.350 – Schedule Change Requests | Scheduling |  |  | X | [18 empty] | X
9.4.355 – Project Scope | Scope & Change Control |  |  | X | [18 empty] | X
9.4.360 – Change Orders | Cost Control & Billing | [9 empty] | X
9.4.360 – Change Orders | Documentation Management | [28 empty] | X
9.4.360 – Change Orders | Scope & Change Control |  |  | X | [18 empty] | X
9.4.365 – PCOs | Cost Control & Billing | [9 empty] | X
9.4.365 – PCOs | Scope & Change Control | [21 empty] | X
9.4.370 – Owner Directives | Scope & Change Control |  |  | X | [18 empty] | X
9.4.375 – Scope Clarifications | Scope & Change Control | [9 empty] | X | [11 empty] | X
9.4.380 – Backcharges | Cost Control & Billing | X | [20 empty] | X
9.4.385 – Force Account Work | Cost Control & Billing | X
9.4.385 – Force Account Work | Documentation Management | [28 empty] | X
9.4.385 – Force Account Work | Labor Management | [11 empty] | X
9.4.385 – Force Account Work | Scope & Change Control | [21 empty] | X
9.4.390 – Claims | Cost Control & Billing | [9 empty] | X
9.4.390 – Claims | Documentation Management | [28 empty] | X
9.4.390 – Claims | Scope & Change Control |  |  | X | [12 empty] | X | [5 empty] | X
9.2.140 – Project Budget | Cost Control & Billing | X |  | X | [6 empty] | X | [11 empty] | X
9.4.400 – Monitor Project Costs | Cost Control & Billing | X |  | X | [18 empty] | X
9.4.405 – Manage Cost Forecasts | Cost Control & Billing | X | [20 empty] | X
9.4.410 – Manage Cost Codes | Cost Control & Billing | X | [20 empty] | X
9.4.415 – Manage Committed Costs | Cost Control & Billing | X |  | X
9.4.415 – Manage Committed Costs | Materials Management | [21 empty] | X
9.4.420 – Manage Actual Costs | Cost Control & Billing | X | [20 empty] | X
9.4.425 – Manage Job Cost Reports | Cost Control & Billing | X |  | X | [18 empty] | X
9.4.430 – Manage Profit Projections | Cost Control & Billing | X |  | X | [18 empty] | X
9.4.435 – Manage Cost-to-Complete | Cost Control & Billing | X |  | X | [18 empty] | X
9.4.440 – Prepare Billing Schedule | Communication |  |  |  | X
9.4.440 – Prepare Billing Schedule | Cost Control & Billing |  |  | X | [18 empty] | X
9.4.445 – Monthly Pay Applications | Communication |  |  |  | X
9.4.445 – Monthly Pay Applications | Cost Control & Billing | X |  | X | [18 empty] | X
9.4.450 – Track Accounts Receivable | Cost Control & Billing | X |  | X | [18 empty] | X
9.4.455 – Manage Lien Waivers | Documentation Management | X | [20 empty] | X | [6 empty] | X | X
9.4.460 – Manage Retainage | Cost Control & Billing | X |  | X | [18 empty] | X
9.4.465 – Manage Final Invoicing | Cost Control & Billing | X |  | X | [18 empty] | X | [7 empty] | X
9.3.470 – Site-Specific Safety Plan | Safety Management |  |  | X | [8 empty] | X | [9 empty] | X |  |  |  |  | X
9.4.475 – Safety Orientation | Safety Management | [11 empty] | X | [9 empty] | X |  |  |  |  | X
9.4.480 – Safety Inspections | Safety Management |  |  | X | [8 empty] | X | [9 empty] | X |  |  |  |  | X
9.4.485 – Safety Meetings | Safety Management | [11 empty] | X | [9 empty] | X |  |  |  |  | X
9.4.490 – Report Safety Incidents | Safety Management | [11 empty] | X | [9 empty] | X |  |  |  |  | X
9.4.495 – Investigate Accidents | Safety Management |  |  | X | [8 empty] | X |  |  |  | X | [5 empty] | X |  |  |  |  | X
9.4.745 – Manage Field Rework | Quality / Rework Management | [10 empty] | X |  | X | X | [7 empty] | X | X |  | X | [5 empty] | X

## SOP Number Crosswalk
Legacy SOP # | New SOP # | Title | SOP Title | Notes
9.41.745 | 9.4.745 | Manage Field Rework | Manage Field Rework | Legacy-to-current crosswalk entry
9.41.190A | 9.4.190 | Document Filing Standards | Document Filing Standards | Legacy-to-current crosswalk entry
9.41.035 | 9.2.070 | Conduct Site Visit | Conduct Site Visit | Legacy-to-current crosswalk entry
9.41.040 | 9.2.055 | Compare Estimated vs. Planned Performance | Compare Est. vs. Planned | Legacy-to-current crosswalk entry
9.41.005 | 9.2.010 | Team Selection | Team Selection | Reproduced sync.
9.41.045 | 9.2.057 | Identify Value Engineering & Prefabrication Opportunities | Identify Value Engineering & Prefabrication Opportunities | Reproduced sync.

## Change_Log
Timestamp | Sheet | Change Type | Details
2026-01-07T14:53:54 | GSL_SOP_Metadata | Add Column | Inserted column 'In Sharepoint' at position 3.
2026-01-07T14:53:54 | GSL_SOP_Metadata | Fill Field | Filled SOP Title for 9.4.631 from SOP File Name (was blank in v2).
2026-01-07T14:53:54 | GSL_SOP_Metadata | Add Row | Added missing SOP ID 9.4.631 from v2 for consistency.
2026-01-07T14:54:08 | Role Alignment Matrix | Add Column | Inserted column 'Project Engineer / APM' at position 25.
2026-01-07T14:54:08 | Role Alignment Matrix | Fill Column | Populated 'Project Engineer / APM' for 1 SOP rows using v2 data.
2026-01-07T14:54:20 | SOP Number Crosswalk | Add Column | Inserted column 'SOP Title' at position 4.
2026-01-07T14:54:20 | SOP Number Crosswalk | Add Column | Inserted column 'Notes' at position 5.
2026-01-07T14:54:20 | SOP Number Crosswalk | Normalize Columns | Added 'SOP Title' and 'Notes' columns for backward compatibility; populated from Title.
2026-01-07T14:54:36 | Coverage Matrix | Append Rows | Appended 29 rows merged from earlier versions.
2026-01-07T14:54:36 | RACI Matrix | Append Rows | Appended 29 rows merged from earlier versions.
2026-01-07T14:54:36 | Redline Recs | Append Rows | Appended 5 rows merged from earlier versions.
2026-01-07T14:54:36 | Conflict Matrix | Append Rows | Appended 3 rows merged from earlier versions.
2026-01-07T14:54:36 | Closeout Checklist | Append Rows | Appended 3 rows merged from earlier versions.
2026-01-07T17:40:29 | GSL_SOP_Metadata | Update Row | Updated 9.2.070 title/description/roles/tags/related SOPs and linked SOP file name.
2026-01-07T17:40:29 | SOP Number Crosswalk | Add/Update Row | Added/updated crosswalk rows for 9.41.035→9.2.070 and 9.41.040→9.2.055.
2026-01-07T17:40:29 | Coverage Matrix | Update Rows | Updated roles/directive references and closed PEP integration gap for 9.2.070.
2026-01-07T17:40:29 | RACI Matrix | Update Rows | Updated RACI roles and closed PEP integration gap for 9.2.070.
2026-01-07T17:40:29 | Redline Recs | Update Row | Marked 9.2.070 PEP integration recommendation as closed; no directive redline required.
2026-01-07T17:40:29 | Role Alignment Matrix | Update Row | Ensured Field Foreman/Field Leadership participation is represented for 9.2.070.

## Mapping_Log
Sheet | SOP Title | Source Action | Mapped Action | Role | Source Version | Match Score
Coverage Matrix | 9.2.010 – Team Selection | Coordinate with GS to confirm field leadership assignments and crew availability. | GS assigns field supervisors | PM | v4 | 0.2
Coverage Matrix | 9.2.010 – Team Selection | Coordinate with GS to confirm field leadership assignments and crew availability. | GS assigns field supervisors | GS | v4 | 0.2
Coverage Matrix | 9.4.190 – Document Filing Standards | Maintain contractual docs in Windows folders | File incoming/outgoing project documents to the correct system and folder (by document type). | Project Manager | v2 | 1
Coverage Matrix | 9.4.190 – Document Filing Standards | Organize folders & verify consistency | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Site Administrator | v2 | 1
Coverage Matrix | 9.4.190 – Document Filing Standards | Maintain contractual docs in Windows folders | File incoming/outgoing project documents to the correct system and folder (by document type). | Project Manager | v4 | 1
Coverage Matrix | 9.4.190 – Document Filing Standards | Organize folders & verify consistency | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Site Administrator | v4 | 1
Coverage Matrix | 9.4.190 – Document Filing Standards | Maintain contractual docs in Windows folders | File incoming/outgoing project documents to the correct system and folder (by document type). | Project Manager | v5 | 1
Coverage Matrix | 9.4.190 – Document Filing Standards | Organize folders & verify consistency | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Site Administrator | v5 | 1
Coverage Matrix | 9.4.190 – Document Filing Standards | Maintain contractual docs in Windows folders | File incoming/outgoing project documents to the correct system and folder (by document type). | Project Manager | v6 | 1
Coverage Matrix | 9.4.190 – Document Filing Standards | Organize folders & verify consistency | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Site Administrator | v6 | 1
Coverage Matrix | 9.4.745 – Manage Field Rework | Classify and route (NCR vs Field Problem vs internal rework) | Classify & Route | Project Manager | v2 | 1
Coverage Matrix | 9.4.745 – Manage Field Rework | Classify and route (NCR vs Field Problem vs internal rework) | Classify & Route | Project Engineer | v2 | 1
Coverage Matrix | 9.4.745 – Manage Field Rework | Classify and route (NCR vs Field Problem vs internal rework) | Classify & Route | APM | v2 | 1
Coverage Matrix | 9.4.745 – Manage Field Rework | Develop rework plan and obtain authorization | Authorize & Plan | Foreman | v2 | 1
Coverage Matrix | 9.4.745 – Manage Field Rework | Track impacts (hours/qty/schedule) and update controls | Execute & Track | General Superintendent | v2 | 1
Coverage Matrix | 9.4.745 – Manage Field Rework | Verify corrected work and close item | Verify & Close | QA | v2 | 1
Coverage Matrix | 9.4.745 – Manage Field Rework | Verify corrected work and close item | Verify & Close | QC | v2 | 1
Coverage Matrix | 9.4.745 – Manage Field Rework | File records and communicate lessons learned | File & Report | Project Engineer | v2 | 1
Coverage Matrix | 9.4.745 – Manage Field Rework | File records and communicate lessons learned | File & Report | APM | v2 | 1
RACI Matrix | 9.2.010 – Team Selection | Coordinate with GS to confirm field leadership assignments and crew availability. | GS assigns field supervisors | PM | v4 | 0.2
RACI Matrix | 9.2.010 – Team Selection | Coordinate with GS to confirm field leadership assignments and crew availability. | GS assigns field supervisors | GS | v4 | 0.2
RACI Matrix | 9.4.190 – Document Filing Standards | Maintain contractual docs in Windows folders | File incoming/outgoing project documents to the correct system and folder (by document type). | Project Manager | v2 | 1
RACI Matrix | 9.4.190 – Document Filing Standards | Organize folders & verify consistency | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Site Administrator | v2 | 1
RACI Matrix | 9.4.190 – Document Filing Standards | Maintain contractual docs in Windows folders | File incoming/outgoing project documents to the correct system and folder (by document type). | Project Manager | v4 | 1
RACI Matrix | 9.4.190 – Document Filing Standards | Organize folders & verify consistency | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Site Administrator | v4 | 1
RACI Matrix | 9.4.190 – Document Filing Standards | Maintain contractual docs in Windows folders | File incoming/outgoing project documents to the correct system and folder (by document type). | Project Manager | v5 | 1
RACI Matrix | 9.4.190 – Document Filing Standards | Organize folders & verify consistency | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Site Administrator | v5 | 1
RACI Matrix | 9.4.190 – Document Filing Standards | Maintain contractual docs in Windows folders | File incoming/outgoing project documents to the correct system and folder (by document type). | Project Manager | v6 | 1
RACI Matrix | 9.4.190 – Document Filing Standards | Organize folders & verify consistency | Perform periodic audits of folder structure and fix noncompliance (weekly/monthly). | Site Administrator | v6 | 1
RACI Matrix | 9.4.745 – Manage Field Rework | Classify and route (NCR vs Field Problem vs internal rework) | Classify & Route | Project Manager | v2 | 1
RACI Matrix | 9.4.745 – Manage Field Rework | Classify and route (NCR vs Field Problem vs internal rework) | Classify & Route | Project Engineer | v2 | 1
RACI Matrix | 9.4.745 – Manage Field Rework | Classify and route (NCR vs Field Problem vs internal rework) | Classify & Route | APM | v2 | 1
RACI Matrix | 9.4.745 – Manage Field Rework | Develop rework plan and obtain authorization | Authorize & Plan | Foreman | v2 | 1
RACI Matrix | 9.4.745 – Manage Field Rework | Track impacts (hours/qty/schedule) and update controls | Execute & Track | General Superintendent | v2 | 1
RACI Matrix | 9.4.745 – Manage Field Rework | Verify corrected work and close item | Verify & Close | QA | v2 | 1
RACI Matrix | 9.4.745 – Manage Field Rework | Verify corrected work and close item | Verify & Close | QC | v2 | 1
RACI Matrix | 9.4.745 – Manage Field Rework | File records and communicate lessons learned | File & Report | Project Engineer | v2 | 1
RACI Matrix | 9.4.745 – Manage Field Rework | File records and communicate lessons learned | File & Report | APM | v2 | 1