SOP: 9.2.005 - Review Contract for Unfavorable or High-Risk Clauses

Department: Branch Management

Related SOPs:
- 9.2.010 - Team Selection
- 9.2.015 - Project Turnover Meeting
- 9.2.020 - Procurement of Large Feeder Wire
- 9.2.030 - Review Contract for Unfavorable or High-Risk Clauses
- 9.2.040 - Project Manager Reviews Plans Specifications & Schedule
- 9.2.055 - Compare Estimated vs Planned Performance
- 9.2.057 - Identify VE and Prefabrication Opportunities
- 9.2.060 - Create Issue List and Begin RFI Process

- 9.1.xxx – Estimating Contract Requirements Review

- 9.2.015 - Project Turnover Meeting

- 9.2.030 – PM Review Contract and High-Risk Clauses

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

PURPOSE

To establish a standardized process for reviewing contract terms to identify unfavorable or high-risk clauses before baseline planning begins, ensuring proper risk mitigation and approval protocols are in place.

SCOPE

Applies to all projects / situations where:

- New contract has been issued for review and signatures

- Contract modifications or amendments are received

- Subcontract flow down terms require review

- Risk assessment is needed before project baseline

ROLES & RESPONSIBILITIES

Branch Manager

Conducts initial contract review; Identifies risk areas; Documents concerns and mitigation strategies.  Approves risk acceptance; Authorizes contract negotiations; Final authority on high-risk decisions.

Estimator

Validates scope assumptions; Confirms pricing aligns with contract terms

Business Manager

Reviews significant risk items; Advises on liability and insurance.  Issue a letter of clarification for negotiation of the contract.

REQUIREMENTS

- Receive contract documents

- General and special conditions

- Scope of work and specifications

- Original estimate and assumptions

- Standard contract review checklist

- Company risk tolerance guidelines

PROCEDURE

STEP 1 - Obtain Complete Contract Package

Branch Manager assures all contract documents are received:

- Prime contract or subcontract agreement

- General conditions

- Special conditions

- Scope of work

- Specifications and drawings list

- Insurance and bonding requirements

STEP 2 - Conduct Initial Review

Business Manager reviews contract using standard checklist for:

- Payment terms and retainage

- Change order procedures and markup allowances

- Liquidated damages and penalties

- Indemnification and liability clauses

- Insurance requirements

- Warranty obligations

- Termination provisions

- Dispute resolution procedures

STEP 3 - Identify High-Risk Clauses

Flag clauses that present risk:

- No-damage-for-delay provisions

- Pay-when-paid or pay-if-paid terms

- Broad indemnification requirements

- Excessive insurance limits

- Unreasonable warranty periods

- One-sided termination rights

- Waiver of lien rights

STEP 4 - Document Risk Assessment

For each identified risk:

- Describe the risk and potential impact

- Assess probability and severity

- Propose mitigation strategies

- Estimate cost of risk acceptance

- Recommend approval or negotiation

STEP 5 - Obtain Approval

Present risk assessment to Branch Manager:

- Review findings and recommendations

- Obtain approval for risk acceptance or negotiation

- Document decisions and rationale

- Update project baseline if risks accepted

STEP 6 - Communicate Results

Share approved contract review with:

- Project team at turnover meeting

- Accounting for billing compliance

- Safety for insurance requirements

- Purchasing for subcontract flowdown

KEY PERFORMANCE INDIDCATORS

Contract review completed before baseline planning 100%

All high-risk clauses documented 100%

Branch Manager approval for risk acceptance 100%

Risk mitigation strategies in place 100%

APPENDIX

  - Estimating Contract Review Forms

  - Contract Review Checklist

  - Risk Assessment Matrix Template

  - Common High-Risk Clauses Reference

  - Flowdown Requirements Checklist