SOP 9.075.41 – Develop Project Schedule

Department: Project Management / Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs:9.2.015 - Project Turnover Meeting; 9.2.040 - Project Manager Reviews Plans Specifications & Schedule; 9.2.050 - Field Supervisor Reviews Plans Specifications & Schedule; 9.2.100 - Prepare Layout & Sequencing Plan; 9.2.140 - Develop Project Budget; 9.4.315 - Develop Project Schedule; 9.4.320 - Update Project Schedule; 9.4.325 - Monitor Schedule Performance

- 9.065.41 – Develop Labor Budget

- 9.070.41 – Prepare Layout & Sequencing Plan

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.5 Project Superintendent

- 7.3.1 Operations Management

- 7.4.4 Purchasing Manager

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To outline the process for developing a complete project schedule that aligns field activities, procurement, prefab, and inspections to meet project milestones and client expectations.

Scope

Applies to all awarded projects prior to mobilization. Required before final labor loading, buyout, and field execution begins.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Leads development of the project schedule and ensures alignment with the scope. |
| General Superintendent | Provides field sequence logic and confirms install feasibility. |
| Project Engineer | Supports task duration estimates, formatting, and dependencies. |
| Foreman / Field Lead | Validates manpower requirements and phase sequencing. |
| Branch Manager | Reviews and approves final schedule milestones and logic. |

Required Documents and Tools

- Contract documents and milestone requirements

- Draft construction schedule

- Labor budget

- Layout & Sequencing Plan

- Procurement and submittal logs

- GSL Schedule Template (MS Project, Smartsheet, or Excel)

Procedure

Step 1: Review Milestone Requirements

- PM reviews:

  - Contractual completion dates

  - GC milestone calendar

  - Permit and inspection deadlines

  - Long-lead material delivery dates

Step 2: Define Work Phases and Tasks

- Break down the project into:

  - Mobilization

  - Underground

  - Rough-in

  - Gear install

  - Trim-out and finishes

  - Testing, startup, and inspections

- Assign task owners and durations

Step 3: Align With Labor and Layout Plans

- Cross-check task durations and sequencing with:

  - Labor budget loading

  - Layout & sequencing strategy

  - Prefab delivery and rack install timelines

- Adjust crew size and work sequence to optimize flow

Step 4: Input Into Scheduling Tool

- PE or PM inputs tasks into GSL-approved scheduling tool

- Link dependencies and float between phases

- Highlight critical path and high-risk dates

- Include inspection and handoff checkpoints

Step 5: Review, Approve, and Publish

- GS and Branch Manager review schedule logic and dates

- Final version shared with GC, Foreman, and support teams

- Upload to project folder and print for trailer posting

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Final Project Schedule | Project Manager | Project Folder / Share Drive |
| Milestone Summary Sheet | Project Engineer | GC Correspondence Folder |
| Labor Loading by Week/Phase | PM / PE | Job Cost & Labor Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Schedule approved prior to first field mobilization | 100% |
| Schedule aligned with labor and procurement strategy | 100% |
| Milestones meet contract and GC deliverables | 100% |

References

- Contract Specifications

- GC Baseline Schedule

- Labor Budget and Layout Plan

- Procurement Log

Appendix

- GSL Scheduling Template

- Milestone Tracker

- Manpower Histogram Example