SOP 9.41.395 – Develop Project Budget

Department: Project Management / Accounting
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.2.005 - Review Contract for High Risk Clauses; 9.2.015 - Project Turnover Meeting; 9.2.040 - Project Manager Reviews Plans Specifications & Schedule; 9.2.090 - Develop Labor Budget; 9.2.110 - Develop Project Schedule; 9.4.400 - Monitor Project Costs; 9.4.405 - Manage Cost Forecasts; 9.4.425 - Manage Job Cost Reports
Reference: GSL Project Manager Procedures – Cost Management

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.3.3 Estimating

- 7.5 Accounting

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To establish a comprehensive project budget that reflects the contract value, cost codes, and anticipated expenses, serving as the baseline for cost control.

Scope

This SOP applies to Project Managers, Estimators, and Accounting.
All budget documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Prepares project budget, aligns with scope and schedule. |
| Estimator | Provides original bid data and cost breakdowns. |
| Accounting | Reviews and inputs budget into financial system. |
| Branch Manager | Approves final project budget. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Contract value and bid estimate

- Standard cost codes

Procedure

- Review contract and final estimate.

- Assign cost codes to budget line items.

- Allocate budget to labor, materials, equipment, and subcontractors.

- Review draft budget with Branch Manager.

- File approved budget per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Project Budget | Project Manager | Per SOP 190A |
| Cost Code Assignments | PM / Estimator | Per SOP 190A |
| Approval Record | Branch Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Budget developed within 10 days of turnover | 100% |
| Budget aligned with estimate and contract value | 100% |
| Approved budget filed prior to mobilization | 100% |

References

- GSL Project Manager Procedures – Cost Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- Budget Template

- Cost Code List