SOP: 9.3.010 - Setup Office Trailer

Department: Project Management / Field Operations

Related SOPs:

- 9.2.130 - Construction Execution Kickoff Meeting

- 9.3.020 - Setup Storage Trailer

- 9.3.030 - Setup Site Fencing and Access Control
- 9.3.040 - Setup Temporary Power
- 9.3.050 - Setup Temporary Water
- 9.3.060 - Setup Sanitary Facilities
- 9.3.070 - Setup Temporary Lighting
- 9.3.080 - Setup Signage

============================================================

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 4: Staging & Job Familiarization

- Tab 22: Document Management

Job Descriptions (Policy Manual Section 7):

- 7.2.5 Project Superintendent

- 7.3.1 Operations Management

- 7.4 Business Administration

- 7.4.5 Administrative Support

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

PURPOSE

============================================================

To establish a standardized process for setting up the project office trailer, ensuring proper placement, utilities, and functionality for project administration and team coordination.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Project requires on-site office facilities

- Field mobilization is underway

- Administrative workspace is needed for project team

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Approves trailer location and configuration; Coordinates delivery timing |

| Field Supervisor (R) | Oversees physical setup; Coordinates with delivery vendor; Ensures utility connections |

| Site Administrator (R) | Sets up office equipment and supplies; Establishes filing systems |

| Safety Coordinator (C) | Reviews placement for safety compliance; Ensures egress requirements |

| General Superintendent (C) | Validates location doesn't conflict with work areas |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Site logistics plan with trailer placement location

- Utility connection points (power, data, phone)

- Delivery access route confirmed

- Leveling and blocking materials

- Office furniture and equipment list

- IT/communication setup requirements

============================================================

PROCEDURE

============================================================

STEP 1 - Confirm Location and Delivery

--------------------------------------

PM and FS confirm:

- Trailer delivery date and time

- Placement location per site logistics plan

- Access route for delivery truck

- Ground conditions and leveling needs

- Utility connection locations

STEP 2 - Prepare Site for Delivery

--------------------------------------

FS ensures site is ready:

- Clear delivery path and placement area

- Verify ground is level or have leveling materials ready

- Mark utility connection points

- Coordinate with GC for any access restrictions

- Have blocking/cribbing materials on site

STEP 3 - Receive and Position Trailer

--------------------------------------

Upon delivery:

- Guide delivery driver to placement location

- Position trailer per site plan

- Level and block trailer securely

- Install steps and handrails

- Verify doors and windows operate properly

STEP 4 - Connect Utilities

--------------------------------------

Coordinate utility connections:

- Temporary power connection (see SOP 9.3.040)

- Data/internet connection

- Phone lines if required

- HVAC verification

- Plumbing if applicable

STEP 5 - Setup Interior

--------------------------------------

Site Administrator sets up:

- Desks, chairs, and furniture

- Filing cabinets and storage

- Office supplies

- Computers and printers

- Plan tables and drawing storage

- Safety board and required postings

STEP 6 - Verify and Document

--------------------------------------

Complete setup verification:

- All utilities functioning

- Safety requirements met (fire extinguisher, first aid, egress)

- Communication systems operational

- Document trailer condition with photos

- Notify team that office is operational

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| Trailer operational before field start | 100% |

| All utilities connected and functional | 100% |

| Safety requirements verified | 100% |

| Setup documented with photos | 100% |

============================================================

APPENDIX

============================================================

- Office Trailer Setup Checklist

- Standard Office Equipment List

- Required Safety Postings List

- Utility Connection Diagram

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.090 - Setup Office Trailer

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Field Operations | Approver: Executive Committee