SOP 9.4.060 – Conduct Quality Meetings

Department: Project Management / Quality Control
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.4.010 - Conduct Coordination Meetings; 9.4.020 - Conduct Subcontractor Coordination Meetings; 9.4.030 - Conduct Client/Owner Meetings; 9.4.040 - Conduct Safety Meetings; 9.4.050 - Conduct Prefabrication Coordination Meetings; 9.4.345 - Conduct Schedule Review Meetings; 9.4.515 - Develop Quality Management Plan; 9.4.520 - Conduct Quality Meetings
Reference: GSL Project Manager Procedures – Coordination

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To conduct regular quality meetings to ensure project work meets specifications, client requirements, and GSL standards.

Scope

This SOP applies to Project Managers, Field Supervisors, Safety Coordinators, and Quality Inspectors during pre-construction and throughout execution.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Schedules and facilitates quality meetings; ensures corrective actions are tracked. |
| Field Supervisor | Reports quality issues and verifies field compliance. |
| Quality Inspector (if assigned) | Reviews work in progress and documents findings. |
| Safety Coordinator | Confirms overlap between safety and quality requirements. |

Required Documents and Tools

- Project specifications

- Quality control checklists

- Inspection logs

- Non-conformance reports (NCRs)

Procedure

- Schedule Meetings – Hold monthly or as required by contract.

- Prepare Agenda – Include inspection results, NCRs, corrective actions, and upcoming milestones.

- Conduct Meeting – Review current quality status, issues, and lessons learned.

- Assign Corrective Actions – Document and track closure dates.

- File Records – Save meeting minutes and updated NCR log in project folder.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Quality Meeting Agenda | Project Manager | Project Folder |
| Meeting Minutes | PM | Project Folder |
| NCR/Corrective Action Log | Quality Inspector | Project Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Quality meetings held per contract | 100% |
| NCRs resolved within 2 weeks | ≥90% |
| Corrective actions tracked to closure | 100% |

References

- GSL Project Manager Procedures – Coordination

Appendix

- Quality Meeting Agenda Template

- NCR Log Template

- Corrective Action Log